## EOL New Countries
|  | ENRONONLINE WORLDWIDE PRESENCE |  |  |  |  | as of: | 2001-05-25
Notes:
THE AMERICAS
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
1 | Canada |  |  | Brazil | Enron Brazil | Remy Collognes | Carlos Alatorre | M. Taylor | Draft | Legal | 2001-04-01 | 08/15 No date yet. 8/31 No update. 10/20 Brent Hendry is reviewing preliminary drafts from outside counsel. 12/08 Law prohibits financial trading online. Local counsel working on other legal issues as well. 3/09 PA and ETA approved. Working on GTC and Product Long Descriptions. 3/23 Legal and Commercial team to meet next week to discuss GTC. 3/30 Content Finalized by Brazil, EnronOnline will review. GTC still being revised.
2 | United States |  |  | Colombia | Enron Coal / Enron Metals | Mike Farmer (Metals) Stuart Staley (Coal) | Mark Taylor/ Amita Gosalia | M. Taylor | Draft | Review | TBD | 08/15 Mark Taylor is restarting process. 8/31 M. Taylor to obtain ETA. Brent working on.10/20 Brent Hendry is reviewing preliminary drafts from outside counsel. 12/08 Legal problems entering into financial derivative transactions with Colombian counterparites. Legal discussions on physical commodities. 3/16 Still under review
3 | Mexico |  |  | Cayman Islands | Global Products | Chris Mahoney | Amita Gosalia | Justin Boyd |  |  |  | 05/11 New due diligence surveys to be sent to Counsel.
4 | Chile
5 | Bermuda
6 | Peru
7 | Argentina
AFRICA
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
1 | South Africa
ASIA / AUSTRALIA
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
1 | Australia |  |  | South Korea | Enron Metals | David Lilley | Amita Gosalia | Matt Lee | Draft | Draft | TBD | 8/15 Need to confirm status. 8/31 Matt Lee will update. 10/5 Derivative trades need Central bank's approval. Korean law may require amendments to ETA-awaiting legal advice. 11/3 The only possible amendment to the ETA would be to recite that LME Contracts are conducted through Enron Metals Limited (Korean Branch), the local futures broker. LME Contracts qualify as "overseas futures" under the Korean futures law, and accordingly must be conducted through a local futures broker. Enron Metals Limited (Korean Branch) is a local futures broker and we are intending to approach the regulator (the FSS) for a ruling that we can effect LME Contracts via EOL "through" Enron Metals Limited (Korean Branch). No issues for physical metals trades. 12/08 Meeting with regulator being arranged. 03/02 It is recommended that financial transactions be conducted with affiliates registered in other countries. e.g. Singapore, Hong Kong, Japan etc. 5/25 approved for physical products, waiting on response from legal concerning financial products
2 | Japan |  |  | Malaysia | LNG |  |  |  | Review | Cancelled |  | 3/02 Due Diligence in progress. 4/27 Counsel's opinion under review. 5/18 Cancelled.
3 | Singapore |  |  | India | Enron Metals | Eric Gadd | Amita Gosalia | Justin Boyd | Reviewing | Reviewing | TBD | 11/24 New due diligence surveys have been sent to Counsel in this jurisdiction. 03/23 Advice received to date has been unclear and we are seeking further clarification from counsel on a number of points. 05/11 Enron comments on final draft of advice being sent today. 5/25 Awaiting response to our comments on final draft of advice.
4 | Hong Kong
5 | Taiwan
6 | Israel
7 | China
EUROPE
# | Available at: |  |  | In the works: | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
1 | Austria |  | 1 | Dutch Antilles | Seafreight | Andy James | Amita Gosalia | Justin Boyd | Reviewing | Approved |  | 03/23 New due diligence surveys to be sent to Counsel. 5/11 Response expected shortly. 5/18 Approved
2 | Belgium |  | 2 | Hungary | Central Europe Orig | Antony Steiner | Amita Gosalia | Justin Boyd | Reviewing | Reviewing |  | 03/23 New due diligence surveys to be sent to Counsel. 5/11 Counsel's advice under review
3 | Croatia |  | 3 | British Virgin Islands | Enron Coal / Enron Metals | Pierre Aury/ Tim Jones | Amita Gosalia | Justin Boyd | Reviewing | Reviewing |  | 02/12 Due diligence commenced. 02/16 Due Diligence completed. 3/02 No issues in relation to trading of pulp & paper, bandwidth capacity, bullion and energy commodities. 3/09 Working on legal information for all commodities.
4 | Czech Republic
5 | Denmark
6 | Finland
7 | France
8 | Germany
9 | Greece
10 | Ireland
11 | Italy
12 | Latavia
13 | Monaco
14 | Netherlands
15 | Norway
16 | Poland
17 | Portugal
18 | Romania
19 | Russia
20 | Slovakia
21 | Slovenia
22 | Spain
23 | Sweden
24 | Switzerland
25 | Turkey
26 | United Kingdom
Print Report

## EOL New NA Products
|  | ENRONONLINE NEW PRODUCTS STATUS Managed by US office |  |  |  | as of: | 2001-05-25
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
| Freight | US Tanker Freight Swap | US | Freight | Joe King | Robert Cass | Kevin Meredith |  | For Release | 2001-06-01 | 5/18 Needs to be discussed with Tax & Legal. 5/25 Waiting on approval from legal, to be released June 4th.
| Freight | US Tanker Freight Swap | US | Freight | Joe King | Robert Cass | Kevin Meredith | Test | Test | 2001-06-01 | 5/18 Needs to be discussed with Tax & Legal.
| Gas | Can Gas Fin Opt Call/Put (INTERNAL ONLY) | CAN | Gas | Lon Draper | Robert Cass | Melba Lozano | On Hold | On Hold | 2001-03-01 | 3/09 Description in Legal, Launch target is March 19th. 3/16 Waiting on notice from Savita. Product on Hold. 3/30 Product Revised. 4/20 On Hold. 5/11 Product changed to External.
| Gas | US Gas Secondary Firm | US | Gas | Kevin Ruseitti | Robert Cass | Chris Walker | Test | Test | 2001-04-01 | 4/13 Drafting Language. 4/20 Product on Hold. 4/27 Product in Test. 5/11 Waiting on GTC launguage from legal
| Global Products | US SYN Fuel Coal | US | Global Products | Lenny Hochschild | Robert Cass | Chris Walker | On Hold | On Hold | 2001-04-01 | 3/30 Drafting Language. 4/9 Product Type on hold pending Legal development of GTC's and logistics, etc. 4/20 Product on Hold. 5/11 Waiting on GTC from legal.
| Newsprint | Can Newsprint Phy | CAN | Newsprint | Gary Nelson | Robert Cass | Chris Walker |  | For Release | 2001-06-01 | 5/25 Waiting on approvals to be released June 4th.
| Power | Us West Power CAISO Spread | Us | Power | Bob Badeer | Robert Cass | Kevin Meredith | Review | Review | 2001-03-01 | 3/09 Description being reviewed by trader,
| Power | US Phy Power Call and Put | US | Power | Harry Arora & Robert Stalford | Robert Cass | Melba Lozano |  | For Release | 2001-06-01 | 5/25 Waiting on approvals to be released June 4th.
| Recovered Paper | Can Recycled OCC Phy | CAN | Recovered Paper | Gary Nelson | Robert Cass | Chris Walker |  | For Release | 2001-06-01 | 5/25 Pending Sigma factor and GTC. Waiting on approvals to be released June 4th.
| Recovered Paper | Can Recycled ONP Phy | CAN | Recovered Paper | Gary Nelson | Robert Cass | Chris Walker |  | For Release | 2001-06-01 | 5/25 Pending Sigma factor and GTC. Waiting on approvals to be released June 4th.

## EOL New London Products
|  | ENRONONLINE NEW PRODUCTS STATUS Managed by London Office |  |  |  |  | as of: | 2001-05-25
TRANSACTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
| Bullion | Gold and Silver | London | Metals | Tony Piper/ Martin Dulake | Amita Gosalia | Kristina/Arfan | Reviewing | Reviewing | TBD | 11/3 Meeting with trader to be set up. 11/10 Due diligence commenced. Long descriptions being drafted. 12/08 Tentative launch date Dec 15th. 01/05 Awaiting information from legal and traders. 01/19 Due diligence for Sweden, Switzerland, South Africa and Austrailia completed. Awaiting results form USA, Peru, Mexico, and Canada. Legal agreed to use ISDA as main trading agreement. 02/09 Credit commenced counterparty review. 05/11 Joe Gold wants to launch Silver, Platinum and Palladium, but not Gold. Will launch product when experienced traders are hired.
| Coal | Seafreight Swaption | London | Seafreight | Andy James | Amita Gosalia | Arfan |  |  |  | 05/11 Agreed with Andy James that product would be changed from Asian option to Swaption. Awaiting fixes to short description in Options functionality.
| Coal & Freight | Seafreight Auction | London | Coal & Freight | Pierre Aury | Amita Gosalia | Philippa | Reviewing | Reviewing |  | 03/16 Awaiting info from trader. 5/11 Meeting with traders on May 14 to discuss requirements. 5/18 working with traders to define auction
| Freight | Singapore Tanker Freight | London | Freight | Paul Henking | Lara McKinney | Arfan |  | Reviewing | 2001-06-18 | 5/25 long desc approved, with traders
| Metals | Nickel Phys x 3 | London | Metals | Fritz Ten Doornkaat | Amita Gosalia | Arfan | Legal | Legal | 2001-05-29 | 03/16 Product development to commence in April. 04/20 Trader reviewing Product Long Description. 4/27 Long Description resent to Trader- awaiting response. 5/11 Long Desc and GTCs approved, awaiting profiles from legal and credit. To be launched on 6-4-01 as per trader's request.
| Metals | Cobalt Phys | London | Metals | Fritz Ten Doornkat | Amita Gosalia | Arfan | Reviewing | Reviewing | 2001-05-29 | 4/27 Long Description sent to trader- awaiting response. 5/11 As per trader's request, will review LD after Phys Nickel is launched.
| Metals | Aluminum Alloy Physical | London | Metals | Stephen Upot | Lara McKinney | Arfan |  | Reviewing | TBD | 5/25 trader unsure of launch date
| Natural Gas | UK Gas vs Belgian Gas Location Spread | London | Natural Gas | David Furner | Amita Gosalia | Arfan | Legal | Legal | 2001-05-08 | 03/16 EnronOnline functionality to be tested for this. 03/23 LD drafted. Awaiting GTCs from Legal. Awaiting system changes. 04/20 System changes complete. Awaiting GTCs from external counsel. 4/27 Still awaiting info from legal counsel.
| Natural Gas | Belgian Gas Phys Zeehub Option | London | UK Gas | Nicola Craig | Amita Gosalia | Philippa |  |  | 2001-05-28 | 05/11 LD and GTC awaiting trader approval.
| Natural Gas | EnCap Auction | London | UK Gas | Matt Fergusson | Lara McKinney | Philippa | Reviewing | Cancelled | 2001-06-30 | 5/18 with traders to develop content and structure. 5/25 Cancelled by traders
| Oil | Gasoil Phys | London | Oil | Henkka Talvitie | Amita Gosalia | Kristina Zoe | Reviewing | Reviewing | 2001-06-11 | 4/27 Arranging meeting with Trader and Logistics. 5/11 Graham Cane to provide GTC and LD.
| Oil | Gasoline Crack Spread Fin | London | Oil | John Spencer | Amita Gosalia | Philippa | Reviewing | Reviewing
| Oil | Diesel Phys | London | Oil | Ross Koller | Amita Gosalia | Zoe/Kristina |  |  | 2001-06-11 | 4/27 Arranging meeting with Trader and Logistics 05/11 GTCs and LD awaited from Graham Cane.
| Options | Metals | London |  | Tim Jones | Amita Gosalia | Lara | Reviewing | Reviewing |  | 02/09 Awaiting info from Dave F. 5/18 Awaiting change to option fuctionality
| Options | Norway Power | Oslo |  | Thor Lien | Amita Gosalia | Alan | Reviewing | Reviewing |  | 02/09 Awaiting info from Dave F. 5/18 Awaiting change to option fuctionality
| Options | UK Gas | London |  | Dave Redmond | Amita Gosalia | Philippa | Reviewing | Reviewing |  | 02/09 Awaiting system upgrade to deal with Phys options. 5/18 awaiting trader to launch
| Options | Int Coal | London |  | Jez Peters | Amita Gosalia | Caroline | Reviewing | Reviewing |  | 02/09 Awaiting system upgrade to deal with Phys options. 4/27 Trader training new traders on desk - not ready to post option prices on EnronOnline
| Paper | Physical Paper | London | Paper | Niclas Egmar | Lara McKinney | Arfan |  | Reviewing | 2001-06-11 | 5/25 long desc and GTCs with traders
| Softs | Coffee, Sugar, Cocoa | London | Softs | Trena McFarland | Amita Gosalia | Arfan | Legal | Legal | TBD | 11/3 Awaiting info from commercial group. 11/10 Long descriptions to be approved by commercial prior to legal review. 12/01 on hold. 12/08 Approximate launch date Dec 15th. 01/19 Awaiting Senior Management sign off. 03/02 Many legal and tax issues to be setteled. 3/16 Product to be managed from New York. Waiting on info from Trader.

## Activated Countries
|  |  |  | ACTIVATED COUNTRIES |  | as of: | 2001-05-25
THE AMERICAS
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
|  | 2000-10-05 | Bermuda | Weather | Waiting on Info | Leonardo Pacheco | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 No date yet. Mark Taylor is checking and will get back to us. 8/31 M. Taylor will get ETA. Brent is working on country. 10/5 Bermuda's legal forms are the same as North America's. Done
|  | 2000-10-05 | Chile | MG | Bruce Garner | Amita Gosalia | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking). 10/5 Chile can use NA's ETA and PA. Enron entity must not be present in Chile and EOL agreements should not be subject to local law. Done
|  | 2000-10-05 | Peru | MG | Bruce Garner | Amita Gosalia | M. Taylor | Approved | Approved | 2000-09-01 | 08/15 More info Wed. 8/31 May need an agent for service of process in the U.S. (Brent is checking). 10/5 Chile can use NA's ETA and PA. Enron entity must not be present in Chile and EOL agreements should not be subject to local law. Done
|  | 2000-10-20 | Argentina | Enron Argentina | Patrick Hansen | Carlos Alatorre | M. Taylor | Approved | Approved | 2000-10-01 | 08/15 Draft of legal Documents later this week. 8/31 Draft has not been forthcoming. 09/07 Pending! 10/13 Waiting on approval for legal documents.10/20 Legal approval for PA, ETA, GTC-phy gas, and Phy Gas prod Description. To be launched on Oct 23rd. Done
AFRICA
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
|  | 2000-10-05 | South Africa | Enron Coal | Peter Bradley | Amita Gosalia | Justin Boyd | Approved | Approved | TBD | 08/15 No date yet. 8/22 Issue: South Africans can not make payments to non-residents without approval of Reserve Bank. Reserve Bank gives no approvals to South Africans in respect of commodity or derivative transactions with foreign counterparties. 9/22 Allowed to trade commodities but must provide evidence of exchange control approval. Oct 5 - Approved to trade LME Contracts, commodity and weather derivatives, physical non-ferrous metals and coal. South African ctprty to provide evidence of exchange control approval in advance.
ASIA / AUSTRALIA
# | Available at: | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
|  | 2000-10-05 | China | MG | Bruce Garner | Amita Gosalia | Justin Boyd | Approved | Approved | TBD | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange. 9/22 Gas and power cannot be traded, waiting for metal, coal and oil. 10/05 Approved to trade OTC forwards from overseas base. Await info re: other derivatives and physical metal, coal and oil.
|  | 2000-10-05 | Hong Kong | MG | Bruce Garner | Amita Gosalia | Justin Boyd | Approved | Approved | 2000-10-01 | 8/15 Initial and follow up advice received. Further clarification still needed. 9/22 Legal review. 10/05 - Approved to trade LME Contracts, OTC commodity derivatives and physical commodities.
|  | 2000-10-20 | Taiwan | Enron Metals | David Lilley | Amita Gosalia | Matt Lee | Draft | Completed | TBD | 8/15 Need to confirm status. 8/31 Matt Lee will update. 9/22 - Some due diligence completed, Justin forwarded additional instructions. 10/05 Free to trade Physical/derivatives for oil and metals. Many import hurdles and maybe some withholding tax impact on derivative income (up to 20%) 10/20 The execution and marketing of LME Contracts will require a local licence if Enron is deemed to engage in futures in Taiwan. The mere availability and use of the website EOL does not give rise to this. however, any other direct solicitation or marketing into Taiwan will give rise to a licence. Completed
|  | 2000-11-03 | Israel | Seafreight | Pierre Aury | Amita Gosalia | Robert Quick | Completed | Completed | 2000-10-01 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 Advice outstanding: due at end of August. 10/5 - Free to trade LME Contracts and commodity derivatives. Insurance companies, pension funds and municipalities to be excluded. Israeli ctprtys to provide evidence of exchange control approval prior to transaction. Awaiting additional advice re physical trading. 11/3 The physical trading of all commodity products for delivery outside Israel is generally permitted. Completed
|  | 2001-02-16 | China | Enron Metals | Bruce Garner | Amita Gosalia | Justin Boyd | Done | Done | TBD | 8/22 Commodity derivatives trading within China is not promoted unless it takes place on a domestic futures exchange. 9/22 Gas and power cannot be traded, waiting for metal, coal and oil. 10/5 Approved to trade OTC forwards from overseas base. Await info re: other derivatives and physical metal, coal and oil. 11/3 Commodity derivatives: cannot trade these as there is no express legal basis under PRC law. Other legal restrictions also apply. LME Contracts: (i) physical marketing in PRC should be avoided and marketing should be restricted to PRC counterparties with an established trading record, and (ii) PRC counterparties are required to obtain business permit and other governmental licences to conduct overseas commodity futures trading (this will involve Enron Metals Limited and the LME being designated as approved bodies). Generally free to buy/sell physical copper for delivery in-warehouse in PRC. Natural gas/electric power: cannot trade, foreign participation prohibited. Await advice in relation to physical trading of coal and oil. 02/16 Done
EUROPE
|  | Date Changed | Activated Country | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for: | Comments:
# | Available at: | 2000-10-20 | Latavia | MG | Bruce Garner/ David Lilley | Amita Gosalia | Robert Quick | Draft | Completed | 2000-10-01 | 9/22 can trade commodity derivatives. 10/5 - Free to trade commodity derivatives. Banks and insurance companies should be excluded. 10/20 Completed
|  | 2000-10-20 | Russia | MG | Bruce Garner/ David Lilley | Amita Gosalia | Robert Quick | Draft | Completed | 2000-11-01 | 8/15 Initial and follow up advice received. Further clarification still needed. 8/22 Issues; A) Risk of non-deliverable transactions not unforeseeable. B) Payments in foreign currency might require case-by-case consent from Central Bank. C) Every trade with a Russian counterparty needs to be documented in writing. 10/5 Free to trade LME contracts and in commodities and commodity derivatives. There are licensing requirements for power, metal and gas. Cash settled derivatives could be regarded as unenforceable gaming contracts under Russian law. Central Bank license needed for exchange control purposes. 10/20 Completed
|  | 2000-11-24 | Greece | Seafreight | David Lilley | Amita Gosalia | Justin Boyd | Completed | Completed | 2000-09-01 | 8/15 Initial outside legal responses received. Issues need clarification. 8/22 There are significant restrictions on trading in gas and power. In addition, only companies possessing a license issued by the Ministry of Development can trade oil. No License required only permission from Capital Mkt. Committee. 9/22 waiting on legal advice on metal, coal, and oil. 10/5 Free to trade commodity derivatives but need permission to solicit within Greece. Physical trading of electricity and gas not permitted. Awaiting legal advice on physical trades in metal, coal and oil. 10/20 Physical trading of coal and metals permitted. Seeking clarity re physical trading of crude, electricity and gas. 11/6 Free to trade commodity derivatives but need permission to solicit within Greece. The costs of such approval will be limited to nominal administrative costs and legal expenses – it is difficult to determine the time it would take to obtain such approval, given the infrequency of the procedure being used. Physical trading of crude, electricity and gas not permitted without a licence - this only relates to trading activities within Greece. Physical trading of coal and metal is permitted. 11/24 Completed
|  | 2000-11-24 | Monaco | Enron Metals | Tim Jones | Amita Gosalia | Justin Boyd | Completed | Completed | TBD | 11/3 New due diligence surveys have been sent to Counsel in this jurisdiction. 11/17 Trading of physical metals and metals derivatives is permitted. It is important, for regulatory purposes, that trades are negotiated and concluded by the applicable Enron trading entity without any physical presence in Monaco. 11/24 Completed for metals only
|  | 2000-12-08 | Slovakia | Cont Power | Guther Tuhy | Amita Gosalia | Justin Boyd | Completed | Completed | TBD | 11/3 New due diligence surveys have been sent to Counsel in this jurisdiction. 12/08 Completed
|  | 2000-12-08 | Turkey | Seafreight | David Lilley | Amita Gosalia | Justin Boyd | Completed | Completed | 2000-09-01 | 8/15 Initial outside legal responses received. 8/22 For enforceability a hard copy of an umbrella agreement should be signed. Follow up advice awaited!!! 9/22 ETA and PA needs to be adapted for Turkish law. 10/5 Free to trade commodity derivatives. Await advice in relation to physical trading. Law may require changing the ETA and PA. 10/20 ETA and PA amended. Trading and marketing of commodity derivatives requires prior approval of Turkish Capital Markets Board. 11/3 After further discussions with Counsel, it seems that the prior approval of the Turkish Capital Markets Board is only required for marketing (including via the Internet) to the public at large; no approval would therefore apply to our trading activities. A further adaptation of the ETA is required to take into account Turkish currency law matters. 11/17 Time required for the approval from Turkish Capital Markets Board is estimated at 3 months. 12/08 Completed

## Activated Products
|  | ACTIVATED PRODUCTS |  |  |  | as of: | 2001-05-25
US TRANSACTION PRODUCTS
Date Changed | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
1900-01-06 | AUS and JPN Weather | Weather Options | US | Weather |  |  | Dale Neuner | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II . 8/29 To be launched this week. 09/07 Launched yesterday. Done
2000-09-14 | Power | East Cinergy Peak Splits | US | Power |  |  | Dale Neuner | Active | Active | 2000-09-01 | 09/07 Testing products. 9/14 Done
2000-10-20 | Gas | Phy 3/5/10 day swing | US | Gas | Scott Hendrickson | Dale Neuner | Dale Neuner | Active | Active | TBD | 9/22 Legal language drafted and sent to commercial 10/05 In testing Stage 10/13 To be released on Oct 16th 10/20 To be released on 10/20
2000-10-20 | Gas | PHY Fwd | US | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Active | Active | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 10/13 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 10/20 Product completed, to be activated on 10/23
2000-10-20 | Isobutane | Fin Swap | US | Petchems | Wade Hicks | Dale Neuner | Robert Cass | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/05 Approved for release, waiting to be uploaded.10/20 uploaded 10/06
2001-05-11 | Global Products | US No.2 E. Fin Opt Call & Put | Us | Global Products | Mario DeLaossa | Robert Cass | Kevin Meredith | Approved | DONE | 2001-04-01 | 3/30 Drafting Language. 4/13 Test. 4/20 Product in Test. 4/27 Approved
2001-05-11 | Global Products | US No.2 A. Fin Opt Call & Put | Us | Global Products | Mario DeLaossa | Robert Cass | Kevin Meredith | Approved | DONE | 2001-04-01 | 3/30 Drafting Language. 4/13 Test. 4/20 Product in Test. 4/27 Approved
2001-05-11 | Global Products | Ethane Fin Opt Call & Put | US | Global Products | Lee Jackson | Robert Cass | Melba Lozano | Approved | DONE | 2001-04-01 | 4/13 Testing. 4/27 Approved
2001-05-11 | Global Products | Propane Fin Opt Call & Put | US | Global Products | Lee Jackson | Robert Cass | Melba Lozano | Approved | DONE | 2001-04-01 | 4/13 Testing. 4/27 Approved
2001-05-11 | Steel | US Plate Base Fin | US | Steel | Sean Keenan | Robert Cass | Robert Cass | Approved | Approved | 2001-04-01 | 4/13 Drafting / testing. 4/20 On Hold. 5/11 to be uploaded on 5-14
2001-05-11 | Capacity | US Pipeline Capacity NNG Daily | US | Capacity |  | Robert Cass | Melba Lozano | Approved | Approved | 2001-05-01 | 4/27 Testing. 5/11 Product type uploaded 5-7
2000-10-20 | Isobutane | Phy FOB | US | Petchems | Wade Hicks | Dale Neuner | Robert Cass | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/05 Approved for release, waiting to be uploaded.10/20 uploaded 10/06
2000-10-27 | Gas | Phys Index non-x <= 1Mo (Restricted) | US | Gas | Tori Kuykendahl | Dale Neuner | Dale Neuner | Active | Active | TBD | 9/22 reviewing Counterparty access 10/05 In testing stage 10/13 to be released on Oct 16th. 10/20 To be released on 10/20. 10/27 Done
2000-10-27 | NNG Capacity | US Pipeline Capacity | US | Gas | Steve Kirk | Robert Cass | Carl Carter/Naveed Ahmed | Active | Active | 2000-10-01 | 10/20 Product in Test. 10/27 To be Launched on 10/30
2000-10-27 | Polymers | PGC3 (Polymer Grade Propylene Fin Swap) | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | TBD | 9/28 in Draft 10/20 To be released on 10/23. 10/27 Done
2000-10-27 | Polymers | Polypropylene Fin Spread | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | TBD | 9/28 in Draft 10/20 To be released on 10/23. 10/27 Done
2000-11-03 | E/P Mix | Fin Swap | US | Petchems | Adam Gross | Dale Neuner | Dale Neuner | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/27 Product to be released. 11/03 Product Released
2000-11-03 | E/P Mix | Phy FOB | US | Petchems | Adam Gross | Dale Neuner | Dale Neuner | Active | Active | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 product types in legal awaiting approval. 10/27 Product to be released. 11/03 Product Released
2000-11-03 | Heating Oil | US Heating Oil2 Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/23
2000-11-03 | Jet Kerosene | US Jet Kerosene Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/24
2000-11-03 | Polymers | US LLDPE-Ethylene Fin Spread | US | Petchems | Lee Jackson | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/25
2000-11-03 | Steel | Physical Steel | US |  | Jason Seigal/ Shawn Keenan | Carl Carter/Naveed Ahmed | Robert Cass | Active | Active | TBD | 8/16 No legal documents for this commodity, In legal review. 9/22 Harry Collins in legal is developing documents. 10/05 Financial products will roll out first followed by Physical. 10/13 GTCs for physical created. 10/20 Three steel product types have been created for financial in test. 10/27 Steel financial products to be released (Hot rolled/Cold rolled/ Galvanized) 11/03 Financial products released
2000-11-03 | Unleaded Gasoline | US Unleaded Gas Fin Spread | US | Petchems | John Nowlan | Robert Cass | Robert Cass | Active | Active | 2000-10-01 | 10/20 To be released on 10/23. 11/03 released on 10/26
2000-11-10 | Gas | 3 Products for MultiMonth Gas Flex | US | Gas | Tori Kuykendahl | Robert Cass | Melba Lozano | Approved | Approved | 2000-11-01 | 11/9 Product released on 11/9
2000-11-17 | Power (weather desk) | US Power Fin Swap | US | Weather | Kevin Presto | Robert Cass | Robert Cass | Approved | Approved | 2000-11-01 | 11/03 Product to be released 11/17 Product Released
2000-11-24 | Bandwidth | US Bandwidth STM-1 | US | EBS | Jay Hawthorn | Robert Cass | Robert Cass | Completed | Completed | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product is pending legal review. 11/17 Product scheduled for release on 11/20. 11/24 Product missed upload but now scheduled for 11/28
2000-11-24 | Gas | Secondary Capacity - Pipeline | US | Gas | Colleen Sullivan | Carlos Alatorre | Carlos Alatorre | Completed | Completed | 2000-11-01 | 11/10 Product scheduled for release on 11/15. 11/24 Done | ~
2000-11-24 | Mixed Xylene | US Mixed Xylene Fin Swap | US | Petchems | John Nowlan | Robert Cass | Melba Lozano | Completed | Completed | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product schedule for release on 11/20. 11/17 Product scheduled for release on 11/20. 11/24 Product released
2000-11-24 | Nitrate Toluene | US Nitrate Toluene Fin Swap | US | Petchems | John Nowlan | Robert Cass | Melba Lozano | Completed | Completed | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product scheduled for release on 11/20. 11/17 Product scheduled for release on 11/20. 11/24 Product released
2000-12-08 | Crude | US WTI Fin Swap (Basis) | US | Petchems | Rob Fuller | Robert Cass | Robert Cass | Approved | Approved | 2000-11-01 | 11/03 Need product in test. Test site is unavailable until 11/6. 11/10 Product in Test. 12/08 Approved and active
2000-12-15 | Weather | Hong Kong Weather | Australia US | Australia US | Paul Quilkey Michael Nguyen | Justin Timothy Kevin Meredith | Justin Timothy Kevin Meredith | Approved | Approved | 2000-11-01 | 11/03 Australia product being finalized in USA (backup team). Product needs GTC's before it can be released. Early release is requested by Australia. 11/10: Update this item has been revised to allow Hong Kong locations for current Australia product. As such it is not a new product. Australia Product will be amended with a new GTC from Legal to cover Hong Kong reference locations. History of entry: Australia product being finalized in USA (backup team). Product needs GTC's before it can be released. Early release is requested by Australia. 11/17 Creation of a world weather product is being reviewed that would accommodate this Australian Product with Hong Kong location. 12/08 HK locations added to existing product types for both Australia and Houston office. 12/15 No new product type required/Done
2000-12-15 | MTBE | FIN Swap | US | Global Prod | Larry Gagliardi | Robert Cass | Kevin Meredith | Approved | Approved | 2000-12-17 | 12/01 Requested. 12/08 Test. 12/17 Product to be activated
2000-12-22 | Bandwidth | US Bandwidth Premium Service IP Transport | US | Bandwidth | John Suarez | Ahmed / Cass | Rob Cass | Approved | Approved | 2000-12-01 | 12/22 Special Product development for Analyst demonstration of IPQod system with Andersen Consulting.
2000-12-23 | Bandwidth | US Bandwidth Standard Service IP Transport | US | Bandwidth | John Suarez | Ahmed / Cass | Rob Cass | Approved | Approved | 2000-12-01 | 12/22 Special Product development for Analyst demonstration of IPQod system with Andersen Consulting.
2000-12-24 | FGT | US Pipeline Capacity FGT (Firm) | US | Pipeline (FGT) | Steve Hotte | Carter/ Cass | Kevin Meredith | Approved | Approved | 2000-12-01 | 12/22 FGT Pipeline capacity products to be released.
2000-12-25 | FGT | US Pipeline Capacity FGT (Interruptible) | US | Pipeline (FGT) | Steve Hotte | Carter/ Cass | Kevin Meredith | Approved | Approved | 2000-12-01 | 12/22 FGT Pipeline capacity products to be released.
2000-12-26 | Global Products | US Ethane vs Polyethylene Fin Spread | US | Global Prod | Allen Ingberg | Robert Cass | Kevin Meredith | Approved | Approved | TBD | 12/08 new product request. 12/15 Product to be activated.
2001-01-05 | Bandwidth | US Bandwidth Premium Service IP Transport | US | Bandwidth | John Suarez | Ahmed / Cass | Rob Cass | Approved | Approved | 2000-12-01 | 12/21 Special Product development for Analyst demonstration of IPQod system with Andersen Consulting. 1/5/01 Product to be released
2001-01-05 | Bandwidth | US Bandwidth Standard Service IP Transport | US | Bandwidth | John Suarez | Ahmed / Cass | Rob Cass | Approved | Approved | 2000-12-01 | 12/21 Special Product development for Analyst demonstration of IPQod system with Andersen Consulting. 1/5/01 Product to be released
2001-01-05 | Power (Canadian) | Alberta Power Fin Swap - | Canada | Canada Power | Bill Greenizan | Robert Cass | Melba Lozano | Approved | Approved | TBD | 11/17 Product request being reviewed - 3 descriptions (1 Product Type) On Peak Power; Off Peak Power, Flat Power. 11/24 In Test. 12/08 product being reviewed for additional legal concerns. 12/15 Product on hold in legal until Jan 2001- pending further review of market opening and regulatory issues. 01/05 Product to be released
2001-01-12 | Financial Currency | Financial Currency Forward Swap (Internal) | US | FX | William Stuart | Robert Cass | Melba Lozano | Approved | Approved | 2001-01-01 | 1/12 Internal Product released for activation in Production.
2001-01-12 | Gas | Fin Option (European Put / Call) | US | Gas |  | Robert Cass | Melba Lozano | Approved | Approved | 2001-01-01 | 1/12 European Call and Put products created through release of Options Mgr.
2001-02-02 | Steel | Physical Steel | Us | Steel | Carl Carter | Robert Cass | Melba Lozano | Approved | Approved | 2001-02-01 | 02/02 Product being prepared for release this week.
2001-03-02 | Gas | Put and Call Floating Strike Price | Us | Gas | Larry May | Robert Cass | Melba Lozano | Done | Done | 2001-02-01 | 1/19 Working with legal to get language approved. Currently in test. 02/02 Language approved by legal. Currently in Test. 02/09 Product being tested. 02/16 Problems with bridging, working on solution. 03/02 Uploaded in production, will trade on 3/19/01
2001-03-02 | Global Products | US Residual Fuel Oil Fin Swap | Us | Global Products | Sarah Mulholland | Robert Cass | Chris Walker | Done | Done | 2001-03-01 | 2/16 Ready for testing. 02/23 working on commodity code. 03/02 Done
2001-03-09 | Gas | US Spread Product | Us | Gas | Pete Keavey John Arnold Fletch Sturm | Robert Cass | Kevin Meredith | Done | Done | 2001-02-01 | 2/16 Being reviewed by traders and legal. 02/23 Approved by legal, launch target is Mar 5th. 3/09 Launched 03/05/01. Done
2001-03-09 | Global Products | US WTI Phy Basis | US | Global Products | Robert Fuller | Robert Cass | Robert Cass | Done | Done | 2001-01-01 | 12/13 Request to create a physical product type for a WTI Crude Basis product. 12/20 Discussions with Rob Fuller. Reviewing request with technical capability of EOL ( Beth Cowan). 1/05 Meeting scheduled with Global Products and marketing. 1/12 Product being discussed with Trader. 1/19 Product index changed after review by Trader. Legal is reviewing product description. 02/02 Product specs and requirements have changed; pending further review. 02/09 Product Description for exchange product being reviewed by trader. 02/16 Trader approved language. Legal, credit, tax and RAC reviewing product. 02/23 Approved by legal, in test. 03/02 Legal drafting GTC. 3/09 to be launched 3/19/01. 3/23 Product launched after changes to GTC
2001-03-09 | Power | Balance of Day Power | US | Power | Joe Stepenovitch | Robert Cass | Melba Lozano | Done | Done | 2001-02-01 | 1/19 Legal has approved load shapes. Currently in Test. 2/01 Trader is using Test to train himself for production. He will do a demo for his desk heads. 02/09 Being reviewed by head trader. 02/23 Traders launch target is Mar 5th. 03/02 Trader doing more testing. 3/09 Larunch date is 03/19/01
2001-03-09 | Gas | EOL AECO Daily (INTERNAL ONLY) | CAN | Gas | Mike Cowan | Robert Cass | Melba Lozano | Done | Done | 2001-03-01 | 3/09 Launch target is March 12th.
2001-03-23 | Global Products | US Crude Fin Options | Us | Global Products | Pavel Zadorozhny | Robert Cass | Kevin Meredith | Completed | Completed | 2001-03-01 | 3/15 Product to be tested. 3/23 Completed- product released
2001-03-30 | Global Products | US Residual Fuel Oil NYH 1% Fin Spread | Us | Global Products | Sarah Mulholland | Robert Cass | Chris Walker | Completed | Completed | 2001-03-01 | 3/09 Language approved, Launch target is March 19th. 03/16 Releasing 3/19
2001-03-30 | Global Products | US Residual Fuel Oil GC 3% Fin Spread | Us | Global Products | Sarah Mulholland | Robert Cass | Chris Walker | Completed | Completed | 2001-03-01 | 3/09 Language approved, Launch target is March 19th. 03/16 Releasing 3/20
2001-04-01 | Global Products | US Crude Fin Options | Us | Global Products | Pavel Zadorozhny | Robert Cass | Kevin Meredith | Completed | Completed | 2001-03-01 | 3/15 Product to be tested. 3/23 Completed- product released
2001-04-06 | Lumber | US Lumber Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Lumber | US Lumber Physical | US | Clickpaper | Bob Crane | Robert Cass | Chris Walker | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Newsprint | US Newsprint Physical | US | Clickpaper | Bob Crane | Robert Cass | Chris Walker | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Newsprint | US Newsprint Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Packaging | US Packaging Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Panels | US Panels Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Panels | US Panels Physical | US | Clickpaper | Bob Crane | Robert Cass | Chris Walker | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Power | Us Power COB-Mid C Spread | Us | Power | Sean Carndall | Robert Cass | Kevin Meredith | Completed | Completed | 2001-03-01 | 3/09 Description in Legal, 3/16 Releasing on 3/19. 3/23 Done
2001-04-06 | Power | US East Power Phy Fwd EES | US | Power | Eric Saibi | Robert Cass | Chris Walker | Test | Completed | 2001-04-01 | 3/30 Tesing product - Releasing 4/9. 4/06 Done
2001-04-06 | Recycled OCC11 | US Recycled OCC11 Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Recycled OCC11 | US Recycled OCC11 Physical Swap | US | Clickpaper | Bob Crane | Robert Cass | Chris Walker | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Recycled ONP8 | US Recycled ONP8 Financial Swap | US | Clickpaper | Bob Crane | Robert Cass | Kevin Meredith | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Recycled ONP8 | US Recycled ONP8 Physical Swap | US | Clickpaper | Bob Crane | Robert Cass | Chris Walker | Aproved | Completed | 2001-03-01 | 3/23 Request to migrate Clickpaper products to EnronOnline. Product being created in production for 4/09 release. 4/06 Done
2001-04-06 | Global Products | US Physical RGC3 | Us | Global Products | Chad South | Robert Cass | Chris Walker | Aproved | Aproved | 2001-03-01 | 2/16 Drafting Product Long Description. 02/23 Drafting GTC. 3/09 Testing product. 3/16 Revising Long Description. 3/30 To be released 4/9. 4/06 Done
2001-04-13 | Weather | US Weather Basket | US | Weather |  | Robert Cass | Kevin Meredith | Approved | Approved | 2001-04-01 | 4/13 Release date 4/23.
2001-04-13 | Gas | US Gas Fin Swap ENA (Internal only) | US | Gas | Pete Keavey | Robert Cass | Chris Walker | Approved | Approved | 2001-04-01 | 4/13 Release date 4/23.
2001-04-27 | Steel | US Plate Base Phy | US | Steel | Sean Keenan | Robert Cass | Robert Cass | Approved | Approved | 2001-04-01 | 4/13 Drafting / testing. 4/20 Approved
2001-04-27 | Weather | US Weather Basket | US | Weather |  | Robert Cass | Kevin Meredith | Approved | Approved | 2001-04-01 | 4/13 Release date 4/23. 4/20 Approved
2001-04-27 | Global Products | US Residual Fuel Oil 1% Crack Spreads | US | Global Products | Sara Mulholland | Robert Cass | Chris Walker | Approved | Approved | 2001-04-01 | 4/20 Release date 4/30
2001-04-27 | Global Products | US Residual Fuel Oil 3% Crack Spreads | US | Global Products | Sara Mulholland | Robert Cass | Chris Walker | Approved | Approved | 2001-04-01 | 4/20 Release date 4/30
2001-04-27 | Global Products | RGC3 Fin Opt Call & Put | US | Global Products | Chad South | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Approved, to be released on 4/23
2001-04-27 | Paper & Pulp | Financial Swaps x 4 | London | Paper & Pulp | Darren Gurner | Amita Gosalia | Angie & Anna | Review | Approved |  | 03/16 Credit issues and Exchange Functionality to be resolved. 4/20 Done
2001-04-27 | Power | French Power Phys | London | Power | Simon Brod | Amita Gosalia | Marie | Legal | Approved |  | 03/16 GTCs and LD being drafted by legal. 4/20 done
2001-04-27 | Global Products | Ethylene Fin Opt Call & Put | US | Global Products | Chad South | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Approved, to be released on 4/24
2001-04-27 | Global Products | LLDPE Fin Opt Call & Put | US | Global Products | Chad South | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Approved, to be released on 4/25
2001-04-27 | Global Products | PPHP Fin Opt Call & Put | US | Global Products | Chad South | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Approved, to be released on 4/26
2001-05-04 | Global Products | US No.2 E. Fin Opt Call & Put | Us | Global Products | Mario DeLaossa | Robert Cass | Kevin Meredith | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Test. 4/20 Product in Test. 4/27 Approved
2001-05-04 | Global Products | US No.2 A. Fin Opt Call & Put | Us | Global Products | Mario DeLaossa | Robert Cass | Kevin Meredith | Approved | Approved | 2001-04-01 | 3/30 Drafting Language. 4/13 Test. 4/20 Product in Test. 4/27 Approved
2001-05-04 | Global Products | Ethane Fin Opt Call & Put | US | Global Products | Lee Jackson | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 4/13 Testing. 4/27 Approved
2001-05-04 | Global Products | Propane Fin Opt Call & Put | US | Global Products | Lee Jackson | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 4/13 Testing. 4/27 Approved
2001-05-04 | Currency | US Foreign Currency Swap | US | FX | William Stuart | Robert Cass | Melba Lozano | Approved | Approved | 2001-04-01 | 3/30 Product in Test. 4/20 Product on Hold. 4/27 to be released May 7th
NON-US TRANSACTION PRODUCTS
Date Changed | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
2000-09-07 | Metals | Metals LME x5 | London | MG |  |  | Lara/Arfan | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II 09/07 Done!
2000-09-22 | Power | German Power Options | London | Power |  | Amita Gosalia | Anna / Imelda | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II . Legal reviewing. 9/22 Done
2000-10-05 | Gasoil | SG East-West Swap Diff. | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie / Anna | Active | Active | 2000-10-01 | 09/08 Reviewing language. 9/22 - awaiting legal approval of PT and CP upload. 10/5 Done
2000-10-05 | Metals | LME x4 | London | MG | Tim Jones | Amita Gosalia | Lara/Arfan | Active | Active | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On Draft. 10/5 Done
2000-10-20 | Coal | Phy Options | London | Coal | Peter Bradley | Amita Gosalia | Imelda/ Lara | Active | Active | 2000-10-01 | 9/14 On Draft 9/22 - Sent to legal for review. 10/5 Awaiting profile from legal, expecting to go live Oct-16th. 10/20 Done
2000-10-20 | Metals | LME Contracts Fin x3 (lead etc) | London | Metals | Tim Jones | Amita Gosalia | Lara/Imelda | Active | Active | 2000-10-02 | 09/08 On Draft. 9/14 Product description sent for approval, PA and ETA prepared for Chile, Peru, China, Russia, Taiwan, South Africa,. 10/5 - Long disc being reviewed by legal. Tentative go live on 16 Oct. 10/20 Done
2000-10-20 | Sea Freight | Sea Freight x4 | London | Crude | Pierre Aury | Amita Gosalia | Marie | Active | Active | 2000-09-01 | 9/14 On Draft. 9/22 - Awaiting CP Profile upload. 10/5 Awaiting launch. 10/20 Done
2000-10-20 | Tanker Freight | Tanker Freight | London | Crude | Scott Moncrieff | Amita Gosalia | Caroline/ Anna | Active | Active | 2000-10-01 | 09/08 On hold due to Phase II. Legal reviewing. 9/22 Approved by legal. 10/5 Tentative launch on 10th. 10/20 Done
2000-11-03 | Crude | Nordic Product Split | London | Crude | Waiting on Info | Amita Gosalia | Arfan/ Caroline/Diana | Active | Active | 2000-10-01 | 9/14 On Draft. 9/22 Marc D to Commence 10/5 Arfan to Commence. 10/20 GTCs to be agreed with Thor, Martin and Paul. 11/03 Done
2000-11-03 | Petchems x 8 | Petchems | London | Petchems | Stuart Bland | Amita Gosalia | Caroline / Diana | Active | Active | 2000-10-01 | 9/14 On Draft. 10/5 On Hold. 10/20 To go live on Oct 23rd. 11/03 Done
2000-11-03 | Propane | Propane - new locations x 2 | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie | Active | Active | TBD | 11/3 Done
2000-12-01 | Coal | Seafreight Average Time Charter | London | Coal | Pierre Aury | Amita Gosalia | Anna | Completed | Completed |  | 11/17 Expected to go live Dec 4th. 12/01 Completed
2000-12-01 | Coal | Seafreight Average Time Charter - amend existing product | London | Coal | Pierre Aury | Amita Gosalia | Marie | Completed | Completed |  | 11/17 Awaiting new Sigma factor. 12/01 Completed
2000-12-01 | Dutch Gas | Dutch Gas NLG/M3 | London | Gas | Carsten Sterz | Amita Gosalia | Arfan | Completed | Completed | 2000-10-01 | 9/14 On Draft. 9/22 Available to launch 10/20 Mark D to contact Dave F, 11/03 Awaiting response from Dave F. 11/17 Go live Nov 20th 11/24 Go live postponed as traders wish to show prices to 2 decimal places - not poss due to conversion using FX Mgr. 12/01 Completed
2000-12-01 | Power | UK Power - LOLP | London | Power | Neil Jackson | Amita Gosalia | Arfan/Philippa/Alan | Completed | Completed |  | 11/10 Long description received from trader. 12/01 Completed
2000-12-08 | Metals | Copper x 8 Phys - Europe | London | Metals | David Lilley | Amita Gosalia | Marie | Test | Completed | 2000-10-01 | 09/08 On Draft. 9/14 Product description sent for approval, PA and ETA prepared for Chile, Peru, China, Russia, Taiwan, South Africa,. 10/5 Working on long description with traders and legal. Tentative to go live on Oct 19th. 10/20 Awaiting approval from David Lilley. 11/03 Meeting with Trader on 13th Nov. 11/24 Product to launch on Dec 4th 12/01 Launch postponed to Dec 11th.
2001-01-19 | Natural Gas | UK Gas Phys Option x2 | London | UK Gas | Dave Redmond | Amita Gosalia | Arfan | Completed | Completed |  | 01/19 Completed
2001-01-19 | Singapore Crude | HSFO 180-380 Spread | Singapore | Crude | Hans Wong | Amita Gosalia | Marie | Completed | Completed | TBD | 01/05 Long description sent to legal. 01/19 completed
2001-01-19 | Weather | Weather - Average Swaps | London | Weather | Thor Lien | Amita Gosalia | Arfan/Marie | Completed | Completed | TBD | 10/5 Request received from trader. 10/20 Meeting with trader on Oct 24th. 11/03 Awaiting info from Trader 11/10 Waiting on GTC from Legal. 12/01 GTC finalized. Legal reviewing long description. 01/05 Awaiting sigma factor. Product ready to launch. 01/19 Completed
2001-01-19 | Continental Gas | Cont Basis Swap IPE Index minus Zeebrugge | London | Gas | Dider Magne | Amita Gosalia | Arfan/Phillipa/Alan | Completed | Completed | TBD | 12/01 Long description with Trader for approval. 01/05 Products ready to launch, awaiting sigma factors from RAC. 01/19 Completed
2001-01-19 | Continental Gas | Zeebrugge Index Phy x 1 Fin x 1 | London | Gas | Dider Magne | Amita Gosalia | Arfan/Phillipa/Alan | Completed | Completed | TBD | 12/01 Long description with Trader for approval. 01/05 Products ready to launch, awaiting sigma factors from RAC. 01/19 Completed
2001-01-19 | FX | Internal FX Product | London | FX desk | Shane Dallman | Amita Gosalia | Anna/ Imedla | Completed | Completed | TBD | 10/5 Request received from trader. 10/20 Houston PCG. 01/19 Completed
2001-02-09 | Weather Options | Weather Options | London | Weather | Thor Lien | Amita Gosalia | Arfan/ Marie | Approved | Approved | TBD | 9/14 GTC in legal. 9/22 Trader Reviewing 10/5 Legal to provide GTC and Long Descriptions. 10/20 Meeting with Trader on 24 Oct. 11/03 Awaiting info from Trader 11/10 Awaiting GTCs from legal. 12/01 GTC finalized. Legal reviewing long descriptions. 01/05 Awaiting sigma factor. Product ready to launch. 01/19 Long description to be reworked. 02/09 Completed
2001-02-16 | Credit Derivatives | Credit Default Swap, Bankruptcy Swap | London | Credit Derivs | Bryan Seyfreid | Amita Gosalia | Alan (Lara) | Reviewing | Approved |  | 02/09 GTCs and LDs being defined. Awaiting Sigma factors, credit approvals etc. 02/16 Done
2001-03-02 | Spreads | Metals | London |  | Tim Jones | Amita Gosalia | Arfan | Approved | Approved |  | 02/09 Functionality to be learned. 3/02 Launched 3/05/01
2001-03-02 | Broadband | Broadband Phys x 6 | London | Broadband | Marcello Romano | Amita Gosalia | Marie | Done | Done | TBD | 01/19 Legal due diligence commenced. GTCs and LDs being drafted. 3/02 Completed
2001-03-02 | Options | Int Seafreight | London |  | Andy James | Amita Gosalia | Caroline | Approved | Approved |  | 02/09 GTCs/LDs to be reviewed. 3/02 Launch scheduled for 03/12/01
2001-03-16 | Oil | HSFO Swap | London | Global Products | Caroline Cronin | Amita Gosalia | Lara | Completed | Completed |  | 03/16 Completed
2001-03-16 | Power | UK Phy Power | London | Power | Simon Hastings | Amita Gosalia | Arfan/ Caroline | Completed | Completed | TBD | 9/14 On Draft. 9/22 On Hold until Q1 2001. 3/02 Meeting with legal and trader this week. 3/16 Completed
2001-03-16 | Power | German Power Time Spread | London | Power | Adrian Mancebo | Amita Gosalia | Philippa | Completed | Completed |  | 03/16 Completed
2001-03-23 | Natural Gas | German Gas Phys | London | Natural Gas | Jacob Meins | Amita Gosalia | Marie | Legal | Completed |  | 03/16 GTCs and LD being drafted by legal 03/23 Completed - Launch on 26th March
2001-04-27 | Natural Gas | EnPipe Auction - Capacity | London | Natural Gas | Steve Vavrik | Amita Gosalia | Anna | Approved | Approved |  | 03/23 Informed Houston management and tech team re 2nd EnPipe Auction. 4/20 Done
2001-04-27 | Natural Gas | UK Gas Fin Options | London | Natural Gas | Dave Redmond | Amita Gosalia | Philippa | Approved | Approved |  | 04/20 Ready to launch
2001-04-27 | Oil | Brent/Dubai Swap | London | Global Products | John Thomas | Amita Gosalia | Arfan | Approved | Approved |  | 03/16 Amending existing LD. 4/20 Done
2001-04-27 | Oil | HSFO/Brent Crack Spread | London | Global Products | Caroline Cronin | Amita Gosalia | Philippa | Approved | Approved |  | 03/16 Product development to commence w/c 03/19 4/20 Done
2001-05-04 | Oil | Singapore/Dubai time spread | Singapore | Oil | Pat Markey | Amita Gosalia | Caroline | Approved | Approved | 2001-05-08 | 11/17 Draft long description. 12/08 Trader to amend long description. 01/05 Long description being drafted by legal. Conf call with trader next week. 3/02 Long Description being amended 04/20 Telcon with Trader and Marketer. Agreement to proceed quickly. 4/27 Approved. 5/11 Changed LD for qtrly product- to be launched May 14.
2001-05-25 | Metals | Nickel Spread | London | Metals | Adam Turner | Amita Gosalia | Zoe/Kristina | Approved | Approved | 2001-05-14 | 05/11 Ready to Launch. Launch to be delayed to coincide with Phys Nickel launch. 5/18 Launched, waiting for trader to post product.
2001-05-25 | Metals | Zinc Spread | London | Metals | Adam Turner | Amita Gosalia | Zoe/Kristina | Approved | Approved | 2001-05-14 | 05/11 Ready to Launch. Launch to be delayed to coincide with Phys Nickel launch. 5/18 Launched, waiting for trader to post product.
2001-05-25 | Oil | Mogas Crack Spread Fin | London | Oil | John Spencer | Amita Gosalia | Philippa | Approved | Approved | 2001-05-21 | 05/11 LD and GTC ready - trader to approve. 5/18 Approved, ready for launch on 5/21
2001-05-25 | Options | German Power | London |  | Ulf Ek | Amita Gosalia | Marie | Approved | Approved |  | 02/09 Awaiting system upgrade to deal with Phys options. 3/02 Long description with trader for approval. 4/27 Awaiting info from trader. 5/18 trader wants to launch on 5/29
2001-05-25 | Steel | Steel | London | Steel | Cheryl Ingstad | Amita Gosalia | Arfan | Approved | Approved | 2001-05-21 | 04/20 Long descriptions and GTCs being reviewed. 4/27 Awaiting outcome of due diligence and approval from index provider for consent to use index. 05/11 LD agreed by trader and legal. GTC awaiting tax amendment. Awaiting profiles from Credit. Launch expected 21st May. 5/18 Apoproved, ready for launch on 5/21
2001-05-04 | Oil | East/West Fueloil Spread | Singapore | Oil | Pat Markey | Amita Gosalia | Kristina/Zoe | Approved | Approved | 2001-05-08 | 4/27 To be launched on May 7th
2001-05-11 | Credit Inst | Credit Default Swaps in Euro | London | Credit Inst | Bryan Seyfreid | Amita Gosalia | Kristina/Zoe | Approved | Approved | 2001-05-08 | 4/27 Awaiting response from RAC on FX exposure management. 5/11 Ready to launch
2001-05-11 | German Power | Fin swap 2 x new indices | London | Power | Ulf Ek | Amita Gosalia | Anna | Cancelled | Approved | TBD | 01/05 Ready to launch. Ulf to obtain approval. 5/18 Product in system, however trader has not used the product as yet

## Cancelled Requests
|  | CANCELLED PRODUCT REQUESTS |  |  |  | as of: | 2001-05-25
TRANSACTION PRODUCTS
Date Changed | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
2000-09-14 | Isobutane | Phy Index | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | N/A | 08/31 Working on initial draft. 09/06 Draft in progress. 9/14 Cancelled
2000-09-22 | Nat-Gasoline | Phy Index | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | TBD | 08/31 Working on initial draft. 9/22 Cancelled
2000-09-22 | Propane | Phy Index Purity | US | Petchems |  | Dale Neuner | Dale Neuner | Cancelled | Cancelled | TBD | 08/31 Working on initial draft. 09/06 Draft in progress. 9/22 Cancelled
2000-12-08 | Advertising Blocks (Nielsen Ratings) | Advertisement Market | US | EBS | Stephen Barth | Leonardo Pacheco | Dale Neuner | Cancelled | Cancelled | TBD | 08/23 EBS is reviewing legal issues. 09/07 Met with S. Barth (EBS) to discuss. They will work on defining the products and then get back to us. 12/08 Cancelled-no action from requestor
2000-12-08 | Gas | Fin Options | US | Gas | Pete Keavey | Dale Neuner | Dale Neuner | Cancelled | Cancelled | TBD | 08/23 On hold due to Phase. II 9/22 Savita and Dale finalizing language for delivery to Legal. 10/20 Product description under review by David Forster 11/03 Product is being developed in Test, circulated for comments from legal et al. 12/08 Trader advised that product is no longer required
2000-12-08 | Paper | Phy Paper OCC Ex-works | US | Pulp and Paper | Jeff Harbert | Robert Cass | Robert Cass | Reviewing | Reviewing | TBD | 08/23 Desk is working on logistics and legal issues. 9/28 16 created products for ClickPaper.com, awaiting set-up on EOL pending Commercial and Technical issues. 12/08 Cancelled because it is a click paper product
2001-01-12 | Sea Freight | Sea Freight Physical | London | Oil | Pierre Aury | Amita Gosalia | Anna/Imelda | Cancelled | Cancelled | TBD | 9/14 On Draft. 9/22 Investigating auctions functionality for this product. 10/20 Meeting with trader on Nov 1. 11/03 Meeting with Trader on Nov 8th. 11/10 Trader and legal to agree to contract terms. 01/19 Trader wants to use Levelseas platform for this.
2001-03-09 | Gas | Fin Spread | US | Gas | Pete Keavey | Robert Cass | Melba Lozano | Cancelled | Cancelled | 2000-01-01 | 08/23 Product for internal use only to hedge between Nymex and HeHub. 9/14 products will bridge similar to other basis products. 9/22 Forster provided suggested language, Neuner will modify and send to Peter. 12/22 Product description under review by trader and legal. 03/02 Cancelled- no action from trader.
2001-03-09 | Power | Hourly Power | Us | Power | Rudy Acevedo | Robert Cass | Melba Lozano | Cancelled | Cancelled | 2000-01-01 | 9/22 Dale is trying to tie the Loadshape to the Date/Time Stamp in the Transaction Results screen, then language will go to Legal. 10/20 Product is in test. 12/08 Cancelled- Power needs to reissue request to build product. 12/15 Commercial has resumed interest in moving forward with this product type after Jan 1, 2001. 12/22 commercial has resumed interest in moving forward with this product type after Jan 1, 2000. 01/19 Legal has approved load shapes. Currently in test. 3/09 Cancelled- no action from trader
2001-03-16 | Belgian Gas | Belgian Gas - Eynattem | London | Gas | Dider Magne | Amita Gosalia | Arfan | Draft | Cancelled | 2000-10-02 | 9/14 On hold. 12/01 In discussions with Trader. Trader to create GTC's with legal. 3/16 Cancelled
2001-03-16 | Continental Gas | Cont Gas CSS Swap | London | Gas | Dider Magne | Amita Gosalia | Arfan/Phillipa/Alan | Draft | Cancelled | TBD | 12/01 Long description with Trader for approval. 01/05 On Hold - awaiting info from traders. 3/16 Cancelled
2001-05-11 | German Power | Fin swap 2 x new indices | London | Power | Ulf Ek | Amita Gosalia | Anna | Cancelled | Approved | TBD | 01/05 Ready to launch. Ulf to obtain approval.
2001-05-11 | Metals | Copper x 4 phys - Asia | London | Metals | David Lilley | Amita Gosalia | Arfan | Cancelled | Cancelled | TBD | 12/08 Awaiting information from trader. 01/05 Sing product ready - tentative launch 15th Jan. Remainder to be completed. 01/19 On Hold while while tax research is completed. 02/09 Shanhai and Singapore completed, Keelung and Korea outstanding. 04/20 Awaiting further trader instructions. 4/27 Cancelled
2001-05-11 | Continental Gas | Cont Gas CSS Swap | London | Gas | Dider Magne | Amita Gosalia | Arfan/Phillipa/Alan | Cancelled | Cancelled | TBD | 12/01 Long description with Trader for approval. 01/05 On Hold - awaiting info from traders. 3/16 Cancelled
2001-05-11 | Belgian Gas | Belgian Gas - Eynattem | London | Gas | Dider Magne | Amita Gosalia | Arfan | Cancelled | Cancelled | 2000-10-02 | 9/14 On hold. 12/01 In discussions with Trader. Trader to create GTC's with legal. 3/16 Cancelled
2001-03-09 | Broadband | Bandwidth Co-location space | London | Broadband | Nick Brewer | Amita Gosalia | Imelda | Cancelled | Cancelled |  | 11/10 Awaiting commercial sponsor and information. 3/02 Cancelled
2001-03-09 | Crude | Brent/Dubai Spread | London | Crudes | John Crismar | Amita Gosalia | Marie | Cancelled | Cancelled | 2000-10-01 | 08/23 On hold. 9/22 Long Description received from Singapore 10/5 Approved, should be Active on 9th 10/20 Awaiting approval from Chrismar. 3/02 Cancelled- no commercial interest
2001-03-09 | Fuel Oil | SG East-West Fuel Oil Swap Diff. | London | Global Liquids | Chris Mahoney | Amita Gosalia | Marie / Anna | Cancelled | Cancelled | 2000-10-01 | 09/08 Reviewing language. 9/22 On Hold. 3/02 Cancelled- no commercial interest
2001-03-09 | Gasoil | Daily Average x2 | London | Global Liquids | Chris Mahoney | Amita Gosalia | Arfan / Anna | Cancelled | Cancelled | TBD | 09/08 Reviewing language. 9/22 On Hold. 3/02 Cancelled- no commercial interest
2001-03-09 | Marine Bunkers | Marine Bunkers | London | Oil | Scott Moncrieff | Amita Gosalia | Caroline/ Anna | Cancelled | Cancelled | 2000-09-01 | 08/23 On hold due to Phase II 09/07 On hold. 09/22 On hold - Scott Moncrieff wants to launch tanker freight before proceeding with this. 3/02 Cancelled- no commercial interest.
2001-03-09 | Metals | Copper Arb | London | Metals | Craig Young | Amita Gosalia | Caroline | Cancelled | Cancelled |  | 11/10 Awaiting commercial sponsor and information. 3/02 Cancelled- no commercial interest.
2001-03-09 | Oil | HSFO Swap | London | Oil | Stewart Peter | Amita Gosalia | Arfan/Phillipa/Alan | Cancelled | Cancelled | TBD | 12/01 Long description with Trader for approval. 3/02 Cancelled- no commercial interest.
2001-03-09 | Singapore FX | Singapore FX | London | FX desk | Pat Markey | Amita Gosalia | Anna | Cancelled | Cancelled | TBD | 08/23 On hold by request of commercial group 9/22 No further Update. 3/02 Cancelled- no commercial interest.
2001-03-09 | Warehouse Space | Warehouse Space | London | Metals | Ed Dablin | Amita Gosalia | Marie/Arfan | Cancelled | Cancelled | TBD | 11/3 Awaiting info from commercial group. 3/02 Cancelled- no commercial interest
Cancelled
AUCTION PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | Status as of 05/18/00 | Status as of 05/25/01 | Scheduled for | Comments
2001-01-26 | Coal | Coal Auction | US | Coal | John Massey | Leonardo Pacheco | John Massey | Cancelled | Cancelled | TBD | 8/21 Coal group working on text draft
2001-01-26 | Gas | Transportation Cap. | US | FGT | Steve Hotte | Leonardo Pacheco | Steve Hotte | Cancelled | Cancelled | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
2001-01-26 | Gas | Transportation Cap. | US | NGPL | Steve Hotte | Leonardo Pacheco | Steve Hotte | Cancelled | Cancelled | 2000-09-01 | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
2001-01-26 | Power | Capacity Generation | US | Power Desk | Ed Baughman | Leonardo Pacheco | David Portz | Cancelled | Cancelled | TBD | 8/16 Making changes to text draft. The launch will be post Phase II 09/07 On hold for Phase II. 10/05 Auction being reviewed
BUSINESS DEVELOPMENT PRODUCTS
# | Commodity | Product | Country/Location | Business Unit | Business Unit Contact | Process Manager | Responsibility | 2000-12-08 | 2000-12-17 | Scheduled for | Comments
| Gas |  | US | EPG | Steve Hotte | Savita Puthigai | Legal and Commercial | Cancelled | Cancelled | 2000-10-01 | 08/23 Working on descriptions and GTC. 8/31 Product Descriptions and Legal being reviewed. "Chinese Wall" type concerns being reviewed by Legal. 9/07 Reviewing issues related to GPG and ENA information (comply with regulation) 9/14 need to segregate marketing affiliates using Chinese Walls- Preparing list of Proprietary system issues; may include HPL products. 9/22 Meeting held with PCH Managers-Torrey to follow up with Scott Mills-Sitara issues, Torrey will write questions to IT regarding segregation of mktg affiliates. 12/22 Product not viable at this time.
| Power | FIN Swap | Us | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Cancelled | Cancelled | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 11/17 Reviewing regulatory issues.
| Power | PHY Fwd | Us | Enron Argentina | Patrick Hansen | Carlos Alatorre | Dale Neuner | Cancelled | Cancelled | 2000-09-01 | 08/16 Two products are on test. Argentina is a post Phase II Launch. 8/31 GTC reviewed and sent to Legal. 09/06 Pending until after Version 2.0 Launch. 9/14 PA and ETA received from ARG, legal description approved by Houston legal and forwarded to ARG Legal, set for testing during ARG visit. 11/17 Reviewing regulatory issues.