## Distribution
DISTRIBUTION LIST - BI-WEEKLY FRIDAYS
as of | 2000-09-08
NORTH AMERICA |  |  | ALL REGIONS/BUSINESS UNITS
Pierce, Jody |  | ENA Accounting | RAC | Other | 3AC1427
Shepperd, Tammy |  | ENA Origination | Bayley, Rob |  | 3AC1404
|  |  | Buy, Rick |  | 3AC1909
|  |  | Carson, Rick |  | 3AC2041
INTERNATIONAL REGIONS |  |  | Chappell, John |  | 3AC2071
|  |  | Lewis, Richard |  | 3AC3787
Schneider, Chip
Young, Steve
EE&CC
Barto, Brian
Garrison, John
Kelly, Fred
Rigby, John
Tezyk, Matthew
Westfahl, Dick

## Detail by Turbine
Turbine Position Report
Detail by Turbine
2000-09-08
Line | Status |  | Vendor | Contract / PO # | Serial # | Model | Output @ ISO | Heat Rate (HHV) | New/Used | Delivery Date | Owner | DASH Approval Date | Notice to Proceed Given | Status of Financing | Controlled By | Originator / Developer | Project Manager | Project Name | Contract Cost | $ Paid to Date | Other Costs | 7/31/00 Carrying Value per Books | OPEN Carrying Cost @ 8% | OPEN Cancel-lation Payment | Comments
1 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
2 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
3 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
4 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
5 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
6 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
7 | Committed | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 |  |  |  |  | Nigerian barge not yet converted to 50hz
8 | Committed | 1 | GE |  |  | Fr 6B 50hz power barges | 31 | 10151 | Used | NTP + 180 to Nigeria | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 7 | 7 |  | 4.75
9 | Committed | 1 | GE |  |  | Fr 6B 50hz power barges | 31 | 10151 | Used | NTP + 180 to Nigeria | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 7 | 7 |  | 4.75
10 | Committed | 1 | GE | NJ-2-99 |  | 7FA - now simple cycle | 156 | 10456 | New | 2000-08-01 | East Coast Power | 2000-01-10 |  | N/A | East Coast Power |  |  | East Coast Power - Linden 6 (ECP) | 35 | 20 |  |  |  |  | DASH name ENA Turbine Divestiture to ECP
11 | Committed | 1 | GE | 24-LM6K-2-99 | 309266 | LM6000 | 44 | 9030 | New | 2000-08-01 | West LB |  |  | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | City of Austin (ENA) | 14 | 6
12 | Committed | 1 | GE | 24-LM6K-2-99 | 309547 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB |  |  | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | City of Austin (ENA) | 14 | 6
13 | Committed | 1 | GE | 24-LM6K-2-99 | 309575 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB |  |  | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | City of Austin (ENA) | 14 | 6
14 | Committed | 1 | GE | 24-LM6K-2-99 | 309578 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB |  |  | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | City of Austin (ENA) | 14 | 6
15 | Committed | 1 | GE | 24-LM6K-2-99 | 308898 | LM6000 | 44 | 9030 | New | 2000-06-20 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
16 | Committed | 1 | GE | 24-LM6K-2-99 | 308951 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
17 | Committed | 1 | GE | 24-LM6K-2-99 | 308972 | LM6000 | 44 | 9030 | New | 2000-08-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
18 | Committed | 1 | GE | 24-LM6K-2-99 | 308999 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
19 | Committed | 1 | GE | 24-LM6K-2-99 | 309020 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
20 | Committed | 1 | GE | 24-LM6K-2-99 | 309073 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
21 | Committed | 1 | GE | 24-LM6K-2-99 | NSN | LM6000 | 44 | 9030 | New | 2000-01-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
22 | Committed | 1 | GE | 24-LM6K-2-99 | NSN | LM6000 | 44 | 9030 | New | 2000-01-01 | West LB |  |  | N/A | ESA | Brett Wiggs | Jeff Westfahl | Elektrobolt (ESA) | 14 | 6
23 | Tentative | 2 | GE |  |  | Fr 6B 60 hz power barges | 31 | 10151 | Used | Delivered | ENE B/S |  |  | N/A | CALME | Apolonio Baca |  | LIPA (ENA) | 36 | [5 empty] | submitted PPA to NY controller
24 | Tentative | 2 | GE |  |  | Fr 6B 60 hz power barges | 31 | 10151 | Used | Delivered | ENE B/S |  |  | N/A | CALME | Apolonio Baca |  | LIPA (ENA) | 36 | [5 empty] | submitted PPA to NY controller
25 | Tentative | 3 | GE | 297 760 turbine 337x815 gen |  | 7FA - now simple cycle | 171 | 10456 | New | 2001-09-01 | ENE B/S | N |  | N/A | EECC | Dick Westfahl |  | NEPCO / NESCO - Goldendale (EECC) | 54 | 4 |  |  |  |  | DASH circulating
26 | Tentative | 3 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-09-01 | West LB | 2000-08-01 |  | N/A | EECC | Brian Barto |  | Gen Power - Dell, Arkansas location; duct fired (EECC) | 47.5 | 16 |  |  |  |  | EE&CC to accept limited NTP by September 2000
27 | Tentative | 3 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-10-01 | West LB | 2000-08-01 |  | N/A | EECC | Brian Barto |  | Gen Power - Dell, Arkansas location; duct fired (EECC) | 47.5 | 16 |  |  |  |  | EE&CC to accept limited NTP by September 2000
28 | Tentative | 3 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-07-01 | West LB | 2000-08-01 |  | N/A | EECC | Brian Barto |  | Gen Power - McAdams, Mississippi location; duct fired (EECC) | 47.5 | 16 |  |  |  |  | 2000-10-31
29 | Tentative | 3 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-08-01 | West LB | 2000-08-01 |  | N/A | EECC | Brian Barto |  | Gen Power - McAdams, Mississippi location; duct fired (EECC) | 47.5 | 16 |  |  |  |  | 2000-10-31
30 | Tentative | 2 |  |  |  | 9FA STAG Power Islands | 1125 | 10456 | New | 2001-10-01 | ENE B/S |  |  | N/A | EECC | Brian Barto | Stephen Heck | Spain Arcos (EEL) | 83 | 7.7
31 | Tentative | 2 |  |  |  | 9FA STAG Power Islands | 1125 | 10456 | New | 2001-11-01 | ENE B/S |  |  | N/A | EECC | Brian Barto | Stephen Heck | Spain Arcos (EEL) | 83 | 7.7
32 | Tentative | 2 |  |  |  | 9FA STAG Power Islands | 1125 | 10456 | New | 2001-12-01 | ENE B/S |  |  | N/A | EECC | Brian Barto | Stephen Heck | Spain Arcos (EEL) | 83 | 7.7
33 | Tentative | 2 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | West LB | partial 7/17/00 |  | N/A | ENA | David Parquet |  | Pastoria (ENA) | 66 | [5 empty] | First payment due in November 2000
34 | Tentative | 2 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | West LB | partial 7/17/00 |  | N/A | ENA | David Parquet |  | Pastoria (ENA) | 66 | [5 empty] | First payment due in November 2000
35 | Tentative | 2 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | West LB | partial 7/17/00 |  | N/A | ENA | David Parquet |  | Pastoria (ENA) | 66 | [5 empty] | First payment due in November 2000
36 | Tentative | 2 | GE | 24-LM6K-2-99 | 309420 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB |  |  | OPEN | ENA | Thomas |  | Fountain Valley PSCO (ENA) | 14 | 6
37 | Tentative | 2 | GE | 24-LM6K-2-99 | 309505 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB |  |  | OPEN | ENA | Thomas |  | Fountain Valley PSCO (ENA) | 14 | 6
38 | Tentative | 2 | GE | 24-LM6K-2-99 | 309573 | LM6000 | 44 | 9030 | New | 2000-10-01 | West LB |  |  | OPEN | ENA | Thomas |  | Fountain Valley PSCO (ENA) | 14 | 6
39 | Tentative | 2 | GE | 24-LM6K-2-99 | 309601 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB |  |  | OPEN | ENA | Thomas |  | Fountain Valley PSCO (ENA) | 14 | 6
40 | Tentative | 3 | GE | 24-LM6K-2-90 | 309721 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB | partial 7/24/00 |  | N/A | ENA | Maurice Gilbert |  | Las Vegas CoGen II (ENA) | 14 | 6
41 | Tentative | 3 | GE | 24-LM6K-2-90 | 309741 | LM6000 | 44 | 9030 | New | 2000-12-01 | West LB | partial 7/24/00 |  | N/A | ENA | Maurice Gilbert |  | Las Vegas CoGen II (ENA) | 14 | 6
42 | Tentative | 3 | GE | 24-LM6K-2-90 | NSN | LM6000 | 44 | 9030 | New | 2000-01-01 | West LB | partial 7/24/00 |  | N/A | ENA | Maurice Gilbert |  | Las Vegas CoGen II (ENA) | 14 | 6
43 | Tentative | 3 | GE | 24-LM6K-2-90 | NSN | LM6000 | 44 | 9030 | New | 2000-03-01 | West LB | partial 7/24/00 |  | N/A | ENA | Maurice Gilbert |  | Las Vegas CoGen II (ENA) | 14 | 6
44 | Tentative | 2 | GE | VITRO-2-99 |  | 7FA | 171 | 10456 | New | 2000-10-01 | ENE B/S |  |  | Term Sheet | ENA | Max Yazguirre |  | Vitro (ENA) | 31 | 25
45 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Delivered | West LB |  |  | N/A | Canada |  |  | Unassigned | 13 | [5 empty] | trying to sell as part of Moore Project
46 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Delivered | West LB |  |  | N/A | Canada |  |  | Unassigned | 13 | [5 empty] | trying to sell as part of Moore Project
47 | Available | 2 | Westing- house | Y2K(6)-2-98 |  | 501D5A Simple Cycle | 122 | 10856 | New | being cleaned | ENE B/S |  |  | N/A | CALME |  |  | Sadaf bid (CALME) or 2001 Peaker Plants (ENA) or Jordan in N Carolina | 24 | 23 |  |  |  |  | CALME purchased turbine from ENA; turbine has not yet cleared customs; generator incurred salt water damage while unloading
48 | Available | 2 | Westing- house |  |  | 501D5A Simple Cycle | 122 | 10800 | New | 2001-11-01 | LJM | Y (Blue Girl Addendum) |  | N/A | EECC |  |  | Sadaf bid (CALME) or 3rd party (EECC) | 24 | 1.2 |  |  |  |  | DASH Addendum currently being recirculated for approval as over 90 days; already approved by BOD; option payment of $1.2MM has been made, but no cancellation due if we give up
49 | Available | 3 | GE | BD-2-00 |  | 7EA | 166 | 11900 | New | 2001-03-01 | LJM | Blue Dog |  | N/A | EECC |  |  | Unassigned | 18 | 3.5 |  |  |  |  | EE&CC purchased these turbines spec; Delainey accepts responsibility for removing from LJM
50 | Available | 3 | GE | BD-2-00 |  | 7EA | 166 | 11900 | New | 2002-02-01 | LJM | Blue Dog |  | N/A | EECC |  |  | Unassigned | 18 | 3.5 |  |  |  |  | EE&CC purchased these turbines spec; Delainey accepts responsibility for removing from LJM
51 | Available | 3 | GE | 24-LM6K-2-99 | 309101 | LM6000 | 44 | 9030 | New | 2000-06-01 | West LB |  |  | N/A | ENA |  |  | Jordan (ENA) in N Carolina | 14 | 6
52 | Available | 3 | GE | 24-LM6K-2-99 | 309123 | LM6000 | 44 | 9030 | New | 2000-06-01 | West LB |  |  | N/A | ENA |  |  | Jordan (ENA) in N Carolina | 14 | 6
53 | Available | 3 | GE | 24-LM6K-2-99 | 309604 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB |  |  | N/A | ENA |  |  | Tri-Valley in Pleasanton, CA (ENA) | 14 | 6
54 | Available | 3 | GE | 24-LM6K-2-99 | 309719 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB |  |  | N/A | ENA |  |  | LODI in California (ENA) | 14 | 6
55 | Available | 3 | Korean |  |  | Steam Turbine | 110 | N/A | Used | Delivered | ENE B/S |  |  | N/A | ENA | Robert Virgo |  | Unassigned | 2.3 | 2.3 |  | 0 |  |  | package with Korean used GE7B's / currently under sale negotiations - written off to zero on G/L
56 | Available | 3 | Mitsubishi |  |  | 501F Simple Cycle | 184 | 10256 | New | 2001-10-01 | West LB | 2000-08-14 |  | N/A | ESA |  | Jeff Westfahl | Rio Gen (ESA) | 37.5 | 6
57 | Available | 3 | Mitsubishi |  |  | 501F Simple Cycle | 184 | 10256 | New | 2002-06-01 | West LB | 2000-08-14 |  | N/A | ESA |  | Jeff Westfahl | Rio Gen (ESA) | 37.5 | 6
58 | Available | 3 | Mitsubishi |  |  | 501F Simple Cycle | 184 | 10256 | New | 2001-07-01 | West LB | 2000-08-14 |  | N/A | ESA |  | Jeff Westfahl | Cuiba II (ESA)
59 | Available | 3 | Mitsubishi |  |  | 501F Simple Cycle | 184 | 10256 | New | 2001-08-01 | West LB | 2000-08-14 |  | N/A | ESA |  | Jeff Westfahl | Cuiba II (ESA)
60 | Negotiating | 4 | Mitsubishi |  |  | 501F MHI Simple Cycle | 185 | 10245 | New | 2002-11-30 | West LB |  |  | N/A | ESA |  |  | Unassigned | 37 | 0 |  |  |  |  | options not yet exercised; call period expires 10/19/00
61 | Negotiating | 4 | Mitsubishi |  |  | 501F MHI Simple Cycle | 185 | 10245 | New | 2002-12-31 | West LB |  |  | N/A | ESA |  |  | Unassigned | 37 | 0 |  |  |  |  | options not yet exercised; call period expires 10/19/00
62 | Negotiating | 4 | GE |  |  | GE9F 50 hz gas turbine power islands | 123 | 10100 | New |  |  |  |  | N/A |  | Dick Westfahl | Mike Obert | Project Gemini (EECC)
63 | Negotiating | 4 | GE |  |  | GE9F 50 hz gas turbine power islands | 123 | 10100 | New |  |  |  |  | N/A |  | Dick Westfahl | Mike Obert | Project Gemini (EECC)
64 | Negotiating | 4 | GE |  |  | GE9F 50 hz gas turbine power islands | 123 | 10100 | New |  |  |  |  | N/A |  | Dick Westfahl | Mike Obert | Project Gemini (EECC)
65 | Negotiating | 4 | GE |  |  | 7FA | 171 | 10456 | New |  |  | partial 7/17/00 |  | N/A |  |  |  | Pastoria (ENA) | [6 empty] | payment due November 2001
66 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
67 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
68 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
69 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
70 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
71 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
72 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
73 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
74 | Negotiating |  | GE |  |  | 7EA | 166 | 11900 | New | Q3/Q4 2003 | [7 empty] | Trinidad and Tobago Aluminum Smelter Project | 19.6 | [5 empty] | expires 9/30/00
Note on M5: Stephanie K McGinnis: use last signature date per DASH
Note on N5: Stephanie K McGinnis: When EPC contract is officially turned on
Note on G14: Stephanie K McGinnis: left outside and water got into gauges
Note on G15: Stephanie K McGinnis: left outside and water got into gauges
Note on G16: Stephanie K McGinnis: Cogen Tech machine
Note on G50: Stephanie K McGinnis: CoGen Tech machine; ABB STG not ordered yet
Note on G53: Stephanie K McGinnis: barge tilted while unloading

## Summary by Status
Turbine Position Report
Summary by Status
2000-09-08
PRELIMINARY
UNITS | MODEL | CONTROLLED BY | PROJECT(S) | CONTRACT COST | PYMTS TO DATE | CANCEL- LATION | STATUS
COMMITTED
7 | Fr 6B 60hz power barges | APACHI | Nigeria Barge II (APACHI) | 56 | 56 | 0 | Committed
2 | Fr 6B 50hz power barges | APACHI | Nigeria Barge II (APACHI) | 14 | 14 | 0 | Committed
1 | 7FA - now simple cycle | ECP | East Coast Power - Linden 6 (ECP) | 35 | 20 | 0 | Committed
4 | LM6000 | ENA | City of Austin (ENA) | 56 | 24 | 0 | Committed
8 | LM6000 | ESA | Elektrobolt (ESA) | 112 | 48 | 0 | Committed
22 |  |  | Total Committed | 273 | 162 | 0
TENTATIVE
2 | Fr 6B 60hz power barges | CALME | LIPA (ENA) | 72 | 0 | 0 | Tentative
1 | 7FA - now simple cycle | EECC | NEPCO/NESCO Goldendale (EECC) | 54 | 4 | 0 | Tentative
2 | 7FA w/ STG | EECC | Gen Power - Dell (EECC) | 95 | 32 | 0 | Tentative
2 | 7FA w/ STG | EECC | Gen Power - McAdams (EECC) | 95 | 32 | 0 | Tentative
3 | 9FA STAG power islands | EECC | Spain Arcos (EEL) | 249 | 23.1 | 0 | Tentative
3 | 7FA | ENA | Pastoria (ENA) | 198 | 0 | 0 | Tentative
4 | LM6000 | ENA | Fountain Valley PSCO (ENA) | 56 | 24 | 0 | Tentative
4 | LM6000 | ENA | Las Vegas Cogen II (ENA) | 56 | 24 | 0 | Tentative
1 | 7FA | ENA | Vitro (ENA) | 31 | 25 | 0 | Tentative
22 |  |  | Total Tentative | 906 | 164.1 | 0
AVAILABLE
2 | 11N1 | Canada | Unassigned | 26 | 0 | 0 | Available
1 | 501D5A simple cycle | CALME | Sadaf bid (CALME) or 2001 Peaker Plants (ENA) or Jordan (ENA) | 24 | 23 | 0 | Available
1 | 501D5A simple cycle | EECC | Sadaf bid (CALME) or 3rd party (EECC) | 24 | 1.2 | 0 | Available
2 | 7EA | EECC | Unassigned | 36 | 7 | 0 | Available
2 | LM6000 | ENA | Jordan (ENA) | 28 | 12 | 0 | Available
1 | LM6000 | ENA | Tri-Valley (ENA) | 14 | 6 | 0 | Available
1 | LM6000 | ENA | LODI (ENA) | 14 | 6 | 0 | Available
1 | Steam Turbine | ENA | Unassigned | 2.3 | 2.3 | 0 | Available
2 | 501F simple cycle | ESA | Rio Gen (ESA) | 75 | 12 | 0 | Available
2 | 501F simple cycle | ESA | Cuiba II (ESA) | 0 | 0 | 0 | Available
15 |  |  | Total Available | 243.3 | 69.5 | 0
NEGOTIATING
2 | 501F MHI simple cycle | ESA | Unassigned | 74 | 0 | 0 | Negotiating
3 | 9F 50hz gas turbine power islands |  | Project Gemini (EECC) | 0 | 0 | 0 | Negotiating
1 | 7FA |  | Pastoria (ENA) | 0 | 0 | 0 | Negotiating
9 | 7EA |  | Trinidad and Tobago Aluminum Smelter Project | 176.4 | 0 | 0 | Negotiating
15 |  |  | Total Negotiating | 250.4 | 0 | 0
74 |  |  | GRAND TOTALS | 1672.7 | 395.6 | 0

## Summary by Region
Turbine Position Report
Summary by Controlling Region
2000-09-08
PRELIMINARY
UNITS | MODEL | CONTROLLED BY | STATUS | PROJECT(S) | CONTRACT COST | PYMTS TO DATE | CANCEL- LATION
APACHI
7 | Fr 6B 60hz power barges | APACHI | Committed | Nigeria Barge II (APACHI) | 56 | 56 | 0
2 | Fr 6B 50hz power barges | APACHI | Committed | Nigeria Barge II (APACHI) | 14 | 14 | 0
|  |  |  | TOTAL APACHI | 70 | 70 | 0
CALME
2 | Fr 6B 60hz power barges | CALME | Tentative | LIPA (ENA) | 72 | 0 | 0
1 | 501D5A simple cycle | CALME | Available | Sadaf bid (CALME) or 2001 Peaker Plants (ENA) or Jordan (ENA) | 24 | 23 | 0
|  |  |  | TOTAL CALME | 96 | 23 | 0
CANADA
2 | 11N1 | Canada | Available | Unassigned | 26 | 0 | 0
ECP
1 | 7FA - now simple cycle | ECP | Committed | East Coast Power - Linden 6 (ECP) | 35 | 20 | 0
EECC
1 | 7FA - now simple cycle | EECC | Tentative | NEPCO/NESCO Goldendale (EECC) | 54 | 4 | 0
2 | 7FA w/ STG | EECC | Tentative | Gen Power - Dell (EECC) | 95 | 32 | 0
2 | 7FA w/ STG | EECC | Tentative | Gen Power - McAdams (EECC) | 95 | 32 | 0
3 | 9FA STAG power islands | EECC | Tentative | Spain Arcos (EEL) | 249 | 23.1 | 0
1 | 501D5A simple cycle | EECC | Available | Sadaf bid (CALME) or 3rd party (EECC) | 24 | 1.2 | 0
2 | 7EA | EECC | Available | Unassigned | 36 | 7 | 0
|  |  |  | TOTAL EECC | 553 | 99.3 | 0
ENA
4 | LM6000 | ENA | Committed | City of Austin (ENA) | 56 | 24 | 0
3 | 7FA | ENA | Tentative | Pastoria (ENA) | 198 | 0 | 0
4 | LM6000 | ENA | Tentative | Fountain Valley PSCO (ENA) | 56 | 24 | 0
4 | LM6000 | ENA | Tentative | Las Vegas Cogen II (ENA) | 56 | 24 | 0
1 | 7FA | ENA | Tentative | Vitro (ENA) | 31 | 25 | 0
2 | LM6000 | ENA | Available | Jordan (ENA) | 28 | 12 | 0
1 | LM6000 | ENA | Available | Tri-Valley (ENA) | 14 | 6 | 0
1 | LM6000 | ENA | Available | LODI (ENA) | 14 | 6 | 0
1 | Steam Turbine | ENA | Available | Unassigned | 2.3 | 2.3 | 0
|  |  |  | TOTAL ENA | 455.3 | 123.3 | 0
ESA
8 | LM6000 | ESA | Committed | Elektrobolt (ESA) | 112 | 48 | 0
2 | 501F simple cycle | ESA | Available | Rio Gen (ESA) | 75 | 12 | 0
2 | 501F simple cycle | ESA | Available | Cuiba II (ESA) | 0 | 0 | 0
2 | 501F MHI simple cycle | ESA | Negotiating | Unassigned | 74 | 0 | 0
|  |  |  | TOTAL ESA | 261 | 60 | 0
OTHER / UNKNOWN
3 | 9F 50hz gas turbine power islands |  | Negotiating | Project Gemini (EECC) | 0 | 0 | 0
1 | 7FA |  | Negotiating | Pastoria (ENA) | 0 | 0 | 0
9 | 7EA |  | Negotiating | Trinidad and Tobago Aluminum Smelter Project | 176.4 | 0 | 0
|  |  |  | TOTAL OTHER / UNKNOWN | 176.4 | 0 | 0
|  |  |  | GRAND TOTALS | 1672.7 | 395.6 | 0

## Summary by Type
Turbine Position Report
Summary by Controlling Region
2000-09-08
PRELIMINARY
UNITS | MODEL | CONTROLLED BY | PROJECT(S) | CONTRACT COST | PYMTS TO DATE | CANCEL- LATION | STATUS
2 | 11N1 | Canada | Unassigned | 26 | 0 | 0 | Available
1 | 501D5A simple cycle | CALME | Sadaf bid (CALME) or 2001 Peaker Plants (ENA) or Jordan (ENA) | 24 | 23 | 0 | Available
1 | 501D5A simple cycle | EECC | Sadaf bid (CALME) or 3rd party (EECC) | 24 | 1.2 | 0 | Available
2 | 501F MHI simple cycle | ESA | Unassigned | 74 | 0 | 0 | Negotiating
2 | 501F simple cycle | ESA | Rio Gen (ESA) | 75 | 12 | 0 | Available
2 | 501F simple cycle | ESA | Cuiba II (ESA) | 0 | 0 | 0 | Available
2 | 7EA | EECC | Unassigned | 36 | 7 | 0 | Available
9 | 7EA |  | Trinidad and Tobago Aluminum Smelter Project | 176.4 | 0 | 0 | Negotiating
3 | 7FA | ENA | Pastoria (ENA) | 198 | 0 | 0 | Tentative
1 | 7FA | ENA | Vitro (ENA) | 31 | 25 | 0 | Tentative
1 | 7FA |  | Pastoria (ENA) | 0 | 0 | 0 | Negotiating
1 | 7FA - now simple cycle | ECP | East Coast Power - Linden 6 (ECP) | 35 | 20 | 0 | Committed
1 | 7FA - now simple cycle | EECC | NEPCO/NESCO Goldendale (EECC) | 54 | 4 | 0 | Tentative
2 | 7FA w/ STG | EECC | Gen Power - Dell (EECC) | 95 | 32 | 0 | Tentative
2 | 7FA w/ STG | EECC | Gen Power - McAdams (EECC) | 95 | 32 | 0 | Tentative
3 | 9F 50hz gas turbine power islands |  | Project Gemini (EECC) | 0 | 0 | 0 | Negotiating
3 | 9FA STAG power islands | EECC | Spain Arcos (EEL) | 249 | 23.1 | 0 | Tentative
2 | Fr 6B 50hz power barges | APACHI | Nigeria Barge II (APACHI) | 14 | 14 | 0 | Committed
7 | Fr 6B 60hz power barges | APACHI | Nigeria Barge II (APACHI) | 56 | 56 | 0 | Committed
2 | Fr 6B 60hz power barges | CALME | LIPA (ENA) | 72 | 0 | 0 | Tentative
4 | LM6000 | ENA | City of Austin (ENA) | 56 | 24 | 0 | Committed
8 | LM6000 | ESA | Elektrobolt (ESA) | 112 | 48 | 0 | Committed
4 | LM6000 | ENA | Fountain Valley PSCO (ENA) | 56 | 24 | 0 | Tentative
4 | LM6000 | ENA | Las Vegas Cogen II (ENA) | 56 | 24 | 0 | Tentative
2 | LM6000 | ENA | Jordan (ENA) | 28 | 12 | 0 | Available
1 | LM6000 | ENA | Tri-Valley (ENA) | 14 | 6 | 0 | Available
1 | LM6000 | ENA | LODI (ENA) | 14 | 6 | 0 | Available
1 | Steam Turbine | ENA | Unassigned | 2.3 | 2.3 | 0 | Available