## Sheet2 (hidden)
TVA Peaking Plant
Issues/Savings
Issue
EECC increased current estimate
Fuel cost during start up not included
Tax Handling Fee to LLC for arms length transaction .25% not included in plan
Savings Recognized
| New Albany | Caledonia | Brownsville | Total
Decrease Environmental permitting | -310000 | -300000 | -233000 | -843000
Decrease Legal expense | -550000 | -550000 | -350000 | -1450000
Decrease Development | -200000 | -200000 | -200000 | -600000
Total Savings | -1060000 | -1050000 | -783000 | -2893000

## NA Mquip (hidden)
New Albany
Major Equipment Detail
Refurbishment with DLN Units 1-6
(includes commission) |  | 26785396
| Spare Parts | 5214604
32000000
Dow Unit
| Purchase & spares | 1347000
| Dissassembly | 500000
| Commission 10% | 134700
1981700
4 Kepco Units (original)
| Purchase | 27502700
| Commission IBC(10%) | 2700000
| Commission Natole | 900000
| Less Steam Turbine | -700000 | Allocate to 2000
| Disassemble & move to Kunsan Port | 1307660
| Less Steam Turbine | -200500 | Allocate to 2000
| Freight Reimbursement to IBC | 1274025
| Less Steam Turbine | -100000 | Allocate to 2000
| Commission (7%) | 89181.75
32773066.75
1 Kepco Unit (new set)
| 1 of 4 Purchase price | 6875000
| Disassembly & shipping | 500000
| Commission | 0
7375000
Unidentified |  | 0 | Spare parts to be reconciled per Miller
Total IBC items |  | 74129766.75
Transformers etc |  | 10870000
Grand Total Major Equipment |  | 84999766.75

## EECC (hidden)
EECC RECONCILIATION
| Control | Current
| Budget | Estimate |  | Net Increase
Brownsville | 395276 | 587051 |  | 191775
0
Caledonia | 395276 | 620100 |  | 224824
New Albany | 395276 | 641831 |  | 246555
Fulton | 395276 | 225000 | a | -170276
Total | 1581104 | 2073982 |  | 492878
a) Sunk Cost

## To Update (hidden)
To Update:
1 | Save file as new name
2 | Go to Summary tab
in cell "Q4" drop in date of Project Tracking report used as backup
3 | Go to LLC tab
unhide all columns
update actuals for applicable month
check totals
tie budget and current estimate to report from week before; explain any changes on summary tab
make sure that sum of Actuals to Date Total Project + Estimate to Complete + variance = Current Estimate amount
4 | Go to Summary tab
update variance explanations to current estimate

## Summary
ENRON CAPITAL & TRADE RESOURCES
Energy Services |  |  |  |  | Report Date: |  |  | 2014-09-03 13:19
Project 2000 | [9 empty] | Revision # 68
COST SUMMARY ($ thousands) |  |  |  |  | Expenditures to date: |  |  | As of 11/17/00
Revision # 68
2000-11-30
Actuals
Construction Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance | %
Excluding Financing Fee | MW | as of 7/22/99 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00 | from CE | Complete
Wilton Center, IL | 608 | 239675.4678 | 268951.92 | -23.5826 |  | 268928.3374 | -29252.8696 | 100%
Gleason, TN | 509 | 170575.01 | 170502.6664 | 5530.7584 |  | 176033.4247 | -5458.4147 | 96.86%
Wheatland, IN | 470 | 158451.2481 | 154433.6738 | 3547.0888 |  | 157980.7627 | 470.4854 | 97.75%
TOTAL PROJECTS | 1587 | 568701.7259 | 593888.2602 | 9054.2646 |  | 602942.5248 | -34240.7989 | 98.5%
Target $$/MW |  | 358.3502 |  |  |  | 379.926
Actuals
Financing Costs |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance
Project |  | as of 7/22/99 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00 | from CE
Wilton Center, IL |  | 1500 | 0 | 1500 |  | 1500 | 0
Calvert City, KY |  | 1500 | 0 | 1500 |  | 1500 | 0
Wheatland, IN |  | 1500 | 0 | 1500 |  | 1500 | 0
TOTAL PROJECTS |  | 4500 | 0 | 4500 |  | 4500 | 0
Backup Sites |  |  | Actuals
|  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete
Project |  | 1999-09-30 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00
Plano, IL |  |  | 314.5243 |  |  | 314.5243
Calvert City |  | 518.9711 | 518.9704 | 0.00062 |  | 518.9711
Petersburg, IN |  |  | 15 |  |  | 15
TOTAL PROGRAM |  | 518.9711 | 848.4947 | 0.00062 |  | 848.4953
Changes to Current Estimate Explanations
All Plants | Weekly | Recalculated Interest During Construction ( 6.50%)
All Plants | 1999-07-22 | Change in scope with addition of Union Labor
Current Estimate vs Actual Variance Explanations (000s)
Wilton Center, IL | -207.059 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -24287.358 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -1832.0004 | Increase Turbines - Scope Change
| -464.048 | Increase Transformers -Scope Change
| -6989.3952 | Additional Gas Interconnect Costs
| -236.6756 | Misc, $25 land over budget
| 540.6819 | Increase in Power Interconnect cost associated with Com Ed
| 1791.2818 | Decrease in IDC
| 90.305 | Reduced Forecast - Capitalized Salaries
| -918.498 | Increase Development , including GLC consulting costs
| -191.0129 | Cost related to Enron Generation Company, Standard & poors, RW Beck and AES Corp
| -478.2209 | Increase Permitting
| -353.4685 | Start-up Fuel costs higher than budgeted
| -352.4377 | Everest Legal Costs
| 4405 | Use of Contingency ( Contingency is now zero)
| -121.3083 | Insurance payment more than Budget
| -396.6632 | Water Interconnect, budgeted at zero
| -30000.8771 | Over Original Budget -including unapproved Nepco scope changes
Gleason, TN | -32.2033 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -5243.6 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -3392.74 | Increase Turbines - Scope Change
| -579.65 | Increase in Transformer Costs, including three spare bushings
| -965.9798 | Increase in TVA interconnect Costs - Redesign burden
| -191.0129 | Cost related to Enron Generation Company, Standard & poors, RW Beck and AES Corp
| 681.5878 | Decrease in IDC
| -252.2085 | Everest Legal
| -113.825 | Increase in Land -TVA Easement
| -705.4835 | Increase in Environmental Permitting
| -597.8799 | Increase in Start-up Fuel
| -112.3207 | Increase in Electrical Interconnect - Non TVA
| 136.9796 | Reduced Forecast - Capitalized Salaries & Travel Expenses
| -624.51 | Increase Development , including GLC consulting costs
| 5423.498 | Use of Contingency ( Contingency is now zero)
| -175.5552 | Temp variance, plant clerk will reclass labor as commerical not mobilization
| 66 | Other
| -6678.9033 | Under Original Budget -including unapproved Nepco scope changes
Wheatland, IN | -168.3561 | EECC Development Costs incurred prior to 6/1/99 that is not included in the budget
| -5550.8 | Increase in Nepco Construction Costs (includes unaprroved scope changes)-Review Scope Change Tab for further details
| -966.489 | Increase Turbines - Scope Change | [6 empty] | 0
| -428.4806 | Increase Transformers -Scope Change
| -1396.0156 | Increase in Land Acquisition costs
| -22.6163 | Increase in Permitting
| -339.3242 | Increase Development , including GLC consulting costs
| -195.0408 | Cost related to Enron Generation Company, Standard & Poors, RW Beck and AES Corp
| 84.5686 | Reduced Forecast - Capitalized Salaries
| -301.6721 | Everest Legal
| 4169.4222 | Decrease in Estimate to complete Power Interconnect
| 1031.7609 | Decrease Interest During Construction
| -211.3731 | Overtime assoc. with start-up & backfeed invoices not included in budget
| 3317 | Use of Contingency ( Contingency is now zero)
| -977.4161 | Over Original Budget -including unapproved Nepco scope changes
0
C:\Users\Felienne\Enron\EnronSpreadsheets\[benjamin_rogers__1143__2000 Weekly Report - 112000.xls]Summary
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Wilton
ENRON CAPITAL & TRADE RESOURCES | [11 empty] | As of 07/31/00
Energy Services | [65 empty] | C:\Users\Felienne\Enron\EnronSpreadsheets\[benjamin_rogers__1143__2000 Weekly Report - 112000.xls]Summary
Wilton Center, IL | [61 empty] | 2014-09-03 13:19 |  |  |  | Revision # 68 |  | Revision # 68
| 608 | [7 empty] | As of 11/03/00 | [6 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals |  | Anticipated
Revision # 68 | [6 empty] | Expense / | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | Actuals to Date | Increase / | ESTIMATE |  | TOTAL |  | (Increase)
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 |  | 1999-08-31 |  | 1999-09-30 |  | 1999-10-31 |  | 1999-11-30 |  | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | 2000-10-31 | 2000-11-30 | Total Project | (Savings) | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[8 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | [5 empty] | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase -GE 7ea (8) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 140040940 |  | 6800000 |  |  |  | 32884800 | [5 empty] | 18310527 |  | 6800000 |  | 5225143.44 |  | 6152847 |  | 6924847 |  | 6924847 |  | 6924847 |  | 24688143.63 |  | 0 |  | 13325691.37 |  | 7103247 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 142064940.44 | 1832000 | 0 |  | 142064940.44 |  | -2024000.44
| Other |  |  |  |  | ECT | Capital | 93330000 |  | 0 |  | 192000 | [11 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | -192000 | 0 |  | 0 |  | 192000
[60 empty] | 0 |  | 0
| Subtotal GE | [6 empty] | 93330000 |  | 0 |  | 140232940 |  | 6800000 |  | 0 |  | 32884800 |  | 0 |  | 0 |  | 18310527 |  | 6800000 |  | 5225143.44 |  | 6152847 |  | 6924847 |  | 6924847 |  | 6924847 |  | 24688143.63 |  | 0 |  | 13325691.37 |  | 7103247 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 142064940.44 | 1640000 | 0 |  | 142064940.44 |  | -1832000.44
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 5878600 |  | 0 |  | 1250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -74270.4 |  | 7480 |  | 0 |  | 1774814.4 |  | 0 |  | 1774814.4 |  | 591604.8 |  |  |  | 0 |  | 427250 |  | 590954.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 6342648 | 464698 | 0 |  | 6342648 |  | -464048
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT | Capital | [52 empty] | 0 |  | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT | Capital | [52 empty] | 0 |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT | Capital | [52 empty] | 0 |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [47 empty] | 0 |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [53 empty] | 0 |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
[62 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 0 |  | 0 |  | 5878600 |  | 0 |  | 1250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -74270.4 |  | 7480 |  | 0 |  | 1774814.4 |  | 0 |  | 1774814.4 |  | 591604.8 |  | 0 |  | 0 |  | 427250 |  | 590954.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 6342648 | 464698 | 0 |  | 6342648 |  | -464048
| TOTAL MAJOR EQUIPMENT | [6 empty] | 93330000 |  | 0 |  | 146111540 |  | 6800000 |  | 1250000 |  | 32884800 |  | 0 |  | 0 |  | 18310527 |  | 6800000 |  | 5150873.04 |  | 6160327 |  | 6924847 |  | 8699661.4 |  | 6924847 |  | 26462958.03 |  | 591604.8 |  | 13325691.37 |  | 7103247 |  | 427250 |  | 590954.8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 148407588.44 | 2104698 | 0 |  | 148407588.44 |  | -2296048.44
NEPCO SITE CONSTRUCTION COSTS
[14 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco | Capital |  |  |  |  | 1538965 | [23 empty] | 11510 |  | 43198 |  | 372928 |  |  |  | 185141 | [5 empty] | 3790240 |  | 646960 |  |  |  | 57023 |  |  |  | 5107000 | 3573035 | 5000 |  | 5112000 |  | -3573035
| PROJECT MANAGEMENT |  |  |  |  | Nepco | Capital |  |  |  |  | 1717382 | [23 empty] | 125266 |  | 90965 |  | 440457 |  |  |  | 756685 | [5 empty] | 2636520 |  | 157095 |  |  |  | 59012 |  |  |  | 4266000 | 2551618 | 3000 |  | 4269000 |  | -2551618
| PROJECT INDIRECTS |  |  |  |  | Nepco | Capital |  |  |  |  | 14562379 | [23 empty] | 532741 |  | 359138 |  | 834665 |  |  |  | -63412 | [5 empty] | 2533405 |  | 269632 |  |  |  | 187831 |  |  |  | 4654000 | -9855379 | 53000 |  | 4707000 |  | 9855379
| ENGINEERING |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 378688 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 192524 |  | 75508 |  | 76741 |  | 0 |  | 287193 |  | 0 |  | 0 |  | 466012 |  | 76222 |  | 0 |  | 17800 |  |  |  | 1192000 | 815312 | 2000 |  | 1194000 |  | -815312
| FREIGHT |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 47 |  | 67880 |  | 2771 |  | 0 |  | -36611 |  | 0 |  | 0 |  | 28783 |  | 0 |  | 0 |  | 6130 |  |  |  | 69000 | -80000 | 1000 |  | 70000 |  | 80000
| CONTINGENCY |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 104121 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 | -4121 | 100000 |  | 100000 |  | 4121
| RESERVES | [5 empty] | Capital | 0 |  | 0 |  | 164225 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 147037 |  | 0 |  | 0 |  | 0 | 0 | 147037 | 458775 | 475963 |  | 623000 |  | -458775
| TOTAL General Provisions | [5 empty] | Capital | 0 |  | 0 |  | 18615760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 862088 | 0 | 636689 | 0 | 1727562 | 0 | 0 | 0 | 1128996 | 0 | 0 | 0 | 0 |  | 9454960 |  | 1296946 |  | 0 |  | 327796 |  | 0 | 0 | 15435037 | -2540760 | 639963 | 0 | 16075000 | 0 | 2540760
BOP Procurement
| A/G PIPING |  |  |  |  | Nepco | [5 empty] | 410304 | [25 empty] | 10115 |  | 82505 |  |  |  | 254519 | [5 empty] | 128949 |  | 95 |  |  |  | -7183 |  |  |  | 469000 | 58696 | 0 |  | 469000 |  | -58696
| A/G ELECTRICAL |  |  |  |  | Nepco | [5 empty] | 4987110 | [25 empty] | 272613 |  | 963804 |  |  |  | 1614778 | [5 empty] | 1795808 |  | 277225 |  |  |  | 11772 |  |  |  | 4936000 | 667890 | 719000 |  | 5655000 |  | -667890
| INSTRUMENTATION |  |  |  |  | Nepco | [5 empty] | 786663 | [23 empty] | 3301 |  |  |  | 73986 |  |  |  | 446716 | [5 empty] | 314496 |  | 8244 |  |  |  | 38257 |  |  |  | 885000 | 98337 | 0 |  | 885000 |  | -98337
| EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 654500 | [25 empty] | 63890 |  | 331326 |  |  |  | 349256 | [5 empty] | 74075 |  | 10262 |  |  |  | 2191 |  |  |  | 831000 | 176500 | 0 |  | 831000 |  | -176500
| TOTAL BOP Procurement | [5 empty] | Capital | 0 |  | 0 |  | 6838577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3301 | 0 | 346618 | 0 | 1451621 | 0 | 0 | 0 | 2665269 | 0 | 0 | 0 | 0 |  | 2313328 |  | 295826 |  | 0 |  | 45037 |  | 0 | 0 | 7121000 | 1001423 | 719000 | 0 | 7840000 | 0 | -1001423
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [10 empty] | 2332998 | [25 empty] | 949522 |  | 27272 |  |  |  | 2274 | [5 empty] | 310738 |  | 230849 |  |  |  | 449345 |  |  |  | 1970000 | -362998 | 0 |  | 1970000 |  | 362998
| SITE PREPARATION/IMPROVEMENTS - M | [10 empty] | 0 | [37 empty] | 66938 |  | 17959 |  |  |  | 0 |  | 0 | 0 | 84897 | 85000 | 103 |  | 85000 |  | -85000
| UNDERGROUND ELECTRICAL - M | [10 empty] | 497417 | [25 empty] | 133215 |  | 128511 |  |  |  | 1060517 | [5 empty] | -896959 |  | 20806 |  |  |  | 0 |  | 0 | 0 | 446090 | -51417 | 0 |  | 446090 |  | 51327
| UNDERGROUND ELECTRICAL - L & S | [10 empty] | 834305 | [25 empty] | 725 |  | 936926 |  |  |  | 485780 | [5 empty] | 887965 |  | 37139 |  |  |  | 0 |  | 0 | 0 | 2348535 | 1514695 | 465 |  | 2349000 |  | -1514695
| UNDERGROUND PIPING - L & S | [10 empty] | 718539 | [25 empty] | 6350 |  | 555282 |  |  |  | 444670 | [5 empty] | 317161 |  | 6476 | [7 empty] | 1329939 | 609461 | 0 |  | 1329939 |  | -611400
| UNDERGROUND PIPING - M | [10 empty] | 453000 | [25 empty] | 103285 |  | 65044 |  |  |  | 65987 | [5 empty] | 28196 |  | 0 |  |  |  | 3488 |  |  |  | 266000 | -187000 | 0 |  | 266000 |  | 187000
| CONCRETE - L & S | [10 empty] | 2265021 | [25 empty] | 644530 |  | 1379020 |  |  |  | 1185772 | [5 empty] | 166582 |  | 162938 |  |  |  | 164158 |  |  |  | 3703000 | 1608979 | 171000 |  | 3874000 |  | -1608979
| CONCRETE - M | [10 empty] | 1150462 | [25 empty] | 508620 |  | 553474 |  |  |  | 192602 | [5 empty] | 183460 |  | 4885 |  |  |  | 959 |  |  |  | 1444000 | 295538 | 2000 |  | 1446000 |  | -295538
| GROUT - L | [10 empty] | 189949 | [25 empty] | 0 |  | 52828 |  |  |  | 236144 | [5 empty] | 719843 |  | 22647 |  |  |  | 0 |  | 0 | 0 | 1031462 | 841051 | 0 |  | 1031462 |  | -841513
| GROUT - M | [10 empty] | 77621 | [25 empty] | 4214 |  | 7412 |  |  |  | 3992 | [5 empty] | 19276 |  | 3054 |  |  |  | 2052 |  |  |  | 40000 | -37621 | 0 |  | 40000 |  | 37621
| STRUCTURAL STEEL - L | [10 empty] | 144437 | [25 empty] | 0 |  | 0 |  |  |  | 86250 | [5 empty] | 448505 |  | 13813 |  |  |  | 0 |  | 0 | 0 | 548568 | 404563 | 432 |  | 549000 |  | -404563
| STRUCTURAL STEEL - M | [10 empty] | 327314 | [25 empty] | 85468 |  | 1 |  |  |  | 109164 | [5 empty] | 155678 |  | 0 |  |  |  | 0 |  | 0 | 0 | 350311 | 22686 | 0 |  | 350311 |  | -22997
| ARCHITECTURAL -S | [10 empty] | 330460 | [25 empty] | 0 | [5 empty] | 204390 | [5 empty] | -201644 |  | 14928 |  |  |  | 0 |  | 0 | 0 | 17674 | -312460 | 326 |  | 18000 |  | 312460
| BUILDINGS/ENCLOSURES -S | [10 empty] | 808591 | [25 empty] | 0 |  | 92600 |  |  |  | 57960 | [5 empty] | 328823 |  | 15680 |  |  |  | 66937 |  |  |  | 562000 | -246591 | 0 |  | 562000 |  | 246591
| A/G PIPING - L & S | [10 empty] | 858343 | [25 empty] | 0 |  | 45963 |  |  |  | 312622 | [5 empty] | 900383 |  | 23197 |  |  |  | 0 |  | 0 | 0 | 1282165 | 423657 | 0 |  | 1282165 |  | -423822
| A/G ELECTRICAL - L & S | [10 empty] | 1745515 | [27 empty] | 46290 |  |  |  | 1181048 | [5 empty] | 4490023 |  | 320829 |  |  |  | 40810 |  |  |  | 6079000 | 4337485 | 4000 |  | 6083000 |  | -4337485
| INSTRUMENTATION - L | [10 empty] | 571564 | [27 empty] | 526 |  |  |  | 32449 | [5 empty] | 188776 |  | 570 |  |  |  | 679 |  |  |  | 223000 | -348564 | 0 |  | 222997 |  | 348567
| INSULATION & PAINTING -S | [10 empty] | 931641 | [27 empty] | 0 | [9 empty] | 423025 |  | 256828 |  |  |  | 271147 |  |  |  | 951000 | 19359 | 0 |  | 951000 |  | -19359
| MECHANICAL EQUIPMENT - L & S | [10 empty] | 6297865 | [25 empty] | 134000 |  | 625531 |  |  |  | 3192197 | [5 empty] | 14663790 |  | 225940 |  |  |  | 12542 |  |  |  | 18854000 | 12556135 | 0 |  | 18854000 |  | -12556135
| PLANT STARTUP - L, M & S | [10 empty] | 868340 | [31 empty] | 169550 | [5 empty] | 3849976 |  | 391701 |  |  |  | 43773 |  |  |  | 4455000 | 3588660 | 2000 |  | 4457000 |  | -3588660
| UNION ADDER ESTIMATE ERROR | [10 empty] | -1225177 | [43 empty] | 0 |  | 0 | 0 | 0 | 1225177 | 0 |  | 0 |  | -1225177
| ENGINEERING REWORK | [38 empty] | 29554 |  |  |  | 28031 | [5 empty] | 202334 |  | 26893 |  |  |  | 5188 |  |  |  | 292000 | 292000 | 0 |  | 292000 |  | -292000
| CHANGE ORDERS | [38 empty] | 99225 |  |  |  | 17420 | [5 empty] | 120060 |  | 18177 |  |  |  | -3882 |  |  |  | 251000 | 251000 | 0 |  | 251000 |  | -251000
| BACKCHARGES | [38 empty] | 12201 |  |  |  | 65160 | [5 empty] | 343670 |  | -186751 |  |  |  | 5720 |  |  |  | 240000 | -51000 | 0 |  | 240000 |  | -240000
| TOTAL Construction | [10 empty] | 20178205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2569929 | 0 | 4657660 | 0 | 0 | 0 | 9133979 | 0 | 0 | 0 | 0 |  | 27716599 |  | 1628558 |  | 0 |  | 1062916 |  | 0 | 0 | 46769641 | 26477795 | 180326 | 0 | 46949964 | 0 | -26771759 | 0
Switchyard
| SWITCHYARD | [10 empty] | 5312100 | [25 empty] | 28388 |  | 763285 |  |  |  | 2460865 | [5 empty] | 1217659 |  | 430823 |  |  |  | -338020 |  |  |  | 4563000 | -652100 | 97000 |  | 4660000 |  | 652100
| TOTAL SWITCHYARD | [10 empty] | 5312100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28388 | 0 | 763285 | 0 | 0 | 0 | 2460865 | 0 | 0 | 0 | 0 |  | 1217659 |  | 430823 |  | 0 |  | -338020 |  | 0 | 0 | 4563000 | -652100 | 97000 | 0 | 4660000 | 0 | 652100
| Plug to get back to Nepco's Forecast (In some cases Actuals are higher than forecast) | [48 empty] | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Nepco % Cash (difference between prior | [10 empty] | 0 |  |  |  | 0 | [19 empty] | 8573073 |  | 7135450 |  | -7855877 |  | 12922196 |  | -3861277 |  | 19510321 |  |  |  | -29795364 |  | -2675074 |  |  |  | -1097729 |  |  |  | 2855719 | 0 | -3148683 | 0 | -292964 | 0 | 292964
| month actual and current month % of Cash Curves) | [64 empty] | 0
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [6 empty] | 0 |  | 0 |  | 50944642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9438462 | 0 | 10717074 | 0 | 744251 | 0 | 12922196 | 0 | 11527832 | 0 | 19510321 | 0 | 0 |  | 10907182 |  | 977079 |  | 0 |  | 0 |  | 0 | 0 | 76744397 | 24286358 | -1512394 | 0 | 75232000 | 0 | -24287358 | 0
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 935200 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 77933.3333 |  | 77933.35 |  | 77933 |  | 77933.33 |  | 82933.33 |  | 77933.34 |  | 77933.33 |  | 77933.33 |  | 77933.33 |  | 77933 |  | 77933.33 |  | 77933.33 |  |  |  | 0 |  | 6741 |  | 0 | 0 | 946940.3333 |  | 0 |  | 946940.3333 |  | -11740.3333
| NEPCO |  |  |  |  | NEPCO | Capital | 0 |  | 0 |  | 2824800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 235400 |  | 235400 |  | 235399 |  | 235399 |  | 235399 |  | 235398 |  | 235399 |  | 235400 |  | 235400 |  | 235400 |  | 235400 |  | 235398 |  |  |  | 0 |  | 0 |  | 0 | 0 | 2824792 | -8 | 0 |  | 2824792 |  | 8
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
[60 empty] | 0 |  | 0
| TOTAL OVERHEADS & FEES | [6 empty] | 0 |  | 0 |  | 3760000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 313333.3333 |  | 313333.35 |  | 313332 |  | 313332.33 |  | 318332.33 |  | 313331.34 |  | 313332.33 |  | 313333.33 |  | 313333.33 |  | 313333 |  | 313333.33 |  | 313331.33 |  | 0 |  | 0 |  | 6741 |  | 0 | 0 | 3771732.3333 | -8 | 0 |  | 3771732.3333 |  | -11732.3333
ADDERS OUTSIDE EECC SCOPE | [6 empty] | Capital
| Sound Mitigation |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 9479079 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 815280 |  | 2025875.7 |  | 0 |  | 0 |  | 1894103.8 |  | 0 |  | 0 |  | 0 |  | 1183814.88 |  | 2943550.62 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 368146 |  |  |  | 9230771 | 0 | 248308 |  | 9479079 |  | 0
| Evaporative Coolers |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Roads & Ditches |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Drainage |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| On-Site Well/Water System |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
0
| TOTAL ADDERS | [6 empty] | 0 |  | 0 |  | 9479079 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 815280 |  | 2025875.7 |  | 0 |  | 0 |  | 1894103.8 |  | 0 |  | 0 |  | 0 |  | 1183814.88 |  | 2943550.62 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 368146 |  | 0 | 0 | 9230771 | 0 | 248308 |  | 9479079 |  | 0
ECT PROJECT COSTS
85881594.91
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 185000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 185000 | 0 | 0 |  | 185000 |  | 0
| Reimbursable Costs OEC | [5 empty] | Capital | 0 |  | 0 |  | 723786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 104652 |  | 114711.83 |  | 194341.7 |  | 157200.32 |  | 64914.39 |  | 33881.38 |  | 37188 |  | 20139 | 0 | 727028.62 | 0 | 0 |  | 727028.62 |  | -3242.62
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37000 |  | 141652 |  | 151711.83 |  | 231341.7 |  | 194200.32 |  | 64914.39 |  | 33881.38 |  | 37188 |  | 20139 | 0 | 912028.62 | 0 | 0 |  | 912028.62 |  | -3242.62
WATER INTERCONNECT | [5 empty] | ECT | Capital | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 216381.67 |  | 2174.14 |  | 0 |  | 168836 |  | 0 |  | 6527.91 |  | 0 |  | 2743.49 |  | 0 |  | 0 |  | 0 | 0 | 396663.21 | 0 | 0 |  | 396663.21 |  | -396663.21
SALES TAX ON EQUIPMENT | [5 empty] | ECT | Capital | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 359494 |  | 0 | 0 | 359494 | 0 | 140506 |  | 500000 |  | 0
SPARE PARTS | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1253881 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 29469.43 |  | 271859.17 |  | 201156.09 |  | 3218 |  | 0 | 0 | 505702.69 | 0 | 0 |  | 505702.69 |  | 748178.31
LAND ACQUISITION
| Land Option |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 28500 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 0 |  | 8500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 28500 | 0 | 0 |  | 28500 |  | 0
| Title Commitment |  |  |  |  | ECT | Capital |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT | Capital |  |  |  |  | 2251500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1446361 |  | 0 |  | 0 |  | 821965.14 |  | 0 |  | 0 |  | 1000 |  | 7992 |  | 0 |  | 180000 |  | -13167.86 |  | 0 |  | 0 |  | 1662 |  | 0 |  | 0 |  | 350 |  | 0 |  | 0 | 30281 | 2476443.28 | 0 | 0 |  | 2476443.28 |  | -224943.28
| Closing Costs |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [47 empty] | 0 |  | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [6 empty] | 0 |  | 0 |  | 2280000 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 1446361 |  | 8500 |  | 0 |  | 821965.14 |  | 0 |  | 0 |  | 1000 |  | 7992 |  | 0 |  | 180000 |  | -13167.86 |  | 0 |  | 0 |  | 1662 |  | 0 |  | 0 |  | 350 |  | 0 |  | 0 | 30281 | 2504943.28 | 0 | 0 |  | 2504943.28 |  | -224943.28
ENVIRONMENTAL PERMITTING
| Air Permitting | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Groundwater | [5 empty] | Expense | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense |  |  | 0 |  | 400000 |  | 0 |  | 0 |  | 0 |  | 8000 |  | 24712 |  | 71081 |  | 13261.65 |  | 39577.43 |  | 11821.22 |  | 11746.18 |  | 19877.66 |  | 29832.4 |  | 39859.51 |  | 5434 |  | 2588.45 |  | 0 |  | 3856 |  | -1595 |  | 9124.88 |  | 2377 |  | 125613.51 | [5 empty] | 417167.89 | 0 | 0 |  | 417167.89 |  | -17167.89
| Annexation agreement/roadway improvement | [54 empty] | 20360 |  | 5572 | 435121 | 461053 | 0 | 0 |  | 461053 |  | -461053
0
| Subtotal Environmental Permitting | [6 empty] | 0 |  | 0 |  | 400000 |  | 0 |  | 0 |  | 0 |  | 8000 |  | 24712 |  | 71081 |  | 13261.65 |  | 39577.43 |  | 11821.22 |  | 11746.18 |  | 19877.66 |  | 29832.4 |  | 39859.51 |  | 5434 |  | 2588.45 |  | 0 |  | 3856 |  | -1595 |  | 9124.88 |  | 2377 |  | 125613.51 |  | 20360 |  | 5572 | 435121 | 878220.89 | 0 | 0 |  | 878220.89 |  | -478220.89
POWER INTERCONNECTION -Com Ed | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 50050 |  | 160615.6 |  | 8227.76 |  | 115500 |  | 445269.08 |  | 0 |  | 0 |  |  |  | 6343 |  | 0 |  | 8574.66 |  | 0 |  | 0 | -335262 | 459318.1 | 0 | 0 |  | 459318.1 |  | 540681.9
GAS INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 3500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4210113.22 |  | 0 |  | 0 |  | 0 |  | 4364175 |  | 127353 | 687754 | 9389395.22 | 7400000 | 1100000 |  | 10489395.22 |  | -6989395.22
Startup Fuel
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 310380 |  | 1670726 |  | -127637.5 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1853468.5 | 0 | 0 |  | 1853468.5 |  | -353468.5
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 310380 |  | 1670726 |  | -127637.5 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1853468.5 | 0 | 0 |  | 1853468.5 |  | -353468.5
INSURANCE DURING CONSTR | [6 empty] | Capital | 0 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 266248.5 |  | 0 |  | 0 |  | 0 |  | 5000 |  | 0 |  | 0 |  | 59.75 |  | 0 |  | 0 |  | 0 | 0 | 271308.25 | 0 | 0 |  | 271308.25 |  | -121308.25
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 29401.83 |  | 13770.85 |  | 7745.74 |  | 6275.69 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9119.08 |  | 9717.45 |  | 33664 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 109694.64 | -90305 | 0.36 |  | 109695 |  | 90305
DEVELOPMENT EXPENSES
| Salaries | [5 empty] | Expense | 200000 |  | 0 |  | 35000 |  | 0 |  | 0 |  | 22604 |  | 0 |  | 7949 |  | 0 |  |  |  | 0 |  | 0 |  | 6591.41 |  | 0 |  | 0 |  | 0 |  | 0 |  | 19123.98 |  | 0 |  | 0 |  | -33664 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 22604.39 | -12396 | 0 |  | 22604.39 |  | 12395.61
| Travel Expenses | [5 empty] | Expense | 0 |  | 50000 |  | 45000 |  | 0 |  | 1236 |  | 9770 |  | 5706 |  | 9652 |  | 3504 |  | 5185.43 |  | 3598.69 |  | 3892.71 |  | 6342.74 |  | 1599.42 |  | 3506.18 |  | 5695.65 |  | 9038.71 |  | 3164.35 |  | 3884.55 |  | 1293.25 |  | 1428.68 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 78498.36 | 0 | 0 |  | 78498.36 |  | -33498.36
| Consulting - GLC | [5 empty] | Expense | 0 |  | 24235 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37759.78 |  | 42194.99 |  | 35999.89 |  | 35401.09 |  | 38258.9 |  | 64824.96 |  | 99822 |  | 0 |  | 131341.57 |  | 0 |  | 29358.5 |  | 0 |  | 0 | 0 | 514961.68 | 0 | 0 |  | 514961.68 |  | -514961.68
| Other | [5 empty] | Expense | 400000 |  | -356935 |  | 134593 |  | 0 |  | 0 |  | 46735 |  | 21114 |  | 1899 |  | 8288 |  | 84262.75 |  | 10838.34 |  | 0 |  | 20657.14 |  | 8465.74 |  | 2127.81 |  | 4850 |  | 6628.7 |  | 822.91 |  | 5041.9 |  | 575 |  | 57477.71 |  | 107431.97 |  | 31567.85 |  | 2794.75 |  | 2972 |  | 92476 | 0 | 517026.57 | 0 | 0 |  | 517026.57 |  | -382433.57
| Enron Generation Company Costs | [10 empty] | 0 | [23 empty] | 83333.33 |  | 107679.56 | [21 empty] | 191012.89 | 0 | 0 |  | 191012.89 |  | -191012.89
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [10 empty] | 0 | [13 empty] | 127279.45 |  | 49930.79 |  | 29848.78 | [29 empty] | 207059.02 | 207059 | 0 |  | 207059.02 |  | -207059.02
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 600000 |  | -282700 |  | 214593 | 0 | 0 | 0 | 1236 | 0 | 79109 | 0 | 26820 | 0 | 19500 | 0 | 11792 |  | 216727.63 |  | 64367.82 |  | 33741.49 |  | 33591.29 |  | 47824.94 | 0 | 131162.31 | 0 | 154225.1 | 0 | 51068.5 | 0 | 61370.14 | 0 | 73751.41 | 0 | 101690.25 | 0 | 25242.39 |  | 238773.54 |  | 31567.85 |  | 32153.25 |  | 2972 |  | 92476 | 0 | 1531162.91 | 194663 | 0 | 0 | 1531162.91 | 0 | -1316569.91
LEGAL EXPENSES
| Vinson & Elkins | [5 empty] | Expense | 0 |  | 294489 |  | 6751 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 605 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 605 | 0 | 0 |  | 605 |  | 6146
| Everst Legal Expense | [36 empty] | 252208.46 |  | 49463.67 | [19 empty] | 301672.13 | 0 | 0 |  | 301672.13 |  | -301672.13
| Other | [5 empty] | Expense | 500000 |  | -300000 |  | 250000 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 21422.91 |  | 0 |  | 75 |  | 6749.05 |  | 4454.98 |  | 0 |  | 0 |  | 0 |  | 10000 |  | 0 |  | 0 |  | 264209.67 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 306911.61 | 0 | 0 |  | 306911.61 |  | -56911.61
[10 empty] | 5511 | [49 empty] | 0 | 0 | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 500000 | 0 | 0 | 0 | 256751 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 605 |  | 0 |  | 21422.91 |  | 0 |  | 75 |  | 6749.05 |  | 4454.98 |  | 252208.46 |  | 49463.67 |  | 0 |  | 10000 |  | 0 |  | 0 |  | 264209.67 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 609188.74 | 0 | 0 |  | 609188.74 |  | -352437.74
INTEREST DURING CONSTRUCTION (6.5%) | [6 empty] | Capital | 10922239 |  | 47687 |  | 12808124 |  | 340000 |  | 46410 |  | 139384 |  | 227439 |  | 231444 |  | 413290 |  | 378615.0109 |  | 426069.8241 |  | 463711.3754 |  | 505639.6857 |  | 568176 |  | 663422.2939 |  | 873819.3253 |  | 891069.8159 |  | 1048965.8688 |  | 1175441.8445 |  | 1292974 |  | 1330970.1609 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 11016842.2054 |  | 0 |  | 11016842.2054 |  | 1791281.7946
ECT TOTAL Project Costs | [11 empty] | 24972135 | 0 | 340000 | 0 | 47646 | 0 | 218493 | 0 | 282259 | 0 | 1722017 | 0 | 534669.83 | 0 | 622375.1409 | 0 | 1381148.8641 | 0 | 515549.7754 | 0 | 551052.1557 | 0 | 693677.65 | 0 | 997479.5839 | 0 | 1810970.3253 | 0 | 1294710.1259 | 0 | 1582025.6788 | 0 | 1578800.3345 | 0 | 1875329.53 | 0 | 7508652.3809 |  | 614483.34 |  | 373521.65 |  | 401728.89 |  | 4787407 |  | 245540 | 817894 | 30797431.2554 | 7504358 | 1240506.36 | 0 | 32037937.6154 | 0 | -7065802.6154 | 0
CONTINGENCY | [6 empty] | Capital | 5395729 |  | 67851 |  | 4408071.75 | [13 empty] | 0 | [33 empty] | 0 | -4408072 | 0 | 2030320 | 0 | 2030320 | 4408071.75
GRAND TOTAL (without Financing Fees & SWAP) | [11 empty] | 239675467.75 | 0 | 7140000 | 0 | 1297646 | 0 | 33103293 | 0 | 282259 | 0 | 1722017 | 0 | 18845196.83 |  | 8237655.1409 |  | 8871230.9375 |  | 6989210.1254 |  | 7789231.1557 |  | 11600775.18 | 0 | 17679120.9139 | 0 | 39304333.6953 | 0 | 2943898.2559 | 0 | 29327061.2588 | 0 | 23466763.2845 | 0 | 22126233.53 | 0 | 8412940.5109 |  | 11834996.67 |  | 1350600.65 |  | 401728.89 |  | 5162294 |  | 245540 | 817894 | 268951920.0287 | 29487334 | -23579.64 | 2030320 | 268928337.3887 | 2030320 | -29252869.6387
$/Kw | [63 empty] | 442316.3444
[14 empty] | 7140000 | 0 | 1297646 | 0 | 33103293 | 0 | 282259 | 0 | 1722017 | 0 | 18845196.83 | 0 | 8237655.1409 | 0 | 8871230.9375 | 0 | 6989210.1254 | 0 | 7789231.1557 | 0 | 11600775.18 | 0 | 17679120.9139 | 0 | 39304333.6953 | 0 | 2943898.2559 | 0 | 29290061.2588 | 0 | 23325111.2845 | 0 | 21974521.7 | 0 | 8181598.8109 | 0 | 11611326.92 | 0 | 1013827.09 | 0 | 166691.42 | 0 | 5121888 | 0 | 225401 | 817894
[58 empty] | Spare parts | Spare parts | -505702.69
[58 empty] | Mobilization | Mobilization | -912028.62
[58 empty] | Sales Tax | Sales Tax | 0
[58 empty] | Expenses | Expenses | -426646
[58 empty] | October Activity | October Activity | 0
267107542.7187
[58 empty] | Project Reports | Project Reports | 267409645
-302102.2813
166466044
93413104.03
755906.13
-6077
80000
100
278090.26
-127637.5
260859529.92
8017860.6187
INTEREST SWAP | [6 empty] | Capital | 0 |  | 44922.91 |  | -6078 | [7 empty] | -21556.4 |  | 66478.91 |  | -51000 | [35 empty] | -6077.49 | 0 | 0 |  | -6077.49 |  | 0
Franchise tax | [11 empty] | 0 | [9 empty] | 0 |  | 100 | [5 empty] | 279 |  | 10 |  |  |  | 800 | [11 empty] | 100 | [11 empty] | 1289 | 0 | 0 |  | 1289
Property Tax | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 80000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 80000 | 0 | 0 |  | 80000
Current FIT | [11 empty] | -56499 | [9 empty] | -56500 |  | -34 |  | -69954 |  | -22011 |  | -959 |  | -3 |  | 52217 |  | -52497 | [23 empty] | -149741 |  | 0 |  | -149741
Grand Total Including SWAP & Financial Fees | [11 empty] | 239612890.75 | 0 | 7140000 | 0 | 1297646 | 0 | 33103293 | 0 | 260702.6 | 0 | 1731995.91 | 0 | 18794262.83 |  | 8167701.1409 |  | 8849219.9375 |  | 6988530.1254 |  | 7789238.1557 |  | 11652992.18 | 0 | 17627423.9139 | 0 | 39304333.6953 | 0 | 2943898.2559 | 0 | 29327061.2588 | 0 | 23466763.2845 | 0 | 22126233.53 | 0 | 8493040.5109 |  | 11834996.67 |  | 1350600.65 |  | 401728.89 |  | 5162294 |  | 245540 | 817894 | 268877390.5387 | 29487334 | -23579.64 | 2030320 | 268853807.8987 | 2030320 | -29252869.6387
Plano, IL
CAPITALIZED SALARIES | [6 empty] | Expense | 0 |  | 220000 | [7 empty] | 19728.93 |  | 0 |  |  |  | 12698.23 |  |  |  | 5725.45 |  |  |  | 591.45 | [5 empty] | 1242.3 | [21 empty] | 39986.36 |  | 0 |  | 39986.36 |  | 0
DEVELOPMENT EXPENSES | [6 empty] | Expense | 0 |  | 30000 | [5 empty] | 1342.96 |  | 28915.95 |  | 19328.23 |  | 567.63 |  | 68418.82 | [35 empty] | 118573.59 |  | 0 |  | 118573.59 |  | 0
LEGAL EXPENSES | [6 empty] | Expense | 0 |  | 35000 |  |  |  | 52133 | [7 empty] | 1331.32 | [37 empty] | 53464.32 |  | 0 |  | 53464.32 |  | 0
LAND | [6 empty] | Expense | 0 |  | 20000 |  |  |  | 87500 | [29 empty] | 15000 | [15 empty] | 102500 |  | 0 |  | 102500 |  | 0
0
TOTAL-Plano, IL | [7 empty] | 0 |  | 305000 |  | 0 |  | 139633 |  | 1342.96 |  | 48644.88 |  | 19328.23 | 0 | 1898.95 | 0 | 81117.05 |  | 0 |  | 5725.45 |  | 0 |  | 591.45 |  | 0 | 0 | 0 | 0 | 1242.3 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 314524.27 |  | 0 |  | 314524.27 |  | 0
TOTAL ILLINOIS PLANT COSTS | [7 empty] | #REF! |  | #REF! |  | 239612890.75 | 0 | 7279633 | 0 | 1298988.96 | 0 | 33151937.88 | 0 | 280030.83 | 0 | 1733894.86 | 0 | 18875379.88 |  | 8167701.1409 |  | 8854945.3875 |  | 6988530.1254 |  | 7789829.6057 |  | 11652992.18 | 0 | 17627423.9139 | 0 | 39305575.9953 | 0 | 2943898.2559 | 0 | 29327061.2588 | 0 | 23481763.2845 | 0 | 22126233.53 | 0 | 8493040.5109 |  | 11834996.67 |  | 1350600.65 |  | 401728.89 |  | 5162294 |  | 245540 | 817894 | 269191914.8087 | 29487334 | -23579.64 | 2030320 | 269168332.1687 | 2030320 | -29252869.6387
54C 1070
44Q 1070
44Q 9310
IDC correction
2360 Property tax
4082-400 franchise
44Q 2160
Note on R9: acopela: 6/2/99 Per DD budget was changed 6/11/99 Per Shealy Budget changed
Note on BS9: acopela: includes $2,024,000 CO#1
Note on BU108: aspoede: LD against Braden

## Calvert City
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [62 empty] | C:\Users\Felienne\Enron\EnronSpreadsheets\[benjamin_rogers__1143__2000 Weekly Report - 112000.xls]Summary
Calvert City, KY | [9 empty] | 510 |  | MW | [46 empty] | 2014-09-03 13:19 |  |  |  | Revision # 68
| 509 |  |  |  |  | MW |  |  |  |  | As of 4/14/00 | [6 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  |  |  | Anticipated
[8 empty] | Expense / |  | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  |  | Capital |  | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 | 1999-07-31 | 1999-08-31 | Tran.to Gleason | 1999-09-30 | 1999-10-31 | 1999-11-30 | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[10 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - WH501FD (2) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 12224800 |  | 31276400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 0 | 393210.9 | -56349430 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.39 |  | 0 |  | 0.39 |  | 0 |  | 0
| TURBINE UNITS, Purchase - WH501F (1) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 17151750 |  | 12474000 |  | 0 | [7 empty] | 0 | 0 | 0 | -29625750 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Disassemble |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight Commission |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE REFURBISHMENT |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 93330000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 107199.47 | 0 | -107199 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.47 |  | 0 |  | 0 |  | 0.47 |  | -0.47
[59 empty] | 0 |  |  |  | 0
| Subtotal Westinghouse | [8 empty] | 93330000 |  | 0 |  | 0 |  | 29376550 |  | 43750400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 107199.47 | 393210.9 | -86082379 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.08 |  | 0 |  | 0.39 |  | 0.47 |  | -0.47
| SPARE PARTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 293460.55 | 883701.65 | -1177162 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.2 |  | 0 |  | 0 |  | 0.2 |  | -0.2
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [44 empty] | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT |  | Capital | [50 empty] | 0 |  | 0 |  | 0
[6 empty] | ECT | [52 empty] | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 293460.55 | 883701.65 | -1177162 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.2 |  | 0 |  | 0 |  | 0.2 |  | -0.2
| TOTAL MAJOR EQUIPMENT | [8 empty] | 93330000 |  | 0 |  | 0 |  | 29376550 |  | 43750400 |  | 3107550 |  | 0 |  | 3107250 |  | 6240218.71 |  | 0 | 400660.02 | 1276912.55 | -87259541 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.28 |  | 0 |  | 0.39 |  | 0.67 |  | -0.67
NEPCO SITE CONSTRUCTION COSTS
| CONSTRUCTION DIRECTS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION INDIRECTS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| NEPCO PURCHASED BOP EQUIPMENT |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| START-UP |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LANDSCAPING |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WATER WELLS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SWITCHYARD |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [5 empty] | 0 | [34 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | Nepco |  | Capital | [5 empty] | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNION ADDER/OTHER |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DRY TRANSFORMS AND PANELS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 5KV & 600 V SWITCHGEAR AND MCC'S |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 15 KV SWITCHGEAR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONTROL PANELS/TERMINATION BOXES |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DCS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UPS SYSTEM |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| DC SYSTEM |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD MOUNTED INSTRUMENTS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STACK MONITORING |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONTROL VALVES |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| BRIDGE CRANE |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MINOR MECHANICAL EQUIPMENT |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMBUSTION TURBINE GENERATOR |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRESSURE REDUCING STATION |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WATER WASH SKID |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD/SHOP FAB VESSELS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PUMPS |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0 |  | 0
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 77483.3333 | 77483.33 | -232450 | 77483.34 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.0033333 |  | 0 |  | 0 |  | 0.0033333 |  | -0.0033333
| NEPCO |  |  |  |  | NEPCO |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 236725 | 236725 | -710172 | 236722.33 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0.33 |  | 0 |  | 0 |  | 0.33 |  | -0.33
| BASE FEE |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other -1/2 of redsign costs to change project to Gleason | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 250000 |  | 0 |  | 0 |  | 250000 |  | -250000
0
| TOTAL OVERHEADS & FEES | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 314208.3333 | 314208.33 | -942622 | 314205.67 | 0 | 0 | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 250000.3333 |  | 0 |  | 0 |  | 250000.3333 |  | -250000.3333
ADDERS OUTSIDE EECC SCOPE | [7 empty] | Capital
| PIPING | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ELECTRICAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIVIL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTRUMENTATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ADDERS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CONSTRUCTION
| SITE PREPARATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SITE IMPROVEMENTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNDERGROUND ELECTRICAL (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| UNDERGROUND PIPING (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONCRETE | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GROUT & SPECIAL COATINGS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STRUCTURAL STEEL (LAB & MATL) | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ARCHITECTURAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT ERECTED BUILDINGS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ABOVE GROUND PIPING | [6 empty] | Capital | [52 empty] | 0 |  | 0
| MATERIAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ABOVE GROUND ELECTRICAL | [6 empty] | Capital | [52 empty] | 0 |  | 0
| MATERIAL | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SUBCONTRACT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTRUMENTATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSULATION | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PAINTING | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMBUSTION TURBINE/GENERATOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MAJOR MECHANICAL EQUIPMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SWITCHYARD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL CONSTRUCTION | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
ENGINEERING
| ENGINEERING-DIRECT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING-CONTRACT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EQUIP RENTAL, FUEL, SMALL TOOLS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INDIRECT CONSTRUCTION LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OVERHEAD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GENERAL PROVISIONS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRORATABLE, ALLOWANCES | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STARTUP, TRAINING, MANUALS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION MANAGEMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ENGINEERING | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Reimbursable Cost OEC | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
RESALE HANDLING FEES (.25%) | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
WATER INTERCONNECT | [5 empty] | ECT |  | Capital |  | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SPARE PARTS | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
LAND ACQUISITION
| Land Option |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 | 0 | 0 |  | 0 | 0 | 6000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18000 |  | 0 |  | 0 |  | 18000 |  | -18000
| Title Commitment |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase - Marshall County Rd Pavement, Water Supply to land owners |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | -369041 | 369040.52 | 294743.68 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 294743.2 |  | 0 |  | 0 |  | 294743.2 |  | -294743.2
| Closing Costs |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [44 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 | 0 | 0 | -369041 | 369040.52 | 294743.68 | 6000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 312743.2 |  | 0 |  | 0 |  | 312743.2 |  | -312743.2
ENVIRONMENTAL PERMITTING
| Air Permitting -ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23801.2 |  | 35510.12 | 39859.1 | 0 | -69419 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 29751.42 |  | 0 |  | 0 |  | 29751.42 |  | -29751.42
| Groundwater - ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4183.38 |  | 10970 | 9001.6 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 24154.98 |  | 0 |  | 0 |  | 24154.98 |  | -24154.98
| Groundwater - NS | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 6160.28 |  | 12971 |  | 0 |  | 154424.35 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 173555.63 |  | 0 |  | 0 |  | 173555.63 |  | -173555.63
| Other-NS | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 500 |  | 36910.7 |  | 19390 |  | 6648.63 |  | 44225.2 |  | 0 | 13721.51 | 7968.98 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 129365.02 |  | 0 |  | 0 |  | 129365.02 |  | -129365.02
| Other -ENSR | [6 empty] | Expense |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13095 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13095 |  | 0 |  | 0 |  | 13095 |  | -13095
| Other | [12 empty] | 0 | [14 empty] | 100 |  | 0 | 9500 | [22 empty] | 9600 |  | 0 |  | 0 |  | 9600 |  | -9600
0
| Subtotal Environmental Permitting | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 500 |  | 43070.98 |  | 32361 |  | 6648.63 |  | 239729.13 |  | 46480.12 | 62682.21 | 7968.98 | -69419 | 9500 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 379522.05 |  | 0 |  | 0 |  | 379522.05 |  | -379522.05
ELECTRICAL INTERCONNECTION
| Facilities Study | [5 empty] | Capital |  | 0 |  | 60000 |  | 60000 | 0 |  | 0 |  |  |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 7500 | 0 | -7500
| System Impact Study | [5 empty] | Capital |  | 7500 |  | 27500 |  | 35000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Work Order Cost | [5 empty] | Capital |  | 1992500 |  | 207500 |  | 2200000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[59 empty] | 0 |  | 0
| Subtotal Electrical Interconnection | [7 empty] | 2000000 |  | 295000 |  | 2295000 | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7500 |  | 0 |  | 0 |  | 7500 | 0 | -7500
GAS INTERCONNECTION | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Startup Fuel
| Power Sales | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
INSURANCE DURING CONSTR | [7 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
CAPITALIZED SALARIES | [7 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 4234.96 |  | 20999.1 |  | 10759.47 | 6023.47 | 6145.77 | -48163 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -0.23 |  | 0 |  | 0.23 |  | 0 |  | 0
DEVELOPMENT EXPENSES
| Salaries | [6 empty] | Expense |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 21983.72 |  | 0 |  | 0 |  | 0 |  |  | 0 | 0 | 14449 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 36432.72 |  | 0 |  | 0 |  | 36432.72 |  | -36432.72
| Travel Expenses | [6 empty] | Expense |  | 0 |  | 50000 |  | 0 |  | 0 |  | 135 |  | 2870.91 |  | 7328.25 |  | 2780.87 |  | 15078.35 |  | 11429.61 | 15496.73 | 12735.73 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 67855.45 |  | 0 |  | 0 |  | 67855.45 |  | -67855.45
| Consulting - Calpine | [6 empty] | Expense |  | 0 |  | 24235 |  | 0 |  | 0 |  | 0 |  | 24235 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 48335.34 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 72570.34 |  | 0 |  | 0 |  | 72570.34 |  | -72570.34
| Other | [6 empty] | Expense |  | 400000 |  | -356935 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2287.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10697.29 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12984.79 |  | 0 |  | 0 |  | 12984.79 |  | -12984.79
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [26 empty] | 83611.75 | 49930.8 | 30286.69 | -133542 | [23 empty] | 30287.24 |  |  |  | 0 |  | 30287.24 |  | -30287.24
| TOTAL DEVELOPMENT EXPENSE | [8 empty] | 600000 |  | -282700 |  | 0 | 0 | 0 | 0 | 135 | 0 | 49089.63 | 0 | 7328.25 | 0 | 2780.87 | 0 | 17365.85 | 0 | 95041.36 | 65427.53 | 43022.42 | -70757.66 | 0 | 0 | 10697.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220130.54 | 0 | 0 | 0 | 0 | 0 | 220130.54 | 0 | -220130.54 | 0
LEGAL EXPENSES
| Andrews & Kurth | [6 empty] | Expense |  | 0 |  | 294489 |  | 0 |  | 0 |  | 0 |  | 0 |  | 9963.17 |  | 0 |  | 3785 |  | 0 | 33367.16 | 0 | -14302.18 | 0 | 28608.51 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 61421.66 |  | 0 |  | 0 |  | 61421.66 |  | -61421.66
| Middleton & Reutlinger | [6 empty] | Expense |  | 500000 |  | -310271.2 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 76235.1 |  | 51621.39 |  | 16078.18 | 16050.89 | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 159985.56 |  | 0 |  | 0 |  | 159985.56 |  | -159985.56
| Ogden Newell & Welch | [10 empty] | 5511 |  | 0 | [11 empty] | 5510.85 |  | 10271.2 | [26 empty] | 15782.05 |  | 0 |  | 0 |  | 15782.05 |  | -15782.05
| TOTAL LEGAL EXPENSE | [8 empty] | 500000 | 0 | -10271.2 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 9963.17 |  | 76235.1 |  | 60917.24 |  | 26349.38 | 49418.05 | 0 | -14302.18 | 0 | 28608.51 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 237189.27 |  | 0 |  | 0 |  | 237189.27 |  | -237189.27
INTEREST DURING CONSTRUCTION (6.5%) | [7 empty] | Capital |  | 10922239 |  | 47687 |  | 0 |  | 704264 |  | 320324 |  | 477081 |  | 425796 |  | 378280 |  | 557261 |  | 481371.225 | 488494.4432 | 500068.5242 | -4332940.1924 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT TOTAL Project Costs | [13 empty] | 0 | 0 | 704264 | 0 | 320959 | 0 | 569241.61 | 0 | 475448.42 | 0 | 468179.56 | 0 | 896272.32 | 0 | 666001.555 | 672045.7032 | 557205.6942 | -4904623.0324 | 378540.52 | 323352.19 | 16697.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1149584.83 | 0 | 0 | 0 | 0.23 | 0 | 1149585.06 | 0 | -1149585.06 | 0
CONTINGENCY | [7 empty] | Capital |  | 5395729 |  | 67851 |  | 0 | [40 empty] | 0 | 2030320 | 0 | 2030320 | 0 | 2030320 | 0 | 2030320 | 0
GRAND TOTAL (without Financing Fees & SWAP) | [13 empty] | 0 | 0 | 30080814 | 0 | 44071359 | 0 | 3684291.61 | 0 | 475448.42 | 0 | 3575429.56 | 0 | 7136491.03 | 0 | 666001.555 | 1386914.0565 | 2148326.5742 | -93106786.0324 | 692746.19 | 323352.19 | 16697.29 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407085.4433 | 2030320 | 0 | 2030320 | 0.62 | 2030320 | 1407086.0633 | 2030320 | -1407086.0633
$/Kw | [60 empty] | 596051.1933
INTEREST SWAP | [7 empty] | Capital |  | 0 |  | 44922.91 |  | 0 | [40 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
Payment from AES | [7 empty] | Income | [5 empty] | 0 | [7 empty] | 0 |  | 0 |  | 0 | [28 empty] | -400000 |  | 0 |  | 0 |  | -400000 |  | 400000
Franchise Tax | [25 empty] | 100 | [18 empty] | 100 | [9 empty] | 200 | [5 empty] | 200
Current FIT | [13 empty] | 0 | [9 empty] | -82061 |  | -1963 |  | -32859 | -22657 |  |  | -144358 | -13821 | -99352 | -91244 | [19 empty] | -488315 |  |  |  | 0 |  | -488315 |  | 488315
Grand Total Including SWAP & Financial Fees | [13 empty] | 0 | 0 | 30080814 | 0 | 44071359 | 0 | 3684291.61 | 0 | 475448.42 | 0 | 3493368.56 | 0 | 7134628.03 | 0 | 633142.555 | 1364257.0565 | 2148326.5742 | -93106786.0324 | 548388.19 | 309531.19 | -82654.71 | 158756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 518970.4433 | 2030320 | 0 | 2030320 | 0.62 | 2030320 | 518971.0633 | 2030320 | -518771.0633 | 0
Note on AD195: acopela: Legal Expenses incurred 1998 under the 2000 peaker work order. Reclass to expense 5/99

## Gleason
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [71 empty] | C:\Users\Felienne\Enron\EnronSpreadsheets\[benjamin_rogers__1143__2000 Weekly Report - 112000.xls]Summary
Gleason, TN | [9 empty] | 510 |  | MW | [55 empty] | 2014-09-03 13:19 |  |  |  | Revision # 68
| 509 | [6 empty] | MW |  |  | As of 11/03/00 | [6 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals |  |  |  | Anticipated
Revision # 68 | [7 empty] | Expense / |  | ECT |  | Increase / |  | ECT |  | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  |  | Capital |  | Control Budget |  | (Savings) |  | Current Estimate |  | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 |  | 1999-08-31 |  | Tran.from Calvert |  | 1999-09-30 |  | 1999-10-31 |  | 1999-11-30 |  | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 | 2000-10-31 | 2000-11-30 |  | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[10 empty] | #REF! |  |  |  | as of 7/22/99 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00
MAJOR EQUIPMENT
| TURBINE UNITS, Purchase - WH501FD (2) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 62145000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 56349430 |  | 0 |  | 1282310 |  | 144155 |  | 0 |  | 0 |  | 0 |  | 1240525 |  | 0 |  | 1735000.05 |  | 2658570 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 63409990.05 |  | 370521 |  | 0 |  | 63409990.05 |  | -1264990.05
| TURBINE UNITS, Purchase - WH501F (1) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 31185000 |  | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 0 |  | 0 |  | 29625750 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 29625750 |  | 1464500 |  | 3023750 |  | 32649500 |  | -1464500
| TURBINE UNITS, Disassemble |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE UNITS, Freight Commission |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TURBINE REFURBISHMENT |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 93330000 |  | 0 |  | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 107199 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 767227.2 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 874426.2 |  | 663250 |  | 38823.8 |  | 913250 |  | -663250
[68 empty] | 0 |  |  |  | 0
| Subtotal Westinghouse | [8 empty] | 93330000 |  | 0 |  | 93580000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 86082379 |  | 0 |  | 1282310 |  | 144155 |  | 0 |  | 0 |  | 0 |  | 1240525 |  | 0 |  | 1735000.05 |  | 3425797.2 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 93910166.25 |  | 2498271 |  | 3062573.8 |  | 96972740.05 |  | -3392740.05
| SPARE PARTS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 5885811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 1177162 |  | 0 |  | 0 |  |  |  | 1765743.3 |  | 1765743.3 |  | 0 |  | 588581 |  | 382350 |  | 588581.1 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 6268160.7 |  | 382350 |  | 0.3 |  | 6268161 |  | -382350
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [25 empty] | 58500 | [23 empty] | 58500 |  |  |  | 0 |  | 58500 |  | -58500
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT |  | Capital | [55 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT |  | Capital | [55 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT |  | Capital | [55 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [57 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 8000 |  | 130800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 138800 |  | 0 |  | 0 |  | 138800 |  | -138800
[68 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [8 empty] | 0 |  | 0 |  | 5885811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1177162 |  | 0 |  | 0 |  | 58500 |  | 1773743.3 |  | 1896543.3 |  | 0 |  | 588581 |  | 382350 |  | 588581.1 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 6465460.7 |  | 382350 |  | 0.3 |  | 6465461 |  | -579650
| TOTAL MAJOR EQUIPMENT | [8 empty] | 93330000 |  | 0 |  | 99465811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 87259541 |  | 0 |  | 1282310 |  | 202655 |  | 1773743.3 |  | 1896543.3 |  | 0 |  | 1829106 |  | 382350 |  | 2323581.15 |  | 3425797.2 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 100375626.95 |  | 2880621 |  | 3062574.1 |  | 103438201.05 |  | -3972390.05
NEPCO SITE CONSTRUCTION COSTS
[16 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco |  | Capital | [5 empty] | 1493645 | [25 empty] | 11452 |  |  |  | 93253 |  |  |  | 385983 | [7 empty] | 853496 | [7 empty] | 1344184 |  | 14990 |  | 1497183 |  | 1508635 |  | -14990
| PROJECT MANAGEMENT |  |  |  |  | Nepco |  | Capital | [5 empty] | 1564045 | [25 empty] | 55488 |  |  |  | 64145 |  |  |  | 335055 | [7 empty] | 1143006 | [7 empty] | 1597694 |  | 511673 |  | 2020230 |  | 2075718 |  | -511673
| PROJECT INDIRECTS |  |  |  |  | Nepco |  | Capital | [5 empty] | 11021245 | [25 empty] | 283557 |  |  |  | 1223420 |  |  |  | 945234 | [7 empty] | 1182172 | [7 empty] | 3634383 |  | 792963 |  | 11530651 |  | 11814208 |  | -792963
| ENGINEERING |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 538785 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 58714 |  | 0 |  | 38571 |  | 0 |  | 175343 |  | 0 |  | 0 |  |  |  | 192251 |  | 0 | [5 empty] | 464879 |  | 53684 |  | 533755 |  | 592469 |  | -53684
| FREIGHT |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11607 |  | 0 |  | 65643 |  | 0 |  | -19856 |  | 0 |  | 0 |  |  |  | 80078 |  | 0 | [5 empty] | 137472 |  | 0 |  | 138393 |  | 150000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  | 421112 |  | 421112 |  | 421112 |  | -421112
| RESERVES | [6 empty] | Capital |  | 0 |  | 0 |  | -2832 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  |  |  | 0 |  | 0 |  | -2832
| ENGINEERING REWORK | [46 empty] | 34274 | [7 empty] | 104120 | [7 empty] | 138394 |  | 0 |  | 0 |  | 138394 |  | -138394
| BACKCHARGE | [42 empty] | 19839 |  |  |  | 41626 | [7 empty] | 486561 | [7 empty] | 548026 |  | 0 |  | 0 |  | 548026 |  | -548026
| SITE RELOCATION | [42 empty] | 264288 |  |  |  | 17441 | [15 empty] | 281729 |  | 263743 |  | 0 |  | 281729 |  | -281729
[8 empty] | Capital |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [6 empty] | Capital |  | 0 |  | 0 |  | 14764888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 420818 | 0 | 0 | 0 | 1769159 | 0 | 0 | 0 | 1915100 | 0 | 0 |  | 0 |  | 0 | 0 | 4041684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8146761 | 0 | 2058165 | 0 | 16141324 | 0 | 17530291 |  | -2765403
BOP Procurement
| A/G PIPING |  |  |  |  | Nepco | [7 empty] | 200485 | [29 empty] | 557 |  |  |  | 117284 | [7 empty] | 170703 | [7 empty] | 288544 |  |  |  | 0 |  | 288544 |  | -88059
| A/G ELECTRICAL |  |  |  |  | Nepco | [7 empty] | 3824394 | [25 empty] | 84021 |  |  |  | 224712 |  |  |  | 2585797 | [7 empty] | 309839 | [7 empty] | 3204369 |  | -817725 |  | 0 |  | 3204369 |  | 620025
| INSTRUMENTATION |  |  |  |  | Nepco | [7 empty] | 789260 | [33 empty] | 276231 | [7 empty] | 406763 | [7 empty] | 682994 |  | 0 |  | 106266 |  | 789260 |  | 0
| EQUIPMENT |  |  |  |  | Nepco | [7 empty] | 482700 | [33 empty] | 174035 | [7 empty] | 232229 | [7 empty] | 406264 |  | -40205 |  | 36231 |  | 442495 |  | 40205
| ARCHITECTURAL |  |  |  |  | Nepco | [7 empty] | 0 | [33 empty] | 20223 | [7 empty] | 198 | [7 empty] | 20421 |  | 0 |  | 0 |  | 20421 |  | -20421
| TOTAL BOP Procurement | [6 empty] | Capital |  | 0 |  | 0 |  | 5296839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 84021 | 0 | 0 | 0 | 225269 | 0 | 0 | 0 | 3173570 | 0 | 0 |  | 0 |  | 0 | 0 | 1119732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4602592 | 0 | -857930 | 0 | 142497 | 0 | 4745089 |  | 551750
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [12 empty] | 2221753 | [25 empty] | 204588 |  |  |  | 2184464 |  |  |  | 563778 | [7 empty] | 145962 | [7 empty] | 3098792 |  | 0 |  | 0 |  | 3098792 |  | -877039
| UNDERGROUND ELECTRICAL - L & S | [12 empty] | 363307 | [29 empty] | 13499 |  |  |  | 722445 | [7 empty] | 271577 | [7 empty] | 1007521 |  | 145215 |  | 0 |  | 1007521 |  | -644214
| UNDERGROUND ELECTRICAL - M | [12 empty] | 272375 | [29 empty] | 122734 |  |  |  | 75788 | [7 empty] | 31621 | [7 empty] | 230143 |  |  |  | 42232 |  | 272375 |  | 0
| UNDERGROUND PIPING - L & S | [12 empty] | 294546 | [33 empty] | 555814 | [7 empty] | 43961 | [7 empty] | 599775 |  | 79504 |  | 0 |  | 599775 |  | -305229
| UNDERGROUND PIPING - M | [12 empty] | 172231 | [29 empty] | 116875 |  |  |  | 142469 | [7 empty] | 7097 | [7 empty] | 266441 |  | 0 |  | 0 |  | 266441 |  | -94210
| CONCRETE - L & S | [12 empty] | 1115136 | [29 empty] | 42216 |  |  |  | 1362251 | [7 empty] | 438999 | [7 empty] | 1843466 |  | 454386 |  | 0 |  | 1843466 |  | -728330
| CONCRETE - M | [12 empty] | 751110 | [29 empty] | 286589 |  |  |  | 290830 | [7 empty] | 67931 | [7 empty] | 645350 |  |  |  | 105760 |  | 751110 |  | 0
| GROUT - L | [12 empty] | 79049 | [29 empty] | 0 |  |  |  | 22214 | [7 empty] | 75067 | [7 empty] | 97281 |  | 28959 |  | 10727 |  | 108008 |  | -28959
| GROUT - M | [12 empty] | 43500 | [29 empty] | 11125 |  |  |  | 4722 | [7 empty] | 11747 | [7 empty] | 27594 |  |  |  | 15906 |  | 43500 |  | 0
| STRUCTURAL STEEL - L | [12 empty] | 81956 | [29 empty] | 1183 |  |  |  | 28695 | [7 empty] | 111463 | [7 empty] | 141341 |  | 19844 |  | 0 |  | 141341 |  | -59385
| STRUCTURAL STEEL - M | [12 empty] | 217350 | [41 empty] | 3351 | [7 empty] | 3351 |  |  |  | 213999 |  | 217350 |  | 0
| ARCHITECTURAL -S | [12 empty] | 199748 | [29 empty] | 0 |  |  |  | 9122 | [7 empty] | 648948 | [7 empty] | 658070 |  | 908 |  | 0 |  | 658070 |  | -458322
| BUILDINGS -S | [12 empty] | 390000 | [29 empty] | 11300 |  |  |  | 173150 | [7 empty] | 17845 | [7 empty] | 202295 |  |  |  | 187705 |  | 390000 |  | 0
| A/G PIPING - L & S | [12 empty] | 290544 | [29 empty] | 958 |  |  |  | 20726 | [7 empty] | 245665 | [7 empty] | 267349 |  | 79273 |  | 102468 |  | 369817 |  | -79273
| A/G ELECTRICAL - L & S | [12 empty] | 1025638 | [33 empty] | 148038 | [7 empty] | 2106162 | [7 empty] | 2254200 |  | 862227 |  | 0 |  | 2254200 |  | -1228562
| INSTRUMENTATION - L & S | [12 empty] | 347524 | [41 empty] | 70748 | [7 empty] | 70748 |  | 35207 |  | 311983 |  | 382731 |  | -35207
| INSULATION & PAINTING -S | [12 empty] | 564947 | [33 empty] | 0 | [7 empty] | 664653 | [7 empty] | 664653 |  | 0 |  | 0 |  | 664653 |  | -99706
| MECHANICAL EQUIPMENT - L & S | [12 empty] | 3436815 | [29 empty] | 1953 |  |  |  | 682653 | [7 empty] | 4074370 | [7 empty] | 4758976 |  | 924519 |  | 0 |  | 4758976 |  | -1322161
| PLANT STARTUP - L & S | [12 empty] | 582144 | [33 empty] | 72428 | [7 empty] | 713802 | [7 empty] | 786230 |  | 254077 |  | 49991 |  | 836221 |  | -254077
[68 empty] | 0 |  | 0 |  | 0
| TOTAL Construction | [12 empty] | 12449673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 204588 | 0 | 0 | 0 | 2792896 | 0 | 0 | 0 | 4875123 | 0 | 0 |  | 0 |  | 0 | 0 | 9750969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17623576 | 0 | 2884119 | 0 | 1040771 | 0 | 18664347 | 0 | -6214674
Switchyard
| SWITCHYARD | [12 empty] | 9230000 | [29 empty] | 848349 |  |  |  | 7860529 | [7 empty] | 3473150 | [7 empty] | 12182028 |  | 2906758 |  | 0 |  | 12182028 |  | -2952028
| TOTAL SWITCHYARD | [12 empty] | 9230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 848349 | 0 | 0 | 0 | 7860529 | 0 | 0 |  | 0 |  | 0 | 0 | 3473150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12182028 | 0 | 2906758 | 0 | 0 | 0 | 12182028 |  | -2952028
| Other -1/2 of redsign costs to change project to Gleason | [40 empty] | -250000 | [21 empty] | -250000 |  | 0 |  |  |  | 0 |  | 0
| Nepco % Complete | [12 empty] | 0 | [25 empty] | 5344604.56 |  |  |  | -340467 |  | 6512226 |  | -9645865 |  | 7581129 |  |  |  | 10998139 |  | -17082605 | [7 empty] | 3367161.56 |  | -3361668 |  |  |  | -6136755 |  | 6136755
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [8 empty] | 0 |  | 0 |  | 41741400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6054031.56 | 0 | -250000 | 0 | 5295206 | 0 | 6512226 | 0 | 8178457 | 0 | 7581129 | 0 | 0 | 0 | 10998139 | 0 | 1302930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45672118.56 | 0 | 3629444 | 0 | 1312881.44 | 0 | 46985000 | 0 | -5243600 | 0
[56 empty] | 0 | [7 empty] | 45922118.56 | [5 empty] | 47235000
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 929800 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 232450 |  | 0 |  | 77483.34 |  | 77483.33 |  | 77483.33 |  | 77483.34 |  | 77483.34 |  | 77483.33 |  | 77483 |  | 77483.33 |  | 77483.33 |  | 0 |  | 0 |  | 13837 | 0 | 0 |  | 943636.67 |  | 0 |  | 0 |  | 943636.67 |  | -13836.67
| NEPCO |  |  |  |  | NEPCO |  | Capital |  | 0 |  | 0 |  | 2840700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 710172 |  | 0 |  | 236722.33 |  | 236722.33 |  | 236722 |  | 236722 |  | 236722 |  | 236722 |  | 236722 |  | 236722 |  | 236722 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 2840670.66 |  | -29 |  | 0.34 |  | 2840671 |  | 29
| BASE FEE |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
[8 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL OVERHEADS & FEES | [8 empty] | 0 |  | 0 |  | 3770500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 942622 |  | 0 |  | 314205.67 |  | 314205.66 |  | 314205.33 |  | 314205.34 |  | 314205.34 |  | 314205.33 |  | 314205 |  | 314205.33 |  | 314205.33 |  | 0 |  | 0 |  | 13837 | 0 | 0 |  | 3784307.33 |  | -29 |  | 0.34 |  | 3784307.67 |  | -13807.67
ADDERS OUTSIDE EECC SCOPE | [7 empty] | Capital
| Other |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ADDERS | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
ENGINEERING | [61 empty] | 0
| ENGINEERING-DIRECT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| ENGINEERING-CONTRACT LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EQUIP RENTAL, FUEL, SMALL TOOLS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INDIRECT CONSTRUCTION LABOR | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OVERHEAD | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GENERAL PROVISIONS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PRORATABLE, ALLOWANCES | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| STARTUP, TRAINING, MANUALS | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CONSTRUCTION MANAGEMENT | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL ENGINEERING | [8 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 185000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 185000 |  | 0 |  | 0 |  | 185000 |  | 0
| Reimbursable Costs OEC | [6 empty] | Capital |  | 0 |  | 0 |  | 723786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 111481.55 |  | 138056.89 |  | 122389.86 |  | 120325.41 |  | 112206.42 |  | 187137.03 |  | 106789 | 955 | 0 |  | 899341.16 |  | 0 |  | 0 |  | 899341.16 |  | -175555.16
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [8 empty] | 0 |  | 0 |  | 908786 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 37000 |  | 148481.55 |  | 175056.89 |  | 159389.86 |  | 157325.41 |  | 112206.42 |  | 187137.03 |  | 106789 | 955 | 0 |  | 1084341.16 |  | 0 |  | 0 |  | 1084341.16 |  | -175555.16
Electrical Interconnect - Not TVA | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 80535.78 |  | 10412.63 |  | 12797.63 |  | 8574.66 |  | 0 | 0 | 0 |  | 112320.7 |  | 0 |  | 0 |  | 112320.7 |  | -112320.7
WATER INTERCONNECT | [5 empty] | ECT |  | Capital |  | 400000 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
SALES TAX ON EQUIPMENT & Materials | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 675000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 675000 |  | 675000 |  | 0
SPARE PARTS | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 1247007 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11745 |  | 21965 | 0 | 0 |  | 33710 |  | 0 |  | 0 |  | 33710 |  | 1213297
LAND ACQUISITION | [61 empty] | 0
| Land Option |  |  |  |  | ECT |  | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 25010 |  | 0 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 0 |  | 0 | 0 | 0 |  | 45010 |  | 0 |  | 0 |  | 45010 |  | -45010
| Title Commitment |  |  |  |  | ECT |  | Capital | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT |  | Capital | [5 empty] | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 54315 | 0 | 0 |  | 437856 |  | 54315 |  | 0 |  | 437856 |  | -68815
| Closing Costs |  |  |  |  | ECT |  | Capital | [5 empty] | 0 | [53 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [8 empty] | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 369041 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14500 |  | 25010 |  | 0 |  | 0 |  | 0 |  | 0 |  | 20000 |  | 0 |  | 54315 | 0 | 0 |  | 482866 |  | 54315 |  | 0 |  | 482866 |  | -113825
ENVIRONMENTAL PERMITTING
| Air Permitting -ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 69419 | [19 empty] | 69419 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 69419 |  | 0 |  | 0 |  | 69419 |  | 0
| Groundwater - ENSR | [6 empty] | Expense |  | 0 |  | 0 |  | 0 | [21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [9 empty] | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater - NS | [6 empty] | Expense |  |  |  | 0 |  | 0 | [21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 131064.3 |  | 2040.3 |  | 0 |  | 213078.6 |  | 0 |  | 155653.44 |  | 0 | 0 | 0 |  | 501836.64 |  | 0 |  | 0 |  | 501836.64 |  | -501836.64
| Other-NS | [6 empty] | Expense |  |  |  | 0 |  | 0 | [21 empty] | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 16722.88 |  | 18878 | 0 | 0 |  | 35600.88 |  | 0 |  | 0 |  | 35600.88 |  | -35600.88
| Other -ENSR | [6 empty] | Expense |  |  |  | 0 |  | 0 | [21 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [12 empty] | 470581 | [21 empty] | 190571.4 |  |  |  | 264856.32 |  |  |  | 38191.68 |  | 20091.86 |  | 15594.76 |  |  |  | 49988.37 |  | 30443.56 | [5 empty] | 28889 |  | 0 |  | 638626.95 |  | 0 |  | 0 |  | 638626.95 |  | -168045.95
0
| Subtotal Environmental Permitting | [8 empty] | 0 |  | 0 |  | 540000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 69419 |  | 190571.4 |  | 0 |  | 264856.32 |  | 0 |  | 38191.68 |  | 20091.86 |  | 146659.06 |  | 2040.3 |  | 49988.37 |  | 243522.16 |  | 0 |  | 172376.32 |  | 47767 | 0 | 0 |  | 1245483.47 |  | 0 |  | 0 |  | 1245483.47 |  | -705483.47
0
ELECTRICAL INTERCONNECTION - TVA"S side of fence
| Facilities Study | [5 empty] | Capital |  | 0 |  | 60000 |  | 60000 | 60000 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 7500 |  | 0 |  | 7500 |  | 20486.25 |  | 0 |  | 0 |  |  |  | 110182.74 | [5 empty] | 0 |  |  | 0 |  |  | 145668.99 |  | 0 |  | 225000 |  | 370668.99 |  | -310668.99
| System Impact Study | [5 empty] | Capital |  | 7500 |  | 27500 |  | 35000 | 35000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 10517.87 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10602.45 |  | 37563.52 |  | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 |  | 58683.84 |  | 0 |  | 0 |  | 58683.84 |  | -23683.84
| Johnsonville-Weakly 500-kV TlL--Install Interconnection Facility | [5 empty] | Capital | 44468 | 1992500 |  | 207500 |  | 2200000 | 1604313 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 917527 |  | 0 |  | 0 | [5 empty] | 356422 |  | 0 |  | 1273949 |  |  |  | 330364 |  | 1604313 |  | 0
| Gleason, TN 500 kV Sw Sta--Provide Interconnection | [6 empty] | 43853 | [5 empty] | 756363 | [35 empty] | 351211 | [9 empty] | 413244 |  | 0 |  | 764455 |  |  |  | 0 |  | 764455 |  | -8092
| Gleason Power 1, LLC --Provide Engr/Matl Support | [6 empty] | 60299 | [5 empty] | 21072 | [45 empty] | 12 |  | 0 |  | 12 |  |  |  | 21060 |  | 21072 |  | 0
| Johnsonville FP--Provide Relaying Circuits | [6 empty] | 45630 | [5 empty] | 136716 | [35 empty] | 81598 | [9 empty] | 83542 |  | 0 |  | 165140 |  |  |  | 0 |  | 165140 |  | -28424
| Weakly, TN 500 kV Sub--Install MW Terminal | [6 empty] | 45631 | [5 empty] | 418906 | [35 empty] | 252072 |  | 0 | [7 empty] | 135113 |  | 0 |  | 387185 |  |  |  | 31721 |  | 418906 |  | 0
| Shawnee FP--Provide Channel Interconnections | [6 empty] | 45632 | [5 empty] | 80018 | [35 empty] | 51071 | [9 empty] | 9422 |  | 0 |  | 60493 |  |  |  | 19525 |  | 80018 |  | 0
| S. Nashville, Tn 161 kV Sub --Provide Channel Interconnect | [6 empty] | 45633 | [5 empty] | 50029 | [35 empty] | 37032 | [9 empty] | 4223 |  | 0 |  | 41255 |  |  |  | 8774 |  | 50029 |  | 0
| S Jackson, TN 161 kV Sub--Provide Channel Interconnections | [6 empty] | 45634 | [5 empty] | 61757 | [35 empty] | 31121 | [9 empty] | 33409 |  | 0 |  | 64530 |  |  |  | 0 |  | 64530 |  | -2773
| Wilson HP--Provide Channel Crossconnection | [6 empty] | 45635 | [5 empty] | 21962 | [35 empty] | 2847 | [9 empty] | 3400 |  | 0 |  | 6247 |  |  |  | 15715 |  | 21962 |  | 0
| Jackson, TN 500kV Sub--Install MW Terminal | [6 empty] | 45636 | [5 empty] | 125513 | [35 empty] | 47960 | [9 empty] | 43469 |  | 0 |  | 91429 |  |  |  | 34084 |  | 125513 |  | 0
| Rock Springs MW Rptr Sta--Intall MW Repeater Equipment | [6 empty] | 45637 | [5 empty] | 259130 | [35 empty] | 117954 | [9 empty] | 147961 |  | 0 |  | 265915 |  |  |  | 0 |  | 265915 |  | -6785
| PSCC--Provide SCADA Terminations | [6 empty] | 45638 | [5 empty] | 30502 | [35 empty] | 5812 | [9 empty] | 14739 |  | 0 |  | 20551 |  |  |  | 9951 |  | 30502 |  | 0
| COC/PBS--Provide SCADA Terminations | [6 empty] | 45639 | [5 empty] | 12923 | [35 empty] | 2067 | [9 empty] | 2705 |  | 0 |  | 4772 |  |  |  | 8151 |  | 12923 |  | 0
| Martin, TN 161 kV Sub--Install DTL Mux | [6 empty] | 45642 | [5 empty] | 29543 | [35 empty] | 11684 | [9 empty] | 14895 |  | 0 |  | 26579 |  |  |  | 2964 |  | 29543 |  | 0
| Marshall, KY 500 kV Sub--Install DTL Mux | [6 empty] | 45643 | [5 empty] | 31391 | [35 empty] | 21959 | [9 empty] | 9708 |  | 0 |  | 31667 |  |  |  | 0 |  | 31667 |  | -276
| Lynn Grove MW Rpt Sta--Install DTL Mux | [6 empty] | 45644 | [5 empty] | 22237 | [35 empty] | 14054 | [9 empty] | 4465 |  | 0 |  | 18519 |  |  |  | 3718 |  | 22237 |  | 0
| Estimate | [48 empty] | 837000 |  | 0 | [7 empty] | -777000 | -327840 | 0 |  | -267840 |  |  |  | -837000 |  | -1104840 |  | 1104840
| Plug to get back to budget | [12 empty] | -1557375 | [49 empty] | 0 |  | 1690117 |  | 132742 |  | 132742 |  | -1690117
| Subtotal Electrical Interconnection | [7 empty] | 2000000 |  | 295000 |  | 2295000 | 2200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18017.87 |  | 0 |  | 7500 | 0 | 20486.25 | 0 | 0 | 0 | 10602.45 | 0 | 2820532.52 |  | 110182.74 |  | 0 | 0 | 0 | 0 | 0 | 0 | 499729 | -327840 | 0 | 0 | 3159210.83 | 0 | 1690117 | 0 | 6769 | 0 | 3165979.83 | 0 | -965979.83 | 0
GAS INTERCONNECTION | [5 empty] | ECT |  | Capital |  | 0 |  | 0 |  | 1100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 709845.77 |  | 0 |  | 47034 | 50000 | 12522 |  | 819401.77 |  | 0 |  | 280598.23 |  | 1100000 |  | 0
Startup Fuel * Power
| Power Sales | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost/Power Revenue | [6 empty] | Capital |  | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 457081 |  | 1233742 |  | 0 |  | -592943.08 |  | 0 | 0 | 0 |  | 1097879.92 |  | 0 |  | 0 |  | 1097879.92 |  | -597879.92
| Other | [6 empty] | Capital |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [8 empty] | 0 |  | 0 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 457081 |  | 1233742 |  | 0 |  | -592943.08 |  | 0 | 0 | 0 |  | 1097879.92 |  | 0 |  | 0 |  | 1097879.92 |  | -597879.92
INSURANCE DURING CONSTR | [7 empty] | Capital |  | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 200935.25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 200935.25 |  | 0 |  | 0 |  | 200935.25 |  | -935.25
CAPITALIZED SALARIES | [7 empty] | Capital |  | 0 |  | 0 |  | 200000 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 52170.4 |  | 2851 |  | 0 |  | 0 |  | 0 |  | 1755.4 |  | 28687.68 |  | 12673.78 |  | 13977.09 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 112115.35 |  | -87885 |  | 0 |  | 112115.35 |  | 87884.65
DEVELOPMENT EXPENSES
| Salaries | [6 empty] | Expense |  | 200000 |  | 0 |  | 100000 |  | 0 | [15 empty] | 13179.81 | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 13179.81 |  | -86820 |  | 0.19 |  | 13180 |  | 86820
| Travel Expenses | [6 empty] | Expense |  | 0 |  | 50000 |  | 150000 |  | 0 | [17 empty] | 67146.1 |  | 2410.51 |  | 7333.62 |  | 10298.6 |  | 11236.54 |  | 1851.11 |  | 628.06 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 100904.54 |  | -49095 |  | 0.46 |  | 100905 |  | 49095
| Consulting - Calpine | [6 empty] | Expense |  | 0 |  | 24235 |  | 24235 |  | 0 | [17 empty] | 17043.53 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 17043.53 |  | 0 |  | 0 |  | 17043.53 |  | 7191.47
| Other | [6 empty] | Expense |  | 400000 |  | -356935 |  | 125765 |  | 0 | [15 empty] | 5904 |  | 2286 |  |  |  | 11540.01 |  | 19587.28 |  | 34420.93 |  | 87896.37 |  | 28768.8 |  | 44082.48 |  | 165167.83 |  | 37080.42 |  | 150593.29 |  | 14428.78 |  | 126349.8 |  | 18870 | 3299 | 0 |  | 750274.99 |  | 0 |  | 0 |  | 750274.99 |  | -624509.99
| Enron Generation Comp Costs | [38 empty] | 83333.33 |  | 107679.57 | [21 empty] | 191012.9 |  |  |  | 0 |  | 191012.9 |  | -191012.9
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [32 empty] | 32203.28 | [29 empty] | 32203.28 | [5 empty] | 32203.28 |  | -32203.28
| TOTAL DEVELOPMENT EXPENSE | [8 empty] | 600000 |  | -282700 |  | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19083.81 |  | 118678.91 |  | 2410.51 |  | 18873.63 |  | 113219.21 | 0 | 153337.04 | 0 | 89747.48 | 0 | 29396.86 | 0 | 44082.48 | 0 | 165167.83 |  | 37080.42 |  | 150593.29 | 0 | 14428.78 | 0 | 126349.8 | 0 | 18870 | 3299 | 0 | 0 | 1104619.05 | 0 | -135915 | 0 | 0.65 | 0 | 1104619.7 | 0 | -704619.7 | 0
LEGAL EXPENSES
| Legal | [6 empty] | Expense |  | 0 |  | 294489 |  | 500000 |  | 0 |  | 0 | [15 empty] | 14302.18 |  | 13885.7 |  | 27414.72 |  | 13907.58 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 237555.22 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 307065.4 |  | 0 |  | 192934.6 |  | 500000 |  | 0
| Everest Legal | [6 empty] | Expense |  | 500000 |  | -310271.2 |  | 0 |  | 0 |  | 0 | [17 empty] | 0 |  | 0 |  | 0 |  | 252208.46 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 252208.46 |  |  |  | 0 |  | 252208.46 |  | -252208.46
[12 empty] | 5511 |  | 0 | [49 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [8 empty] | 500000 | 0 | -10271.2 | 0 | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14302.18 |  | 13885.7 |  | 27414.72 |  | 13907.58 |  | 252208.46 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 237555.22 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 559273.86 |  | 0 |  | 192934.6 |  | 752208.46 |  | -252208.46
INTEREST DURING CONSTRUCTION (6.5%) | [7 empty] | Capital |  | 10922239 |  | 47687 |  | 11340044 | [17 empty] | -6078 |  | 4332940 |  | 505668.93 |  | 517447.9227 |  | 557933.4232 |  | 574337.9453 |  | 616751.7969 |  | 657673.0081 |  | 719263.8762 |  | 785204.91 |  | 806550 |  | 590762.3413 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 10658456.1537 |  | 0 |  | 0 |  | 10658456.1537 |  | 681587.8463
ECT TOTAL Project Costs | [13 empty] | 17979878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13005.81 |  | 4956551.49 |  | 715387.54 |  | 563736.2727 |  | 949916.5332 | 0 | 1180818.6953 | 0 | 760946.3569 | 0 | 797859.4081 | 0 | 1071160.7462 | 0 | 1141447.02 |  | 1590625.43 |  | 2623913.0513 | 0 | 869278.6 | 0 | -86760.27 | 0 | 296740 | 54254 | 12522 | 0 | 17511402.6837 | 0 | -169485 | 0 | 1148533.48 | 0 | 18659936.1637 | 0 | -680058.1637 | 0
CONTINGENCY | [7 empty] | Capital |  | 5395729 |  | 67851 |  | 5423498 | [49 empty] | 0 |  | -5423498 | 2030320 | 0 | 2030320 | 0 | 2030320 | 5423498
SWAP | [13 empty] | -6077 | [49 empty] | 0 | [5 empty] | 0 |  | -6077
GRAND TOTAL (without Financing Fees & SWAP) | [13 empty] | 170575010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13005.81 |  | 93158714.49 |  | 715387.54 |  | 2178269.8127 |  | 7520808.7532 | 0 | 3026267.3253 | 0 | 8287387.2469 | 0 | 7624290.7481 | 0 | 11403531.5262 | 0 | 12239663.54 |  | 4338594.65 |  | 17362054.5813 | 0 | 2172208.6 | 0 | -86760.27 | 0 | 810306 | -273586 | 12522 | 0 | 170502666.3537 | 0 | 2607170 | 2030320 | 5530758.36 | 2030320 | 176033424.7137 | 2030320 | -5458414.7137
$/Kw
[60 empty] | Spare Parts | Spare Parts | Spare Parts |  | -33710
[60 empty] | Mobilization | Mobilization | Mobilization |  | -1084341.16
[60 empty] | Sales Tax | Sales Tax | Sales Tax |  | 0
[60 empty] | Expenses | Expenses | Expenses |  | -22627
169361988.1937
[60 empty] | Project Report | Project Report | Project Report |  | 168942454.84
419533.3537
SHELBY
ELECTRICAL INTERCONNECTION - TVA"S side of fence
| Estimate | [48 empty] | 200000 |  | 685000 | [7 empty] | 1018000 | 327840 |  |  | 2230840
| Shelby, TN 500KV SS - Install 500 161 KV Transformer Bank#2 | [6 empty] | 43950 | [5 empty] | 25518545 | [35 empty] | 73057.19 |  | 0 | [7 empty] | 369554 |  |  |  | 442611.19 |  | 0 |  | 25075933.81 |  | 25518545 |  | 0
| Cordova-Shelby 500KV TL Reterminate at Shelby | [6 empty] | 44A26 | [5 empty] | 975356 | [35 empty] | 629 | [9 empty] | 1641 |  |  |  | 2270 |  | 0 |  | 973086 |  | 975356 |  | 0
| Milan -Weakly 161 kV Tl--Upgrade Milan -Rutherford Section | [6 empty] | 44484 | [5 empty] | 132742 | [35 empty] | 24827.2 | [9 empty] | 142809 |  |  |  | 167636.2 |  | 0 |  | 0 |  | 167636.2 |  | -34894.2
[14 empty] | 26626643 | [35 empty] | 298513.39 |  | 685000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1532004 | 327840 | 0 | 0 | 2843357.39 | 0 | 0 | 0 | 26049019.81 | 0 | 26661537.2 | 0 | -34894.2 | 0
*Note: Costs being booked as a receivable, with the receivable being reduced over time equal to the transmission credits used. Ending receivable balance to be repaid by TVA to ENA 2009
Grand Total Including SHELBY | [13 empty] | 197201653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13005.81 | 0 | 93158714.49 | 0 | 715387.54 | 0 | 2178269.8127 | 0 | 7520808.7532 | 0 | 3026267.3253 | 0 | 8287387.2469 | 0 | 7624290.7481 | 0 | 11403531.5262 | 0 | 12538176.93 | 0 | 5023594.65 | 0 | 17362054.5813 | 0 | 2172208.6 | 0 | -86760.27 | 0 | 2342310 | 54254 | 12522 | 0 | 173346023.7437 | 0 | 2607170 | 2030320 | 31579778.17 | 2030320 | 202694961.9137 | 2030320 | -5493308.9137 | 0
[54 empty] | 44W 1070 | [6 empty] | 44W CWIP |  |  | 169342752
[54 empty] | 44W 9310 | [6 empty] | mobilization |  |  | 1084341.16
[54 empty] | IDC | [6 empty] | 44W A/R - shelby |  |  | 2843357.39
[54 empty] | IDC | [6 empty] | Spare Parts |  |  | 33710
[54 empty] | 44W 2360 | [6 empty] | October |  |  | 0
[61 empty] | Capital - 39B |  |  | 6715
[54 empty] | 44W 4092 | [6 empty] | Expense - 413 |  |  | 22627
Current FIT
[54 empty] | Start Up Fuel | [6 empty] | Total |  |  | 173333502.55
Rev accrual
[54 empty] | Legal Reclass | [6 empty] | Per Above |  |  | 173346023.7437
[61 empty] | Difference |  |  | -12521.1937
diff
Note on BU16: aspoede: Claim against Westinghouse for Liquidated damages
Note on BF200: James M. Armstrong:
Note on BL200: tvos: $4578 adjustment to true up CWIP to G/L
Note on BO200: tvos: $4578 adjustment to true up CWIP to G/L
Note on AJ206: James M. Armstrong: Legal exp of $3534 deducted to tie to draw schedule
Note on AT206: James M. Armstrong: Legal exp of $7634 deducted to tie to draw schedule

## Wheatland
ENRON CAPITAL & TRADE RESOURCES
Energy Services | [65 empty] | C:\Users\Felienne\Enron\EnronSpreadsheets\[benjamin_rogers__1143__2000 Weekly Report - 112000.xls]Summary
Wheatland, IN | [7 empty] | 510 |  | MW | [51 empty] | 2014-09-03 13:19 |  |  |  | Revision # 68 |  | Revision # 68
| 470 |  |  |  |  | MW |  |  | As of 11/03/00 | [5 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals |  |  | Anticipated
Revision # 68 | [6 empty] | Expense / | ECT |  | Increase / |  | ECT | Actuals to Date |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | Actuals to Date |  | Increase / |  | ESTIMATE |  | TOTAL
|  | Vendor | Responsibility | Enron Contact | Certainty |  | Capital | Control Budget |  | (Savings) |  | Current Estimate | 1998-12-31 |  | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 |  | 1999-07-31 |  | 1999-08-31 |  | 1999-09-30 |  | 1999-10-31 |  | 1999-11-30 | 1999-12-31 |  | 2000-01-31 |  | 2000-02-29 |  | 2000-03-31 |  | 2000-04-30 |  | 2000-05-31 |  | 2000-06-30 |  | 2000-07-31 |  | 2000-08-31 |  | 2000-09-30 |  | 2000-10-31 | 2000-11-30 | Total Project |  | (Savings) |  | TO COMPLETE |  | PROJECT |  | VARIANCE |  | Comments
[8 empty] | #REF! |  |  |  | as of 7/22/99 | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 |  | As of 11/17/00 | As of 11/17/00 | As of 11/17/00 |  | As of 11/17/00
MAJOR EQUIPMENT
| TURBINE UNITS - WH501D5A (4) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 85821500 | 16673400 |  | 43401650 |  | 4291075 |  |  |  | 4291075 |  | 8582150 |  | 0 |  | 0 |  | 318420.9 |  | 0 |  | 0 |  | 39600 | 1077741.26 |  | 1077741.26 |  | 2155482.52 |  | 0 |  | 0 |  | 0 |  | 3810964.9 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 85719300.84 |  | 397801 |  | 500000.16 |  | 86219301 |  | -397801
| Other |  |  |  |  | ECT | Capital | 93330000 |  | 0 |  | 100000 | [10 empty] | 35517 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 633171 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 668688 |  | 568688 |  | 0 |  | 668688 |  | -568688
0
| Subtotal Westinghouse | [6 empty] | 93330000 |  | 0 |  | 85921500 | 16673400 |  | 43401650 |  | 4291075 |  | 0 |  | 4291075 |  | 8617667 |  | 0 |  | 0 |  | 318420.9 |  | 0 |  | 0 |  | 39600 | 1077741.26 |  | 1077741.26 |  | 2155482.52 |  | 0 |  | 0 |  | 0 |  | 4444135.9 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 86387988.84 |  | 966489 |  | 500000.16 |  | 86887989 |  | -966489
| SPARE PARTS | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMERS (Not included w/TDEC) |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 3949654 | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 197482.7 |  | 350000 |  | 935 |  | 595253.1 |  | 0 | 1190506.2 |  | 1190506.2 |  | 0 |  | 396836 |  | 0 |  | 396835.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 4318354.6 |  | 234200 |  | 0 |  | 4318354.6 |  | -368700.6
| TRANSFORMERS - Other Misc Charges | [10 empty] | 412400 | [14 empty] | 62400 | [5 empty] | 59780 | [8 empty] | 215500 | [15 empty] | 337680 |  | 59780 |  | 134500 |  | 472180 |  | -59780
| ADDITIONAL EVAPORATIVE COOLER |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| ADDITIONAL 5FT STACK HEIGHT |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| WATER WELL |  |  |  |  | ECT | Capital | [50 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| GE CO2 HEATERS |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [45 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
[6 empty] | ECT | [51 empty] | 0 |  |  |  | 0 |  | 0 |  | 0
| AUX TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LOAD CENTER TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TD OF I-ABB |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FREIGHT - TRANSFORMERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TRANSFORMER INSTALLATION |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| OFF LOAD CIRCUIT BREAKERS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MISC TVA REQUIREMENTS |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
[62 empty] | 0 |  | 0 |  | 0
| Subtotal Other Major Equipment | [6 empty] | 0 |  | 0 |  | 4362054 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 259882.7 |  | 350000 |  | 935 |  | 655033.1 |  | 0 | 1190506.2 |  | 1190506.2 |  | 0 |  | 612336 |  | 0 |  | 396835.4 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 4656034.6 |  | 293980 |  | 134500 |  | 4790534.6 |  | -428480.6
| TOTAL MAJOR EQUIPMENT | [6 empty] | 93330000 |  | 0 |  | 90283554 | 16673400 |  | 43401650 |  | 4291075 |  | 0 |  | 4291075 |  | 8617667 |  | 0 |  | 259882.7 |  | 668420.9 |  | 935 |  | 655033.1 |  | 39600 | 2268247.46 |  | 2268247.46 |  | 2155482.52 |  | 612336 |  | 0 |  | 396835.4 |  | 4444135.9 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 91044023.44 |  | 1260469 |  | 634500.16 |  | 91678523.6 |  | -1394969.6
NEPCO SITE CONSTRUCTION COSTS
[13 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
General Provisions
| EQUIPMENT & SMALL TOOL |  |  |  |  | Nepco | Capital |  |  |  |  | 1132854 | [22 empty] | 19960 |  |  | 108633 |  |  |  | 306368 | [15 empty] | 434961 |  | 31436 |  | 729329 |  | 1164290 |  | -31436
| PROJECT MANAGEMENT |  |  |  |  | Nepco | Capital |  |  |  |  | 1580972 | [22 empty] | 87898 |  |  | 334679 |  |  |  | 294464 | [15 empty] | 717041 |  | 422238 |  | 1286169 |  | 2003210 |  | -422238
| PROJECT INDIRECTS |  |  |  |  | Nepco | Capital |  |  |  |  | 8636948 | [22 empty] | 420234 |  |  | 1574879 |  |  |  | 1993776 | [15 empty] | 3988889 |  | 990813 |  | 5638872 |  | 9627761 |  | -990813
| ENGINEERING |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 384721 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 84553 | 0 |  | 95308 |  | 0 |  | 241888 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 421749 |  | 80969 |  | 43941 |  | 465690 |  | -80969
| FREIGHT |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 150000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 14301 | 0 |  | 55823 |  | 0 |  | -36830 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 33294 |  | 0 |  | 116706 |  | 150000 |  | 0
| CONTINGENCY |  |  |  |  | Nepco | Capital | 0 |  | 0 |  | 547484 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | -547484 |  | 0 |  | 0 |  | 547484
| RESERVES | [5 empty] | Capital | 0 |  | 0 |  | -231 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | -485 |  | 0 |  | 0 |  | -231
[7 empty] | Capital | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0
| TOTAL General Provisions | [5 empty] | Capital | 0 |  | 0 |  | 12432748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626946 | 0 | 0 | 2169322 | 0 | 0 | 0 | 2799666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5595934 | 0 | 977487 | 0 | 7815017 | 0 | 13410951 | 0 | -978203
| BOP Procurement | [56 empty] | 0
| A/G PIPING |  |  |  |  | Nepco | [5 empty] | 337160 | [29 empty] | 124742 | [15 empty] | 124742 |  |  |  | 212418 |  | 337160 |  | 0
| A/G ELECTRICAL |  |  |  |  | Nepco | [5 empty] | 3526570 | [22 empty] | 115533 |  |  | 355967 |  |  |  | 653907 | [15 empty] | 1125407 |  | -257957 |  | 2143206 |  | 3268613 |  | 257957
| INSTRUMENTATION |  |  |  |  | Nepco | [5 empty] | 967394 | [29 empty] | 7369 | [15 empty] | 7369 |  | -90000 |  | 870025 |  | 877394 |  | 90000
| EQUIPMENT |  |  |  |  | Nepco | [5 empty] | 577625 | [25 empty] | 3829 |  |  |  | 1124 | [15 empty] | 4953 |  | -111016 |  | 461656 |  | 466609 |  | 111016
| TOTAL BOP Procurement | [5 empty] | Capital | 0 |  | 0 |  | 5408749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115533 | 0 | 0 | 359796 | 0 | 0 | 0 | 787142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1262471 | 0 | -458973 | 0 | 3687305 | 0 | 4949776 | 0 | 458973
Construction
| SITE PREPARATION/IMPROVEMENTS - S | [10 empty] | 1021325 | [25 empty] | 673702 |  |  |  | 34670 | [15 empty] | 708372 |  | 340660 |  | 653613 |  | 1361985 |  | -340660
| SITE PREPARATION/IMPROVEMENTS - M | [36 empty] | 3903 |  |  |  | 52416 | [15 empty] | 56319 | 112638 | 2535 | 227811 | 0 | 455622 | 56319 | 967563 | -56319
| UNDERGROUND ELECTRICAL - L & S | [10 empty] | 520119 | [22 empty] | 3780 |  |  | 267326 |  |  |  | 247709 | [15 empty] | 518815 | 1037630 | 243386 | 2318646 | 244690 | 4881982 | 763505 | 10527469 | -243386
| UNDERGROUND ELECTRICAL - M | [10 empty] | 375128 | [22 empty] | 28611 |  |  | 99328 |  |  |  | 18917 | [15 empty] | 146856 |  |  |  | 228272 |  | 375128 |  | 0
| UNDERGROUND PIPING - L & S | [10 empty] | 460629 | [22 empty] | 3169 |  |  | 202298 |  |  |  | 157353 | [15 empty] | 362820 |  | 217787 |  | 315596 |  | 678416 |  | -217787
| UNDERGROUND PIPING - M | [10 empty] | 193150 | [22 empty] | 17185 |  |  | 84043 |  |  |  | 22208 | [15 empty] | 123436 |  |  |  | 69714 |  | 193150 |  | 0
| CONCRETE - L & S | [10 empty] | 896017 | [22 empty] | 3445 |  |  | 391971 |  |  |  | 401306 | [15 empty] | 796722 |  | 499345 |  | 598640 |  | 1395362 |  | -499345
| CONCRETE - M | [10 empty] | 664866 | [22 empty] | 0 |  |  | 250012 |  |  |  | 270600 | [15 empty] | 520612 |  |  |  | 144254 |  | 664866 |  | 0
| GROUT - L & S | [10 empty] | 94449 | [22 empty] | 0 |  |  | 4537 |  |  |  | 6221 | [15 empty] | 10758 | 21516 | 53806 | 96838 | 137497 | 331173 | 148255 | 810601 | -53806 | 1567396 | 3134792 | 6269584
| GROUT - M | [10 empty] | 46881 | [22 empty] | 0 |  |  | 1645 |  |  |  | 6055 | [15 empty] | 7700 |  |  |  | 39181 |  | 46881 |  | 0
| STRUCTURAL STEEL - L | [10 empty] | 26528 | [22 empty] | 0 |  |  | 182 |  |  |  | 2015 | [15 empty] | 2197 |  | 14632 |  | 38963 |  | 41160 |  | -14632
| STRUCTURAL STEEL - M | [10 empty] | 94700 | [22 empty] | 0 |  |  | 0 |  |  |  | 41858 | [15 empty] | 41858 |  |  |  | 52842 |  | 94700 |  | 0
| ARCHITECTURAL -S | [10 empty] | 70928 | [22 empty] | 0 |  |  | 0 |  |  |  | 6824 | [15 empty] | 6824 |  | 0 |  | 64104 |  | 70928 |  | 0
| BUILDINGS -S | [10 empty] | 625218 | [22 empty] | 0 |  |  | 0 |  |  |  | 130320 | [15 empty] | 130320 |  |  |  | 494898 |  | 625218 |  | 0
| A/G PIPING - L & S | [10 empty] | 351660 | [22 empty] | 0 |  |  | 3409 |  |  |  | 965 | [15 empty] | 4374 |  | 170172 |  | 517458 |  | 521832 |  | -170172
| A/G ELECTRICAL - L & S | [10 empty] | 1672316 | [22 empty] | 0 |  |  | 3559 |  |  |  | 44700 | [15 empty] | 48259 |  | 1021462 |  | 2645519 |  | 2693778 |  | -1021462
| INSTRUMENTATION - L & S | [10 empty] | 373497 | [22 empty] | 308 |  |  | 0 |  |  |  | 14849 | [15 empty] | 15157 |  | 137028 |  | 495368 |  | 510525 |  | -137028
| INSULATION & PAINTING -S | [10 empty] | 587792 | [22 empty] | 0 |  |  | 0 | [19 empty] | 0 |  |  |  | 587792 |  | 587792 |  | 0
| MECHANICAL EQUIPMENT - L & S | [10 empty] | 3449390 | [22 empty] | 4845 |  |  | 123305 |  |  |  | 391129 | [15 empty] | 519279 |  | 816965 |  | 3747076 |  | 4266355 |  | -816965
| PLANT STARTUP - L & S | [10 empty] | 752310 | [22 empty] | 0 |  |  | 544 |  |  |  | 45638 | [15 empty] | 46182 |  | 259495 |  | 965623 |  | 1011805 |  | -259495
| BACKCHARGE | [36 empty] | 3058 |  |  |  | 13969 | [7 empty] | 1534960 | [7 empty] | 1551987 |  | 0 |  | 0 |  | 1551987 |  | -1551987
| TOTAL Construction | [10 empty] | 12276903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61343 | 0 | 0 | 2112822 | 0 | 0 | 0 | 1909722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1534960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5618847 | 1171784 | 3777273 | 2643295 | 12041100 | 5668777 | 17659947 | 12305633 | -5383044 | 1567396
Switchyard
| SWITCHYARD | [10 empty] | 7824800 | [25 empty] | 355795 |  |  |  | 1899850 | [15 empty] | 2255645 |  | 2321129 |  | 7890284 |  | 10145929 |  | -2321129
| TOTAL SWITCHYARD | [10 empty] | 7824800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355795 | 0 | 0 | 0 | 1899850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2255645 | 0 | 2321129 | 0 | 7890284 | 0 | 10145929 | 0 | -2321129
| Backing out Acceleration Scope Change | [36 empty] | -943865 | [19 empty] | -943865 |  |  |  | 0 |  |  |  | 0
| Nepco % Complete | [10 empty] | 0 | [22 empty] | 3651556.55 | 0 |  | 1183570.57 |  | 5993551 |  | 123980 |  | 6627016.5 |  |  |  | 11025293 | [9 empty] | 28604967.62 |  | 2815750 |  | -28798745.55 |  | -2672603 |  | 2672603
| TOTAL NEPCO SITE CONSTRUCTION COSTS | [6 empty] | 0 |  | 0 |  | 37943200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4455378.55 | 0 | 0 | 5237440.57 | 0 | 5993551 | 0 | 7520360 | 0 | 6627016.5 | 0 | 0 | 0 | 11025293 | 0 | 1534960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42393999.62 | 1171784 | 9432666 | 2643295 | 2634960.45 | 5668777 | 43494000 | 12305633 | -5550800 | 1567396
OVERHEADS & FEES
| EE& C |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 929800 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 77483.3333 |  | 77483.33 |  | 77483.33 |  | 77483.33 |  | 77483.34 | 77483.33 |  | 77483.33 |  | 77483.33 |  | 77483.34 |  | 77483 |  | 77483.34 |  | 77483.33 |  | 0 |  | 0 |  | 6741 |  | 0 | 0 | 936540.6633 |  | 0 |  | 0 |  | 936540.6633 |  | -6740.6633
| NEPCO |  |  |  |  | NEPCO | Capital | 0 |  | 0 |  | 2386700 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 198891.6667 |  | 198891.67 |  | 198888.67 |  | 198888.67 |  | 198888.67 | 198899 |  | 198889 |  | 198889 |  | 198889 |  | 198889 |  | 198889 |  | 198889 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 2386682.3467 |  | 0 |  | 17.6533 |  | 2386700 |  | 0
| BASE FEE |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SCHEDULED BONUS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COST SAVINGS |  |  |  |  | EECC | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
[62 empty] | 0 |  |  |  | 0
| TOTAL OVERHEADS & FEES | [6 empty] | 0 |  | 0 |  | 3316500 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 276375 |  | 276375 |  | 276372 |  | 276372 |  | 276372.01 | 276382.33 |  | 276372.33 |  | 276372.33 |  | 276372.34 |  | 276372 |  | 276372.34 |  | 276372.33 |  | 0 |  | 0 |  | 6741 |  | 0 | 0 | 3323223.01 |  | 0 |  | 17.6533 |  | 3323240.6633 |  | -6740.6633
ADDERS OUTSIDE EECC SCOPE | [6 empty] | Capital
| Other |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
0
| TOTAL ADDERS | [6 empty] | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
ECT PROJECT COSTS
MOBILIZATION OF O&M
| Mobilization Fee OEC |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 185000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 37000 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 185000 |  | 0 |  | 0 |  | 185000 |  | 0
| Reimbursble Costs OEC | [5 empty] | Capital | 0 |  | 0 |  | 723786 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 173319.82 |  | 125493.07 |  | 179683.78 |  | 146125.89 |  | 164872.12 |  | 85226.45 |  | 27389 |  | 33049 | 0 | 935159.13 |  | 0 |  | 0 |  | 935159.13 |  | -211373.13
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Mobilization of O&M | [6 empty] | 0 |  | 0 |  | 908786 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 37000 |  | 210319.82 |  | 162493.07 |  | 216683.78 |  | 183125.89 |  | 164872.12 |  | 85226.45 |  | 27389 |  | 33049 | 0 | 1120159.13 |  | 0 |  | 0 |  | 1120159.13 |  | -211373.13
RESALE HANDLING FEES (.25%) | [5 empty] | ECT | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
WATER INTERCONNECT | [5 empty] | ECT | Capital | 400000 |  | 100000 |  | 1500000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 38083.5 | 0 |  | 16047.5 |  | 750 |  | 44229 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 99110 |  | 0 |  | 1400890 |  | 1500000 |  | 0
SALES TAX ON EQUIPMENT | [5 empty] | ECT | Capital | 0 |  | 0 |  | 50000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 13668.55 |  | 0 |  | 0 | 0 | 13668.55 |  | 0 |  | 36331.45 |  | 50000 |  | 0
SPARE PARTS | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1172731 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 35636.88 |  | 6878 |  | 0 | 0 | 42514.88 |  | 0 |  | 0 |  | 42514.88 |  | 1130216.12
LAND ACQUISITION
| Land Option |  |  |  |  | ECT | Capital | 0 |  | 0 |  | 42500 | 0 |  | 0 |  | 15000 |  | 10000 |  | 10000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 1500 |  | 15000 |  | 3220.61 |  | 7500 |  | 5700 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 75420.61 |  | 1000 |  | 0 |  | 75420.61 |  | -32920.61
| Title Commitment |  |  |  |  | ECT | Capital |  |  |  |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Land Purchase |  |  |  |  | ECT | Capital |  |  |  |  | 727500 | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 932284.26 |  | 128659.6 |  | 8500 | 5000 |  | 257825 |  | 501321.1 |  | -25183 |  | 28975 |  | 0 |  | 0 |  | 0 |  | 0 |  | 23213 |  | 230000 | 0 | 2090594.96 |  | 365157 |  | 0 |  | 2090594.96 |  | -1363094.96
| Closing Costs |  |  |  |  | ECT | Capital |  |  |  |  | 0 | [49 empty] | 0 |  | 0 |  | 0
| Subtotal Land Acquisition | [6 empty] | 0 |  | 0 |  | 770000 | 0 |  | 0 |  | 15000 |  | 10000 |  | 10000 |  | 7500 |  | 0 |  | 0 |  | 0 |  | 932284.26 |  | 128659.6 |  | 8500 | 5000 |  | 259325 |  | 516321.1 |  | -21962.39 |  | 36475 |  | 5700 |  | 0 |  | 0 |  | 0 |  | 23213 |  | 230000 | 0 | 2166015.57 |  | 366157 |  | 0 |  | 2166015.57 |  | -1396015.57
ENVIRONMENTAL PERMITTING
| Air Permitting | [5 empty] | Expense | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Groundwater | [5 empty] | Expense | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense |  |  | 0 |  | 450000 | 0 |  | 0 |  | 0 |  | 53840.69 |  | 82339.3 |  | 9930.43 |  | 32110.8 |  | 22234 |  | 64176.31 |  | 27327.91 |  | 8595.51 |  | 47810.12 | 11305.06 |  | 28715.83 |  | 31364.26 |  | 9815.23 |  | 0 |  | 2925.2 |  | 16444.66 |  | 12076.23 |  | 3547.74 |  | 8057 |  |  |  | 472616.28 |  | 0 |  | 0 |  | 472616.28 |  | -22616.28
| Subtotal Environmental Permitting | [6 empty] | 0 |  | 0 |  | 450000 | 0 |  | 0 |  | 0 |  | 53840.69 |  | 82339.3 |  | 9930.43 |  | 32110.8 |  | 22234 |  | 64176.31 |  | 27327.91 |  | 8595.51 |  | 47810.12 | 11305.06 |  | 28715.83 |  | 31364.26 |  | 9815.23 |  | 0 |  | 2925.2 |  | 16444.66 |  | 12076.23 |  | 3547.74 |  | 8057 |  | 0 | 0 | 472616.28 |  | 0 |  | 0 |  | 472616.28 |  | -22616.28
Power INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 5000000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 10000 |  | 0 |  | 0 | 15000 |  | 9120 |  | 0 |  | 0 |  | 0 |  | 0 |  | 20001.05 |  | 297614.54 |  | 53822.2 |  | 19042 |  | 235548 | 5978 | 666125.79 |  | -4000000 |  | 164452 |  | 830577.79 |  | 4169422.21
GAS INTERCONNECTION | [5 empty] | ECT | Capital | 0 |  | 0 |  | 1500000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 946000 |  | 0 |  | 0 |  | 385500 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 1331500 |  | 0 |  | 168500 |  | 1500000 |  | 0
Startup Fuel
| Power Sales | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Fuel Cost | [5 empty] | Capital | 0 |  | 0 |  | 1000000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 141167 |  | 949317.51 |  | -297293.82 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 793190.69 |  | 0 |  | 0 |  | 793190.69 |  | 206809.31
| Other | [5 empty] | Capital | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Subtotal Net Startup Fuel | [6 empty] | 0 |  | 0 |  | 1000000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 141167 |  | 949317.51 |  | -297293.82 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 793190.69 |  | 0 |  | 0 |  | 793190.69 |  | 206809.31
INSURANCE DURING CONSTR | [6 empty] | Capital | 0 |  | 0 |  | 200000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 175875 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 175875 |  | 0 |  | 0 |  | 175875 |  | 24125
CAPITALIZED SALARIES | [6 empty] | Capital | 0 |  | 0 |  | 200000 | 0 |  | 0 |  |  |  | 0 |  | 3670.07 |  | 22738 |  | 14946.71 |  | 7606.71 |  | 10911.6 |  | 18233.16 |  | 0 |  | 0 | 0 |  | 1468.85 |  | 24646.4 |  | 11209.91 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 115431.41 |  | -84569 |  | 0 |  | 115431.41 |  | 84568.59
DEVELOPMENT EXPENSES
| Salaries | [5 empty] | Expense | 200000 |  | 0 |  | 30000 | 0 |  | 0 |  | 14497.18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 14497.18 |  | 0 |  | 0 |  | 14497.18 |  | 15502.82
| Travel Expenses | [5 empty] | Expense | 0 |  | 50000 |  | 150000 | 0 |  | 1177.53 |  | 426.75 |  | 2729.26 |  | 1480.06 |  | 2752.75 |  | 11808.68 |  | 12739.96 |  | 11636.6 |  | 3911.51 |  | 3113.56 |  | 7537.43 | 3430.47 |  | 6123.69 |  | 1927.44 |  | 5311.06 |  | 0 |  | 931.37 |  | 0 |  | 0 |  | 0 |  | 2125 |  |  |  | 79163.12 |  | 0 |  | 0 |  | 79163.12 |  | 70836.88
| Consulting - Calpine | [5 empty] | Expense | 0 |  | 24235 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Other | [5 empty] | Expense | 400000 |  | -356935 |  | 220000 | 0 |  | 0 | [7 empty] | 2287.5 |  | 7317.49 |  | 20400 |  | 875 |  | 26869.6 |  | 11540.02 |  | 22846.65 | 28124.79 |  | 28858.74 |  | 29874.24 |  | 47425 |  | 64331 |  | 39287.61 |  | 110237.73 |  | 13668.55 |  | 57977.26 |  | 42238 |  | 5165 | 0 | 559324.18 |  | 0 |  | 0 |  | 559324.18 |  | -339324.18
| Enron Generation Comp Costs | [33 empty] | 83333.35 | 111707.46 | [21 empty] | 195040.81 |  | 0 |  | 0 |  | 195040.81 |  | -195040.81
| EECC cost incurred prior to 6/1/99 (includes Capital & Exp) | [23 empty] | 75487.01 |  | 65146.92 |  | 18599.24 | [10 empty] | 9122.91 | [17 empty] | 168356.08 |  | 159233 |  | 0 |  | 168356.08 |  | -168356.08
| TOTAL DEVELOPMENT EXPENSE | [6 empty] | 600000 |  | -282700 |  | 400000 | 0 | 0 | 1177.53 | 0 | 14923.93 | 0 | 2729.26 | 0 | 1480.06 | 0 | 5040.25 | 0 | 94613.18 | 0 | 98286.88 | 0 | 31110.84 | 0 | 30781.11 | 0 | 14653.58 | 0 | 113717.43 | 143262.72 | 0 | 34982.43 | 0 | 40924.59 | 0 | 52736.06 | 0 | 64331 | 0 | 40218.98 | 0 | 110237.73 | 0 | 13668.55 | 0 | 57977.26 | 0 | 44363 | 0 | 5165 | 0 | 1016381.37 | 0 | 159233 | 0 | 0 | 0 | 1016381.37 | 0 | -616381.37
LEGAL EXPENSES
| Vinson & Elkins | [5 empty] | Expense | 0 |  | 294489 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Everest Legal | [10 empty] | 0 | [23 empty] | 252208.46 |  | 49463.67 | [19 empty] | 301672.13 |  | 0 |  | 0 |  | 301672.13 |  | -301672.13
| Other | [5 empty] | Expense | 500000 |  | -300000 |  | 400000 | 0 |  | 0 |  | 0 | [7 empty] | 0 |  | 15169.98 |  | 0 |  | 29399.49 |  | 20442.9 |  | 10582.42 | 68346.51 |  | 5360.34 |  | 13664.6 |  | 7710.95 |  | 20000 |  | 2287.5 |  | 119117.21 |  | 0 |  | 0 |  | 41481 |  | 4040 | 0 | 357602.9 |  |  |  | 42397.1 |  | 400000 |  | 0
[10 empty] | 5511 | [47 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0
| TOTAL LEGAL EXPENSE | [6 empty] | 500000 | 0 | 0 | 0 | 400000 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 15169.98 |  | 0 |  | 29399.49 |  | 20442.9 |  | 10582.42 | 320554.97 |  | 54824.01 |  | 13664.6 |  | 7710.95 |  | 20000 |  | 2287.5 |  | 119117.21 |  | 0 |  | 0 |  | 41481 |  | 4040 | 0 | 659275.03 |  | 0 |  | 42397.1 |  | 701672.13 |  | -301672.13
INTEREST DURING CONSTRUCTION (6.5%) | [6 empty] | Capital | 10922239 |  | 47687 |  | 10032325 | 413818 |  | 239841 |  | 375473 |  | 374160 |  | 374175 |  | 473740 |  | 431577.4186 |  | 437225.4821 |  | 445286.6764 |  | 454783 |  | 462626.3155 |  | 491955.341 | 516340 |  | 563836.3251 |  | 615994.8583 |  | 668433.2002 |  | 710982 |  | 720582.0299 |  | 229734.4232 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 9000564.0703 |  | -984592 |  |  |  | 9000564.0703 |  | 1031760.9297
ECT TOTAL Project Costs | [11 empty] | 23583842 | 413818 | 0 | 241018.53 | 0 | 405396.93 | 0 | 440729.95 | 0 | 471664.43 | 0 | 518948.68 | 0 | 573248.1086 | 0 | 580523.0521 | 0 | 551485.4264 | 0 | 1502808.93 | 0 | 634977.9055 | 0 | 710648.811 | 2133337.75 | 0 | 968319.9451 | 0 | 1280665.8083 | 0 | 1367991.7802 | 0 | 1135448.07 | 0 | 1937714.9999 | 0 | 381367.1432 | 0 | 488231.44 | 0 | 249879.08 | 0 | 170423 | 0 | 507802 | 5978 | 17672427.7703 | 0 | -4543771 | 0 | 1812570.55 | 0 | 19484998.3203 | 0 | 4098843.6797 | 0
CONTINGENCY | [6 empty] | Capital | 5395729 |  | 67851 |  | 3324152.1 | [46 empty] | 2030320 | -3324152 | 2030320 | 0.1 | 2030320 | 0.1 | 2030320 | 3324152
GRAND TOTAL (without Financing Fees & SWAP) | [11 empty] | 158451248.1 | 17087218 | 0 | 43642668.53 | 0 | 4696471.93 | 0 | 440729.95 | 0 | 4762739.43 | 0 | 9136615.68 | 0 | 573248.1086 | 0 | 1116780.7521 | 0 | 1496281.3264 | 0 | 1780115.93 | 0 | 1566383.0055 | 0 | 5481999.371 | 4677967.54 | 0 | 8750380.3051 | 0 | 9706071.6583 | 0 | 9777060.1202 | 0 | 8038836.57 | 0 | 2610922.7399 | 0 | 16127168.3732 | 0 | 2023191.44 | 0 | 249879.08 | 0 | 177164 | 0 | 507802 | 5978 | 154433673.8403 | 3202104 | 2825212 | 4673615 | 5082048.9133 | 7699097 | 157980762.6836 | 14335953 | 470485.4164
$/Kw | [63 empty] | 336129.2823
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -35636.88 |  |  |  | Spare Parts | Spare Parts | -42514.88
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -37000 | 0 | -210319.82 | 0 | -162493.07 | 0 | -216683.78 | 0 | -183125.89 | 0 | -164872.12 | 0 | -85226.45 |  |  |  | Mobilization | Mobilization | -1120159.13
[56 empty] | Sales Tax | Sales Tax | -13668.55
[48 empty] | -300697 | [7 empty] | Expenses | Expenses | -300697
[13 empty] | 17087218 | 0 | 43642668.53 | 0 | 4696471.93 | 0 | 440729.95 | 0 | 4762739.43 | 0 | 9136615.68 | 0 | 573248.1086 | 0 | 1116780.7521 | 0 | 1496281.3264 | 0 | 1780115.93 | 0 | 1566383.0055 | 0 | 5481999.371 | 4677967.54 | 0 | 8750380.3051 | 0 | 9669071.6583 | 0 | 9566740.3002 | 0 | 7876343.5 | 0 | 2394238.9599 | 0 | 15643345.4832 | 0 | 1858319.32 | 0 | 129015.75 | [5 empty] | 152956634.2803
150359339.7603
[56 empty] | Project Report | Project Report | 152971635
[48 empty] | 150359340.02 | [9 empty] | -15000.7197
-0.2597
Note on BT12: aspoede: Claim against WH for Liquidated damages