## Project Scope
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
|  | CUSTOMER COMPANY NAME: | Houston Pipe Line Co.
|  | PROJECT NAME: | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  | W.O. NUMBER: | estimate
|  | PROJECT ENGINEER: | Reid Hansen |  |  | File Name: GasSolutions
REVISION NUMBER:
PROJECT SCOPE
HPL SCOPE:
1. HPL shall provide, install, retain ownership, maintain & operate communication package to Producers measurement
equipment & EFM.
2. HPL shall receive documetatation provided by Producer to support material & method of construction for piping changes
for Producer to install a 3" 600# senior orifice meter to deliver appx. 5.0MM/D of pipeline quality gas into the HPL Texoma
30" line (3018) at station 9761+66 in Gregg County, TX..
3. HPL shall witness calibration of measurement equipment.
PRODUCER SCOPE:
1. Provide material, labor & equipment to install piping changes for a 3" orifice fitting, EFM w/ Enron compatible software &
SCADA capabilities, sampler & control valve (set @ 811) for OPP to deliver to HPL, Texoma 30" line (3080) at station
9761+66 in Gregg County, TX..
2. All piping, meter, equipment & downstream piping shall be constructed & installed w/ documentation to support material
& method of construction according to Enron Engineering Standards & Specifications prior to delivery.
3. Provide & install dehydration & separator w/ high liquid level monitor & shut-down device w/ associated piping & storage to
operate this process.
4. Producer shall operate, maintain & retain ownership of meter facility & downstream piping to the inlet of the HPL tap & be
responsible for all costs & liabilities asociated with operating this equipment.
5. Producer shall provide an all weather road w/ right to HPL to ingress / egress meter facility w/ fence to prevent cattle or
vandals from damaging meter piping & equipment.
Meter No.: | 98-____ (NEW) |  | Region: |  | HOUSTON |  | County: | GREGG COUNTY, TX.
Volume: | 5.0 MM/D |  | Area: |  | LUMBERTON |  | System: | 765 TEXOMA PIPELINE
Pressure: | 750 |  | Field: |  |  |  | P.O.I. Type: | GPO
Line No.: | 3080 |  | Station: |  | 9761+66 |  | Align. Drwg.: | HC-3080-31-H
|  |  | Zip Code: |  | 77562 |  | Survey: | SS DAVIS SURVEY A-59
Note: This estimate is good for 90 days.
Estimate does not include income tax gross

## Notes
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
|  | CUSTOMER COMPANY NAME: |  | Houston Pipe Line Co.
|  | PROJECT NAME: |  | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  | W.O. NUMBER: |  | estimate
|  | PROJECT ENGINEER: |  | Reid Hansen |  | File Name: GasSolutions
REVISION NUMBER:
NOTES & ASSUMPTIONS
ASSUMPTIONS
(A) Gas will be pipeline quality & not require analyzers.
NOTES
(N) Flow estimated at 5.0 MM/D (max) @ 750#
(N) 30" Texoma (3080)
| Pipe data: |  | 30" x .312, X65
Hydrotest:
| MAOP (design): |  | 811
| Pipeline pressure during Hot-tap |  | 551 | (Class 2 or 3 location)
|  |  | 661 | (Class 1 location)
(A) - Assumption
(N) - Note

## M&E Costs
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE ANALYSIS
2014-09-03
|  |  | CUSTOMER COMPANY NAME: | Houston Pipe Line Co.
|  |  | PROJECT NAME: | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  |  | W.O. NUMBER: | estimate
|  |  | PROJECT ENGINEER: | Reid Hansen |  |  | File Name: GasSolutions
REVISION NUMBER:
MATERIAL AND EQUIPMENT COSTS
PROPERTY UNIT | DESCRIPTION |  |  | EST. QUANITY | UNIT of MEASURE | W.O.A. PER UNIT COST (TAP&RISER) | W.O.A. COST ESTIMATE (METER) | W.O.A. COST ESTIMATE (TOTAL)
53400 | COMM. PKG.: MDS-9810 w/ tower, base & antena |  |  | 1 | Lot |  | 4750 | 4750
90500 | Miscellaneous |  |  | 1 | Lot |  | 200 | 200
.
MATERIAL TOTALS | [5 empty] | 0 | 4950 | 4950
90400 | FREIGHT (4.50% of materials) |  |  |  |  | 0 | 222.75 | 222.75
90300 | TAX (8.25% of materials) |  |  |  |  | 0 | 408.375 | 408.375
MATL. & EQUIP. SUB-TOTAL | [5 empty] | 0 | 5581.125 | 5581.125

## FD Costs
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
|  |  | CUSTOMER COMPANY NAME: |  | Houston Pipe Line Co.
|  |  | PROJECT NAME: |  | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  |  | W.O. NUMBER: |  | estimate
|  |  | PROJECT ENGINEER: |  | Reid Hansen |  |  | File Name: GasSolutions
REVISION NUMBER:
FIELD DIRECT COSTS
DESCRIPTION |  |  |  | EST. QTY. | EST. UNIT | W.O.A. UNIT COST | W.O.A COST ESTIMATE (TAP & RISER) | W.O.A. COST ESTIMATE (METER) | W.O.A. COST ESTIMATE (TOTAL)
CONSTRUCTION SUPPORT:
| SURVEY (Preliminary and As-Built) |  |  |  | Day | 750 | 0 | 0 | 0
FIELD INSPECTION :
|  | - Construction - 1 Chief Insp. |  |  | Days | 330 | 0 | 0 | 0
|  | - Construction - 1 Craft Insp. |  |  | Days | 295 | 0 | 0 | 0
|  | - Contruction Management |  |  | Days | 480 | 0 | 0 | 0
| X-RAY |  |  |  | Days | 550 | 0 | 0 | 0
| VACUM TRUCK SERVICE |  |  |  | Hours | 40 | 0 | 0 | 0
| HOT-TAP SERVICE |  |  |  | Lot | 875 | 0
CONSTR. SUPPORT TOTAL | [6 empty] | 0 | 0 | 0
CONTRACT INSTALLATION:
LABOR: Install site w/ culvert, tap, meter & fence
|  | Welder w/ rig |  |  | Hrs. | 42 | 0 |  | 0
|  | Wldr. Helper |  |  | Hrs. | 15 | 0 |  | 0
|  | Foreman |  | 10 | Hrs. | 18 |  | 180 | 180
|  | Laborer (2) |  | 20 | Hrs. | 16 |  | 320 | 320
EQUIPMENT: Prepare site & handle material
|  | R/T hoe w/ truck, trailer & operator |  |  | Hrs. | 65 | 0 | 0 | 0
|  | Crew Truck w/ tools |  | 10 | Hrs. | 17 |  | 170 | 170
|  | Foremans Truck |  |  | Hrs. | 15 | 0 | 0 | 0
| Instalation: Insturment / Electrical |  |  |  | Lot | 1500 |  | 0 | 0
| Transportation |  |  |  | Lot | 700 | 0 | 0 | 0
SITE PREPERATION
|  | Fence |  |  | Lot | 500 | 0 | 0 | 0
CONTRACT INSTALL. TOTAL | [6 empty] | 0 | 670 | 670
FIELD DIRECT COSTS SUB-TOTAL | [6 empty] | 0 | 670 | 670
TOTAL INSTALLED COST (Labor + Materials) | [6 empty] | 5581.125 | 670 | 6251.125

## PS Costs
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
|  | CUSTOMER COMPANY NAME: |  | Houston Pipe Line Co.
|  | PROJECT NAME: |  | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  | W.O. NUMBER: |  | estimate
|  | PROJECT ENGINEER: |  | Reid Hansen |  |  | File Name: GasSolutions
REVISION NUMBER:
PROJECT SUPPORT COSTS
DESCRIPTION |  |  | EST. QTY. | EST. UNIT | W.O.A. UNIT COST | W.O.A. COST ESTIMATE TAP&RISER | W.O.A. COST ESTIMATE (METER) | W.O.A. COST ESTIMATE (TOTAL) | PROPERTY UNIT
ENVIRONMENTAL:
| Asbestos abatement |  |  | Lot | 750 | 0 | 0 | 0
| Permitting |  |  | Lot | 750 | 0 | 0 | 0 | 50540
ENVIRON. TOTAL | [5 empty] | 0 | 0 | 0
RIGHT OF WAY:
| ROW Direct Salaries |  |  | Days | 350 | 0 | 0 | 0 | 90100
| ROW Esmnt. Acquisition/Damages |  |  | Lot | 1000 | 0 | 0 | 0 | 90100
| ROW Review Charges |  |  | Lot | 350 | 0 | 0 | 0 | 90100
| ROW, Landman |  |  | Days | 350 | 0 | 0 | 0 | 90000
ROW TOTAL | [5 empty] | 0 | 0 | 0
COMPANY:
| DISTRICT LABOR |  | 20 | Hrs. | 35 |  |  | 700 | 90100
| ENGINEERING - COMPANY |  | 1 | Day | 400 |  |  | 400 | 90100
ENGINEERING - COMPANY
| Drafting & alignment sheets |  |  | Day | 400 | 0 | 0 | 0 | 90000
COMPANY TOTALS | [5 empty] | 0 | 0 | 1100
GAS LOSS (Blowdown & Purge) |  |  |  | Lp Sum | 0 | 0 | 0 | 0 | 32500
PROJECT SUPPORT COSTS SUB-TOTAL | [5 empty] | 0 | 0 | 1100
TOTAL ESTIMATED COST (without mark-up) | [5 empty] | 0 | 6251.125 | 7351.125
Income Tax Gross-up (25%) | [5 empty] | 0 | 1562.7812 | 1837.7812
As-Built Package (2.0%) | [5 empty] | 0 | 125.0225 | 147.0225 | 90200
AFUDC (6.5% per year, for 90 days) | [5 empty] | 0 | 100.1893 | 117.8194 | 99300
Overhead (13.0% HPL & 1.0% NNG) | [5 empty] | 0 | 875.1575 | 1029.1575 | 99000
TOTAL ESTIMATED COST | [5 empty] | 0 | 8914.2755 | 10482.9057

## Risk Factors
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
| CUSTOMER COMPANY NAME: | Houston Pipe Line Co.
| PROJECT NAME: | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
| W.O. NUMBER: | estimate
| PROJECT ENGINEER: | Reid Hansen |  | File Name: GasSolutions
REVISION NUMBER:
RISK FACTORS
Terms & conditions for ingress / egrss to ROW.

## Contact List
EOC HOUSTON TECHNICAL SERVICES
PROJECT COST ESTIMATE
2014-09-03
|  | CUSTOMER COMPANY NAME: |  | Houston Pipe Line Co.
|  | PROJECT NAME: |  | Gas Solutions Longview Plant: delivery meter addition to Texoma 30"
line (3080) at station 9761+66 in Gregg County, TX.
|  | W.O. NUMBER: |  | estimate
|  | PROJECT ENGINEER: |  | Reid Hansen |  |  | File Name: GasSolutions
REVISION NUMBER:
PROJECT CONTACT LIST
[6 empty] | Office |  | Pager | Mobile
| Reid Hansen |  | GCO Project Engineer |  |  | (713)853-7540 |  | 800-504-0913
| Don Thomas |  | GCO Construction Manager |  |  | (713) 853-5581 |  | (281) 490-6549 | (713) 818-4075
| Charlie Thompson |  | EOC Tech Ops Director |  |  | (713) 685-4201 |  | 800-501-5722 | (713) 818-8314
| Kevin Kuehler |  | GCO E&C Director |  |  | (713) 853-9319 |  | 800-980-6628
PIN 096-8634
| Ty Porche |  | Construction Coordinator |  |  | 361/698-4354 |  | 361/788-1635 | 713/805-1781
| T. A. Mills |  | Lumberton Team - W C Contact |  |  | 281/652-2562 |  | 409/755-9433 | 409/656-4467
| James McKay |  | ECT Gas Control |  |  | 713/ 853-6448 |  | (800) 716-7133 | (713) 202-7839
| John Towles |  | Right of Way |  |  | 713/ 646-7244
| Brad Blevins |  | ECT Facility Planning |  |  | 713/ 853-6508
| Robert Morgan |  | ECT Facility Planning |  |  | 713/853-7406
| Chris Sonnebom |  | ECT Facility Planning |  |  | 713/853-6530