## Accelerated
Nicor
Deal Closing Schedule - Accelerated Case
2014-09-03
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
| 11/05 - 11/09 | 11/12 - 11/16 | 11/19 - 11/23 | 11/26 - 11/30 | 12/03 - 12/07 | 12/10 - 12/14 | 12/17 - 12/21 | 12/24 - 12/28 | 12/31 - 1/04 | 1/07 - 1/11 | 1/14 - 1/18 | 1/21 - 1/25 | 1/28 - 2/1 | 2/4 - 2/8 | 2/11 - 2/15 | 2/18 - 2/22 | 2/25 - 3/1
Thanksgiving Week
Executed Letter Of Intent
Documents
Power Contract (Firm/Optional)
Utility Contract Negotiations (Illinois Power)
Equipment Contract Negotiations
O&M Contract Negotiations
Project Financing Negotiations
Deal Approval
Financier Deal Approval Process
Nicor Deal Approval Process
Enron Deal Approval Process
Closing
Comments

## Expected
Nicor
Deal Closing Schedule - Expected Case
2014-09-03
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17
| 11/05 - 11/09 | 11/12 - 11/16 | 11/19 - 11/23 | 11/26 - 11/30 | 12/03 - 12/07 | 12/10 - 12/14 | 12/17 - 12/21 | 12/24 - 12/28 | 12/31 - 1/04 | 1/07 - 1/11 | 1/14 - 1/18 | 1/21 - 1/25 | 1/28 - 2/1 | 2/4 - 2/8 | 2/11 - 2/15 | 2/18 - 2/22 | 2/25 - 3/1
|  |  | Thanksgiving Week |  |  |  |  | Christmas Week | New Year's Week
Executed Letter Of Interest
Executed Letter of Intent
Documents
Power Contract (Firm/Optional)
Utility Contract Negotiations (Illinois Power)
Equipment Contract Negotiations
O&M Contract Negotiations
Project Financing Negotiations
Deal Approval
Financier Deal Approval Process
Nicor Deal Approval Process
Enron Deal Approval Process
Closing
Comments