## Assumptions
Enron Corp |  |  | Standard Estimate Report | Page 9
|  |  | Topock Lateral Expansion Tie-in, Loop, and River Crossing | 10/05/2001
ASSUMPTIONS:
| 1. | No Selexol plant expansion included in this estimate. Assumption made expansion volumes would by-pass Selexol plant.
| 2. | No extra right of way costs to deal with Native Americans other than the normal.
| 3. | No tax gross up included.
| 4. | Expansion good for 300 MMcf/d ONLY. No room to expand behind 300 MMcf/d without major costs.
| 5. | The cost estimate has a + 30% variance and the numbers given are in the middle of the range.
| 6. | No cost allowance in the for any other expansions to get gas to the Topock lateral.

## Tie In, Loop, & River X-in
Enron Corp |  |  |  | Standard Estimate Report |  | Page 9
|  |  |  | Topock Lateral Expansion Tie-in, Loop, and River Crossing |  | 10/05/2001
Estimate Totals
|  | Labor | 2778310
|  | Materials | 2240746
|  |  | 5019056 | 5019056
|  | Freight (%) | 112037.3 |  | 5%
|  |  | 112037.3 | 5131093.3
|  | Tax (%) | 168055.95 | 5299149.25 | 7.5%
|  | Colorado River X-ing (LS) | 5000000
|  |  | 5000000 | 10299149.25
|  | Pipeline Right of Way (LS) | 588800
|  | Environmental (LS) | 100000
|  |  | 688800 | 10987949.25
|  | CSUP - Survey (LS) | 200000
|  | CSUP - Inspection (LS) | 100000
|  |  | 300000 | 11287949.25
|  | DLAB - District Labor (LS) | 30000
|  |  | 30000 | 11317949.25
|  | Engineering - Enron (LS) | 170000
|  | Engineering - Contract (LS) | 80000
|  | Engineering - AsBuiltDwg (LS) | 11000 |  | 1.4%
|  |  | 261000 | 11578949.25
|  | PROJECT MANAGEMENT (LS) | 48000
|  |  | 48000 | 11626949.25
|  | CONTINGENCY (%) | 1162694.925 |  | 10%
|  |  | 1162694.925 | 12789644.175
|  | OVERHEAD (%) | 1278964.4175 |  | 10%
|  |  | 1278964.4175 | 14068608.5925
|  | AFUDC (% of Current Total) | 562744.3437 |  | 4%
|  |  | 562744.3437 | 14631352.9362
|  | GROSS RECEIPTS (%) | 156852.22 | 14788205.1562 | 7%
|  | ESCALATION (2002) (%) | 67222.38 | 14855427.5362 | 3%
|  |  | Total | 14855427.5362
Note: This is a + 30% cost estimate.

## Measurement Facilities Only
Enron Corp |  |  |  | Standard Estimate Report |  | Page 9
|  |  |  | Topock Lateral Expansion Measurment Facilities Only |  | 10/05/2001
Estimate Totals
|  | Labor | 70655
|  | Materials | 259387
|  | Subcontract | 1817
|  |  | 331859 | 331859
|  | Freight (%) | 12969.35 |  | 5%
|  |  | 12969.35 | 344828.35
|  | Tax (%) | 19454.025 | 364282.375 | 7.5%
|  | Pipeline Right of Way (LS) | 2500
|  | Environmental (LS) | 500
|  |  | 3000 | 367282.375
|  | CSUP - Survey (LS) | 2000
|  | CSUP - Inspection (LS) | 1500
|  |  | 3500 | 370782.375
|  | DLAB - District Labor (LS) | 2500
|  |  | 2500 | 373282.375
|  | Engineering - Enron (LS) | 5000
|  | Engineering - Contract (LS) | 2500
|  | Engineering - AsBuiltDwg (LS) | 500 |  | 1.4%
|  |  | 8000 | 381282.375
|  | PROJECT MANAGEMENT (LS) | 1100
|  |  | 1100 | 382382.375
|  | CONTINGENCY (%) | 38238.2375 |  | 10%
|  |  | 38238.2375 | 420620.6125
|  | OVERHEAD (%) | 42062.0612 |  | 10%
|  |  | 42062.0612 | 462682.6737
|  | AFUDC (% of Current Total) | 18507.3069 |  | 4%
|  |  | 18507.3069 | 481189.9807
|  | GROSS RECEIPTS (%) | 18157.09 | 499347.0707 | 7%
|  | ESCALATION (2002) (%) | 7781.61 |  | 3%
|  |  | 7781.61 | 507128.6807
|  |  | Total | 507128.6807
Note: This is a + 30% cost estimate.