## Turbine Inventory
MASTER TURBINE LIST
Developing Company | GT/ST/HRSG | Quantity | Manufacturer | Purchaser | On/Off Balance Sheet | BOP Purchased (Y/N) | Delivery Date(s) | Total Capex Commitment (MM USD) | Project(s) | Originator/ Developer | Hz | Total MW @ ISO | Heat Rate (HHV) | New/Used GT | Comments | Payment Dates & Amounts
ENA | LM6000 | 2 | GE | WLB | Off | Y - Transformers to be purchased 4/24/00 from ABB via WLB | 1-3 7/00; 4-6 8/00; 7-8 9/00; 9-11 10/00; 12-13 11/00; 14-15 12/00; 16-18 1/01; 19-20 2/01; 21-22 3/01; 23-24 4/01 | 28 | (see "LM6000 Timing") | Dietrich/Jacoby | 60 | 93 | 10400 | New
ENA | LM6000 | 4 | GE | WLB | Off | " |  | 56 | Las Vegas Co-Gen | Gilbert | 60 | 186 | 10400 | New | Operate in CC 4x2
ENA | LM6000 | 4 | GE | WLB | Off | " |  | 56 | City of Austin | Ducote/McDonald | 60 | 186 | 10400 | New
ENA | LM6000 | 4 | GE | WLB | Off | " |  | 56 | Colorado PSC | Thomas | 60 | 186 | 10400 | New
ENA | LM6000 | 4 | GE | WLB | Off | " |  | 56 | Puerto Suarez (ESA) |  | 60 | 186 | 10400 | New
ENA | LM6000 | 6 | GE | WLB | Off | " |  | 84 | Florida Merchant | Jacoby | 60 | 279 | 10400 | New
ENA | 7FA | 1 | GE | ENA | On |  | 2000-10-01 | 31 | Vitro/Mexico | Max Yazguirra | 60 | 250 | 6800 |  | Vitro- combined cycle project
ENA | 7FA | 1 | GE | WLB | Off | N | 2000-10-01 | 35 | Midwest/Peoples (in process of being assigned to Elwood Energy - Peoples/Dominion project | Dietrich/ Luce | 60 | 170 | 10500 | New | One of orginal Cogen Tech GTs; WLB and Peoples have ADA between themselves | See attached worksheet (obligation of People's)
ENA | 7FA2 | 3 | GE | WLB | Off | N | 2002-07-01 | 220 | Pastoria | Parquet | 60 | 750 | 6800 | New
ENA | ST | 1 |  | ENA | On |  | Available Now | 2.3 | Korean | Miller/Virgo | 60 | 110 |  | Used | Currently under sale negotiations
ENA | F6B | 2 | GE | ENA | On | N | Available Now | 13 | Lagos/LIPA swap with Calme | Dietrich/Jacoby | 50 | 70 | 12500 | Used
ENA | 11N1 | 2 | ABB | WLB | Off | N | Available Now | 26 | Canada | Milnthorp/LeDain | 60 | 166 |  | Used
EECC | 501D5A | 1 | Westinghouse | CALME | On | N | 2001-11-01 | 24 | CALME Panama | Shultz/Barto | 60 | 130 | 11500 | New |  | 90% pd to date; shipment (est 6/3) - 5%; COD (est 8/1) - 5%
EECC | 7FA; 1 - ST | 2 | GE | WLB3 | Off | N | 1 - 7/01; 1 - 8/01; ST 8/01 | 95 | GenPower | Barto | 60 | 500 | 6800 | New |  | See attached worksheet
EECC | 7FA; 1 - ST | 2 | GE | WLB3 | Off | N | 1 - 9/01; 1 - 10/01; ST 9/01 | 95 | GenPower | Barto | 60 | 500 | 6800 | New |  | See attached worksheet which includes schedule for CS2 & NEPCO NESCO
EECC | 7FA | 1 | GE | EECC | On | N | 2001-09-01 | 54 | Goldendale (NEPCO) | Westfahl | 60 | 250 | 6800 | New | aka NACO GTs | See attached worksheet
EECC | V94.2 Enhanced; ST; HRSG | 1 | Siemens; Toshiba ST & HRSG | EECC | On | N | 2001-11-01 | 64 | Croatia | Barto | 50 | 155 | 11260 | New |  | 5% - manu release; 15% NTP; 15% 3 mos after NTP; 10% 6 mos after NTP; 20% delivery GT; 10% delieveru of generator; 5% delivery of PCC container; 15% completion of erection; 5% pass performance test
EECC | 7EA2 | 2 | GE | LJM | Off3,4 | N | 1 - 2/01; 1 - 2/02 | 36 |  | Barto | 60 | 166 | 11900 | New |  | See attached worksheet
EECC | 9FA2 | 3 | GE | EECC3 | On | N | 1 - 10/01; 1 - 11/01; 1 - 12/01 | 249 | Arcos (Spain) | Barto | 50 | 1125 | 6800 | New | Subject to Sutton Bridge Settlement; due to timining issues, Izzo has requested Enron to purchase on balance sheet
CALME | 501D5A | 1 | Westinghouse | ENA | On | N | 2000-09-30 | 24 | Saudi Arabia | Haug | 60 | 130 | 11500 | New
CALME | F6B Power Barges | 9 | GE | EI Powerbarge Co. | On | N | Available Now | 72 | 2 - LIPA | Baca | 60 | 270 | 12,500 - 13,000 | Used
ESA | 501F | 2 | Mitsubishi | WLB | Off4 | N | 1- 7/01; 1 - 8/01 | 70 | Riogen | Wiggs | 60 | 368 |  | New
ESA | 501F1 | 2 | Mitsubishi | WLB | Off3,4 | N | 1 - 5/01; 1 - 10/01 | 75 | Cuiaba II or Riogen Expansion | Wiggs | 60 | 368 |  | New
60
Enron Europe | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
APACHI | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1ESA has option on these units which it expects to exercise 4/00 or 5/00
2Definitve agreement being negotiated
3Not officially in WLB but currently being sized for WLB
4ESA is currently negotiating a separate WLB-type facility for its projects

## LM6000 Inventory
ENRON LM6000 STATUS SHEET
UPDATED: 6/7/00
| S&SEP ID NUMBERS |  |  |  |  | PACKAGE ORDER STATUS | [9 empty] | DATES |  |  | SITING |  | MISCELLANEOUS
|  |  |  | AC |  | ENGINE | [6 empty] | EXH |  |  | CONTRACT | SCHED | ACTUAL | POINT | CURRENT |  |  | CHANGE
UNIT | DWG | PACKAGE | ENGINE | GEN | PRODUCT | FUEL | GEN | NOISE | FREEZE | PIPING | LINE | L/O | STACK | MAIN | INLET | DELIVERY | DELIVERY | DELIVERY | OF | SITE | TEST | COMMENTS | ORDERS | UNIT
NUMBER | SERIES | SERIAL # | SERIAL # | SERIAL # | SALES # | KIT | MFR | SPEC | PROT | CONFIG | SIDE | COOLING | STYLE | XFORMER | CHILLER | DATE | DATE | DATE | DELIVERY | ALLOCATION | TYPE |  | ISSUED | NUMBER
1 | 559XXX | 308898 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-06-20 |  | STORAGE |  |  |  |  | 1
7 | 568XXX | 309101 |  |  | 601134B | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan | 45H |  |  | 2000-09-30 | 2000-06-22 |  | STORAGE | Florida | FULL STRING |  | ? | 7
8 | 568XXX | 309123 |  |  | 601134B | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan | 45H |  |  | 2000-09-30 | 2000-06-30 |  | STORAGE | Florida |  |  | ? | 8
4 | 559XXX | 308999 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45 |  |  | 2000-08-30 | 2000-07-05 |  | STORAGE |  |  |  |  | 4
5 | 559XXX | 309020 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45H |  |  | 2000-08-30 | 2000-07-10 |  | STORAGE |  |  |  |  | 5
6 | 559XXX | 309073 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45H |  |  | 2000-08-30 | 2000-07-21 |  | STORAGE |  |  |  |  | 6
2 | 559XXX | 308951 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-07-26 |  | STORAGE |  |  |  |  | 2
3 | 559XXX | 308972 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-08-15 |  | STORAGE |  |  |  |  | 3
9 | 581XXX | 309266 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2000-10-30 | 2000-08-19 |  | Austin | Austin | STATIC |  |  | 9
10 | 581XXX | 309307 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2000-10-30 | 2000-09-01 |  | Austin | Austin | STATIC |  |  | 10
11 | 581XXX | 309376 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2000-10-30 | 2000-09-06 |  | Austin | Austin | STATIC |  |  | 11
12 | 581XXX | 309398 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2000-11-30 | 2000-09-14 |  | Austin | Austin | STATIC |  |  | 12
13 | 562XXX | 309420 |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2000-11-30 | 2000-09-21 |  | STORAGE | ESA |  |  |  | 13
14 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2000-12-30 | 2000-09-28 |  | STORAGE | ESA |  |  |  | 14
15 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2000-12-30 | 2000-10-25 |  | STORAGE | ESA |  |  |  | 15
16 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-01 |  | STORAGE | ESA |  |  |  | 16
17 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-13 |  | STORAGE | Florida |  |  | 1 | 17
18 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-20 |  | STORAGE | Florida |  |  | 1 | 18
19 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2001-02-28 | 2000-11-27 |  | STORAGE | Florida |  |  | 1 | 19
20 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-02-28 | 2000-12-11 |  | STORAGE | Florida |  |  | 1 | 20
21 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2001-03-30 | 2001-01-05 |  | STORAGE | Las Vegas |  |  |  | 21
22 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2001-03-30 | 2001-01-12 |  | STORAGE | Las Vegas |  |  |  | 22
23 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2001-04-30 | 2001-01-20 |  | STORAGE | Las Vegas |  |  |  | 23
24 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2001-04-30 | 2001-03-13 |  | STORAGE | Las Vegas |  |  |  | 24

## LM6000 Assign
LM 6000 Updated Assignment Schedule
[6 empty] | CUSTOMER |  | MERCHANT
|  | Original | Scheduled |  | Signed
UNIT | Est. | Delivery | Delivery | Closed | T/S or | Advanced | Early | Advanced | Early
NUMBER | C.O.D | Date | Date | Deal | L.O.I. | Discussion | Discussions | Development | Development
1 |  | 2000-07-30 | 2000-06-26 |  |  |  |  | ESA
2 |  | 2000-09-30 | 2000-06-26 |  |  |  |  | Tri-Valley 1 (CA) | Tri-Valley 2 (CA)
Project Cactus II *
NCA 1
Humboldt (CA)
3 |  | 2000-09-30 | 2000-06-30 |  |  |  | Tennergy |  | Enner Connect (LV)
Project Cactus II *
Humboldt (CA)
NCA 2
Project Columbia (OR) *
4 |  | 2000-08-30 | 2000-07-05 | [5 empty] | Enner Connect (LV)
[7 empty] | Tennergy | ESA | Humboldt (CA)
Project Columbia (OR) *
5 |  | 2000-08-30 | 2000-07-10 |  |  |  | San Antonio | ESA | Humboldt (CA)
Project Columbia (OR) *
6 |  | 2000-08-30 | 2000-07-21 |  |  |  | San Antonio | ESA | Redding (CA)
Project Columbia (OR) *
7 | 2002-05-01 | 2000-07-30 | 2000-07-26 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
8 | 2002-05-01 | 2000-07-30 | 2000-08-15 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
9 | 2001-05-01 | 2000-10-30 | 2000-08-19 | Austin
10 | 2001-05-01 | 2000-10-30 | 2000-09-01 | Austin
11 | 2001-05-01 | 2000-10-30 | 2000-09-06 | Austin
12 | 2001-05-01 | 2000-11-30 | 2000-09-14 | Austin
13 |  | 2000-11-30 | 2000-09-21 |  |  | PSCO
14 |  | 2000-12-30 | 2000-09-28 |  |  | PSCO
15 |  | 2000-12-30 | 2000-10-25 |  |  | PSCO
16 |  | 2001-01-30 | 2000-11-01 |  |  | PSCO
17 | 2002-05-01 | 2001-01-30 | 2000-11-13 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
18 | 2002-05-01 | 2001-01-30 | 2000-11-20 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
19 | 2002-05-01 | 2001-02-28 | 2000-11-27 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
20 | 2002-05-01 | 2001-02-28 | 2000-12-11 | [5 empty] | Lousiana
[8 empty] | Florida | Missouri
Chicago
21 | 03/01/2002 * | 2001-03-30 | 2001-01-05 |  |  |  |  | Las Vegas
22 | 03/01/2002 * | 2001-03-30 | 2001-01-12 |  |  |  |  | Las Vegas
23 | 03/01/2002 * | 2001-04-30 | 2001-01-20 |  |  |  |  | Las Vegas
24 | 03/01/2002 * | 2001-04-30 | 2001-03-13 |  |  |  |  | Las Vegas
* | These turbines need to be configured for combined-cycle operations.

## LM6000 Status
ENRON LM6000 STATUS SHEET
UPDATED: 6/7/00
| S&SEP ID NUMBERS |  |  |  |  | PACKAGE ORDER STATUS | [9 empty] | DATES |  |  | SITING |  | MISCELLANEOUS
|  |  |  | AC |  | ENGINE | [6 empty] | EXH |  |  | CONTRACT | SCHED | ACTUAL | POINT | CURRENT |  |  | CHANGE
UNIT | DWG | PACKAGE | ENGINE | GEN | PRODUCT | FUEL | GEN | NOISE | FREEZE | PIPING | LINE | L/O | STACK | MAIN | INLET | DELIVERY | DELIVERY | DELIVERY | OF | SITE | TEST | COMMENTS | ORDERS | UNIT
NUMBER | SERIES | SERIAL # | SERIAL # | SERIAL # | SALES # | KIT | MFR | SPEC | PROT | CONFIG | SIDE | COOLING | STYLE | XFORMER | CHILLER | DATE | DATE | DATE | DELIVERY | ALLOCATION | TYPE |  | ISSUED | NUMBER
1 | 559XXX | 308898 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-06-20 |  | STORAGE |  |  |  |  | 1
7 | 568XXX | 309101 |  |  | 601134B | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan | 45H |  |  | 2000-09-30 | 2000-06-22 |  | STORAGE | Florida | FULL STRING |  | ? | 7
8 | 568XXX | 309123 |  |  | 601134B | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan | 45H |  |  | 2000-09-30 | 2000-06-30 |  | STORAGE | Florida |  |  | ? | 8
4 | 559XXX | 308999 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45 |  |  | 2000-08-30 | 2000-07-05 |  | STORAGE |  |  |  |  | 4
5 | 559XXX | 309020 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45H |  |  | 2000-08-30 | 2000-07-10 |  | STORAGE |  |  |  |  | 5
6 | 559XXX | 309073 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45H |  |  | 2000-08-30 | 2000-07-21 |  | STORAGE |  |  |  |  | 6
2 | 559XXX | 308951 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | LH | LH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-07-26 |  | STORAGE |  |  |  |  | 2
3 | 559XXX | 308972 |  |  | 601134 | Gas/Water | GE | 85 dbA | -10F | RH | RH | Fin/Fan | 45 |  |  | 2000-07-30 | 2000-08-15 |  | STORAGE |  |  |  |  | 3
9 | 581XXX | 309266 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2000-10-30 | 2000-08-19 |  | Austin | Austin | STATIC |  |  | 9
10 | 581XXX | 309307 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2000-10-30 | 2000-09-01 |  | Austin | Austin | STATIC |  |  | 10
11 | 581XXX | 309376 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2000-10-30 | 2000-09-06 |  | Austin | Austin | STATIC |  |  | 11
12 | 581XXX | 309398 |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2000-11-30 | 2000-09-14 |  | Austin | Austin | STATIC |  |  | 12
13 | 562XXX | 309420 |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2000-11-30 | 2000-09-21 |  | STORAGE | ESA |  |  |  | 13
14 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2000-12-30 | 2000-09-28 |  | STORAGE | ESA |  |  |  | 14
15 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2000-12-30 | 2000-10-25 |  | STORAGE | ESA |  |  |  | 15
16 | 562XXX |  |  |  | 601134A | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-01 |  | STORAGE | ESA |  |  |  | 16
17 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-13 |  | STORAGE | Florida |  |  | 1 | 17
18 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-01-30 | 2000-11-20 |  | STORAGE | Florida |  |  | 1 | 18
19 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | LH | LH | Fin/Fan |  |  |  | 2001-02-28 | 2000-11-27 |  | STORAGE | Florida |  |  | 1 | 19
20 | 562XXX |  |  |  | 601134A | Dual/Water | Brush | 85 dbA | -10F | RH | RH | Fin/Fan |  |  |  | 2001-02-28 | 2000-12-11 |  | STORAGE | Florida |  |  | 1 | 20
21 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2001-03-30 | 2001-01-05 |  | STORAGE | Las Vegas |  |  |  | 21
22 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2001-03-30 | 2001-01-12 |  | STORAGE | Las Vegas |  |  |  | 22
23 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | LH | LH | Shell/Tube |  |  |  | 2001-04-30 | 2001-01-20 |  | STORAGE | Las Vegas |  |  |  | 23
24 | 581XXX |  |  |  | 601134C | Gas/Water | Brush | 85 dbA | -10F | RH | RH | Shell/Tube |  |  |  | 2001-04-30 | 2001-03-13 |  | STORAGE | Las Vegas |  |  |  | 24

## Generation
ENA
Generation Assets Position
Grand
[6 empty] | On Balance Sheet |  |  |  |  | Off Balance Sheet |  |  |  | Total
| Unallocated Turbines |  |  |  | Delivery | Turbine | Other |  | Total |  | Turbine | Other | Total
|  | Quant | MW | Type | Date | Cost | Costs | IDC | Cost |  | Cost | Costs | Cost
Steam Turbine |  | 1 | 110 | Steam Turbine ( Korean) | 2000 | 0 | 0 | 0 | 0 | a |  |  | 0 |  | 0
LM6000s |  |  | na | GE LM6000 | 2001 |  |  | 90675 | 90675 | b | 0 | 0 | 0 |  | 90675
|  | 4 | 180 | LV Cogen LM6000 | 2001 |  |  |  | 0 |  | 54000000 | 2916666.6667 | 56916666.6667 | d | 56916666.6667
|  | 6 | 270 | FL LM6000 | 2001 |  |  |  | 0 |  | 81000000 | 4375000 | 85375000 | d | 85375000
|  | 6 | 270 | PSCo LM6000 | 2001 |  |  |  | 0 |  | 81000000 | 4375000 | 85375000 | d | 85375000
|  | 3 | 620 | GE 7FA (Pastoria) | 2002 |  |  |  | 0 |  | 198000000 |  | 198000000 |  | 198000000
Canada |  | 2 | 166 | ABB 11N1(Canada) | 2001 |  |  |  | 0 |  | 33000000 |  | 33000000 |  | 33000000
| TOTAL | 22 | 1616 |  |  | 0 | 0 | 90675 | 90675 |  | 447000000 | 11666666.6667 | 458666666.6667 |  | 458757341.6667
| Turbine Transfers Out |  |  |  | Transfer
|  | Quant | MW |  | Date
Holland |  | 2 | 60 | LIPA GEC Fr 6B | Now | 9500000 | 0 | 0 | 9500000 | c |  |  | 0 |  | 9500000
| TOTAL | 2 | 60 |  |  | 9500000 | 0 | 0 | 9500000 |  | 0 | 0 | 0 |  | 9500000
| 1999 Peaking Plants |  |  |  | In Service | Plant | Capital |  | Net Book
|  |  | MW |  | Date | In Service | Improvement | Depreciation | Value
|  |  | 475 | Brownsville, TN | 1999-06-01 | 126003080 | 0 | -2663435 | 123339645 | [5 empty] | 123339645
|  |  | 475 | Caledonia, MS | 1999-06-01 | 152963616 | 147438 | -3240782 | 149870272 | [5 empty] | 149870272
|  |  | 390 | New Albany, MS | 1999-06-01 | 147500329 | 1556274 | -2954500 | 146102103 | [5 empty] | 146102103
| TOTAL |  | 1340 |  |  | 426467025 | 1703712 | -8858717 | 419312020 |  | 0 | 0 | 0 |  | 419312020
2000 Peaking Plants
|  |  | 608 | Wilton, IL | 2000-05-24 | 272051707 |  |  | 272051707 | [5 empty] | 272051707
|  |  | 509 | Gleason,TN | 2000-06-01 | 177623262 |  |  | 177623262 | [5 empty] | 177623262
|  |  | 470 | Wheatland, IN | 2000-06-01 | 162991024 |  |  | 162991024 | [5 empty] | 162991024
| TOTAL |  | 1587 |  |  | 612665993 | 0 | 0 | 612665993 | e | 0 | 0 | 0 |  | 612665993
| GRAND TOTAL |  | 4603 | mw |  |  |  |  | 1041568688 |  |  |  | 458666666.6667 |  | 1500235354.6667
|  | a | Steam turbine written down in Q2
|  | b | IDC incurred prior to receiving refund from GE on the $16,740,000 deposit -- To be refunded
|  | c | $6 Million impairment in Q2
|  | d | Includes Power Boosters & IDC
|  | e | Includes Acceleration Trend on Gleason and Wheatland and removes EECC Base Fee
Other Turbine Information
| Vitro |  | 1 | GE 7FA (orig Project Orange Turbine) |  |  |  |  | On Balance Sheet
| Linden 6 |  | 1 | GE 7FA (orig Project Orange Turbine) |  |  |  |  | Not ENA obligation
| Elwood/Peoples |  | 1 | GE 7FA (orig Project Orange Turbine) |  |  |  |  | Not ENA obligation
| Coyote Springs 2 |  | 1 | GE 7FA (orig Naco Turbine) |  |  |  |  | Not ENA obligation
| Electricities |  | 2 | WH 501D5A (project scrubbed, turbines were on EECC's Balance sheet)
| Doyle Project |  | 2 | GE 7EA |  |  |  |  | In Construction/Operation
|  |  | 3 | GE 7B's (Korean Refurb's)
| TECO |  | 1 | GE 7EA |  |  |  |  | Not ENA obligation
| City of Austin |  | 4 | LM 6000 |  |  |  |  | In construction
| ESA |  | 4 | LM6000 |  |  |  |  | Need to make Balance Sheet Transfer
Note on O9: acopela: paid in full
Note on Q10: Jody Pierce: Total cost of 24 turbines reduced by allocated costs of assigned turbines.
Note on S10: Jody Pierce: Allocated cost of boosters plus 6.7mm IDC
Note on Q15: acopela: WLB
Note on I20: tshepperd: Impair $3MM in Q2
Note on O20: acopela: paid in full

## LM6000 Parts
LM 6000 GTG
|  | Refrigeration | Inlet Air Heating |  |  | MV | MV | LV | LV |  | BOP | Fuel Oil | Fuel Oil | Fuel Gas | Instrument | S&S
Item # | Location | System | System | SCR | HV Swgr | Transformers | Swgr | Transformers | Swgr | CEMS | PLC | Centrifuge | Storage Tanks | Compressors | Air Systems | Pkgs
1
2
3
4
5
6
7
8
9 | Austin | Y, Discount Possible | Y, Discount Possible | Y, Discount Possible | NEPCO | NEPCO | NEPCO | NEPCO | NEPCO | NEPCO | NEPCO | N/A | N/A | NEPCO | NEPCO | ?
10 | Austin | Y | Y | Y | N | N | N | N | N | N | N | N/A | N/A | N | N | ?
11 | Austin | Y | Y | Y | N | N | N | N | N | N | N | N/A | N/A | N | N | ?
12 | Austin | Y | Y | Y | N | N | N | N | N | N | N | N/A | N/A | N | N | ?
13
14
15
16
17 | Las Vegas | N | N
18 | Las Vegas | N | N
19 | Las Vegas | N | N
20 | Las Vegas | N | N
21
22
23
24

## GenPower (Dell) Pmt Schedule (hidden)
EECC
Payment Schedules
Dell Site
| Invoice | Payment | [7 empty] | Monthly | Cumulative
| Month | Due Date | Event | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$ | $$$
| 2000-03-01 | 2000-03-01 | Signed LOC | 8.6% | 3165121.64 | 8.5% | 3128317.9 | 8.34% | 1794978.168 | 8088417.708 | 8088417.708
| 2000-03-01 | April 22 - 00 | Progress Payment | 1.8% | 662467.32 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1665958.854 | 9754376.562
| 2000-04-01 | May 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1684360.724 | 11438737.286
| 2000-05-01 | June 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1684360.724 | 13123098.01
| 2000-06-01 | July 22 - 00 | Progress Payment | 1.9% | 699271.06 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1702762.594 | 14825860.604
| 2000-07-01 | Aug 22 - 00 | Progress Payment | 19.9% | 7323944.26 | 19% | 6992710.6 | 18.32% | 3942925.664 | 18259580.524 | 33085441.128
| 2000-08-01 | Sept 22 - 00 | Progress Payment | 3% | 1104112.2 | 2.5% | 920093.5 | 2.56% | 550976.512 | 2575182.212 | 35660623.34
| 2000-09-01 | Oct 22 - 00 | Progress Payment | 3% | 1104112.2 | 2.5% | 920093.5 | 3% | 645675.6 | 2669881.3 | 38330504.64
| 2000-10-01 | Nov 22 - 00 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 41184404.64
| 2000-11-01 | Dec 22 - 00 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 44038304.64
| 2000-12-01 | Jan 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 46892204.64
| 2001-01-01 | Feb 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 49746104.64
| 2001-02-01 | Mar 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 52600004.64
| 2001-03-01 | April 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 55453904.64
| 2001-04-01 | May 22 - 01 | Progress Payment | 3.1% | 1140915.94 | 3% | 1104112.2 | 3% | 645675.6 | 2890703.74 | 58344608.38
| 2001-05-01 | June 22 - 01 | Progress Payment | 4% | 1472149.6 | 3% | 1104112.2 | 3.1% | 667198.12 | 3243459.92 | 61588068.3
| 2001-06-01 | July 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.5% | 1288130.9 | 3.5% | 753288.2 | 3513568.7 | 65101637
| 2001-07-01 | Aug 22 - 01 | Progress Payment | 4% | 1472149.6 | 4% | 1472149.6 | 3.5% | 753288.2 | 3697587.4 | 68799224.4
| 2001-08-01 | Sept 22 - 01 | GT 1 - STM Shipment | 20% | 7360748 | 4% | 1472149.6 | 25% | 5380630 | 14213527.6 | 83012752
| 2001-09-01 | Oct 22 - 01 | GT 2 Shipment | 5% | 1840187 | 20% | 7360748 | 5% | 1076126 | 10277061 | 93289813
| 2001-10-01 | Nov 22 - 01 | 30 Days After Shipment | 0% | 0 | 5% | 1840187 | 0% | 0 | 1840187 | 95130000
| Total Sales |  |  | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
|  |  |  | 36803740 |  | 36803740 |  | 21522520
| IPS # 91021 |  | Notes:
| 2000-03-06 |  | Payment
The initial payment is due within 3 days of signed Letter of Credit
Progress Payments are due on the 22nd of the indicated month and will be billed 30 days in advance.( Except for the February Payments)
Payments tied to shipment of equipment are due net 15 days after receipt of invoice and certification that equipment has shipped.
August reflects repayment of deferred amounts from February through July 2000.
EECC
Termination Schedules
Dell Site
Cumulative
| Month |  | Termination | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$
| 2000-03-01 |  | Signed LOC | 10.4% | 3827588.96 | 10.4% | 3827588.96 | 5% | 1076126 | 8731303.92
| 2000-04-01 |  |  | 10.8% | 3974803.92 | 10.8% | 3974803.92 | 5% | 1076126 | 9025733.84
| 2000-05-01 |  |  | 11.1% | 4085215.14 | 11.1% | 4085215.14 | 5% | 1076126 | 9246556.28
| Jun 15 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 5% | 1076126 | 11970033.04
| Jun 16 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 10% | 2152252 | 13046159.04
| 2000-07-01 |  |  | 20% | 7360748 | 20% | 7360748 | 15% | 3228378 | 17949874
| 2000-08-01 |  |  | 30% | 11041122 | 30% | 11041122 | 20% | 4304504 | 26386748
| 2000-09-01 |  |  | 32% | 11777196.8 | 32% | 11777196.8 | 24% | 5165404.8 | 28719798.4
| 2000-10-01 |  |  | 34% | 12513271.6 | 34% | 12513271.6 | 28% | 6026305.6 | 31052848.8
| 2000-11-01 |  |  | 36% | 13249346.4 | 36% | 13249346.4 | 40% | 8609008 | 35107700.8
| 2000-12-01 |  |  | 38% | 13985421.2 | 40% | 14721496 | 51% | 10976485.2 | 39683402.4
| 2001-01-01 |  |  | 40% | 14721496 | 40% | 14721496 | 59% | 12698286.8 | 42141278.8
| 2001-02-01 |  |  | 40% | 14721496 | 40% | 14721496 | 70% | 15065764 | 44508756
| 2001-03-01 |  |  | 40% | 14721496 | 40% | 14721496 | 80% | 17218016 | 46661008
| 2001-04-01 |  |  | 40% | 14721496 | 40% | 14721496 | 83% | 17863691.6 | 47306683.6
| 2001-05-01 |  |  | 40% | 14721496 | 40% | 14721496 | 87% | 18724592.4 | 48167584.4
| 2001-06-01 |  |  | 40% | 14721496 | 40% | 14721496 | 93% | 20015943.6 | 49458935.6
| 2001-07-01 |  |  | 40% | 14721496 | 40% | 14721496 | 95% | 20446394 | 49889386
| 2001-08-01 |  |  | 40% | 14721496 | 40% | 14721496 | 98% | 21092069.6 | 50535061.6
| 2001-09-01 |  | GT 1 - STM Shipment | 100% | 36803740 | 40% | 14721496 | 100% | 21522520 | 73047756
| 2001-10-01 |  | GT 2 Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
| 2001-11-01 |  | 30 Days After Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
| IPS # 91021 |  | Notes:
2000-03-06
Termination
The buyer may terminate this agreement at any time upon written notification and payment of
termination charges in accordance with the schedule set forth above.
Title to any terminated combustion turbine-generator equipment or accessories remains
with the Seller.
The termination charge for any equipment for which title has transferred is 100%.
Upon Financial Closure EEPC is responsible for 100% of the termination charges.

## Peoples Pmt Schedule (hidden)
Payment Date | Payments from WestLB to GE
1999-12-31 | 0
2000-01-05 | 2529455.29
2000-02-22 | 0
2000-03-20 | 2529455.29
2000-04-20 | 2529455.29
2000-05-22 | 2529455.29
2000-06-20 | 2529455.29
2000-07-20 | 2529455.29
2000-08-21 | 6485782.8
2000-09-20 | 10766399.45
Total | 32428913.99

## GenPower (McAdams) Pmt Schedule (hidden)
EECC
Payment Schedules
McAdams Site
| Invoice |  | Payment | [7 empty] | Monthly | Cumulative
| Month |  | Due Date | Event | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$ | $$$
| 2000-03-01 |  | 2000-03-22 | Signed LOC | 8.6% | 3165121.64 | 8.5% | 3128317.9 | 8.5% | 1829414.2 | 8122853.74 | 8122853.74
| 2000-03-01 |  | April 22 - 00 | Progress Payment | 1.8% | 662467.32 | 1.75% | 644065.45 | 1.75% | 376644.1 | 1683176.87 | 9806030.61
| 2000-04-01 |  | May 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.77% | 380948.604 | 1705883.244 | 11511913.854
| 2000-05-01 |  | June 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.77% | 380948.604 | 1705883.244 | 13217797.098
| 2000-06-01 |  | July 22 - 00 | Progress Payment | 1.9% | 699271.06 | 1.75% | 644065.45 | 1.79% | 385253.108 | 1728589.618 | 14946386.716
| 2000-07-01 |  | Aug 22 - 00 | Progress Payment | 19.9% | 7323944.26 | 19% | 6992710.6 | 19.2% | 4132323.84 | 18448978.7 | 33395365.416
| 2000-08-01 |  | Sept 22 - 00 | Progress Payment | 3.8% | 1398542.12 | 3.5% | 1288130.9 | 3.55% | 764049.46 | 3450722.48 | 36846087.896
| 2000-09-01 |  | Oct 22 - 00 | Progress Payment | 3.8% | 1398542.12 | 3.5% | 1288130.9 | 3.58% | 770506.216 | 3457179.236 | 40303267.132
| 2000-10-01 |  | Nov 22 - 00 | Progress Payment | 3.9% | 1435345.86 | 3.5% | 1288130.9 | 3.62% | 779115.224 | 3502591.984 | 43805859.116
| 2000-11-01 |  | Dec 22 - 00 | Progress Payment | 3.9% | 1435345.86 | 3.6% | 1324934.64 | 3.66% | 787724.232 | 3548004.732 | 47353863.848
| 2000-12-01 |  | Jan 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.6% | 1324934.64 | 3.66% | 787724.232 | 3548004.732 | 50901868.58
| 2001-01-01 |  | Feb 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.7% | 1361738.38 | 3.7% | 796333.24 | 3593417.48 | 54495286.06
| 2001-02-01 |  | Mar 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.7% | 1361738.38 | 3.7% | 796333.24 | 3593417.48 | 58088703.54
| 2001-03-01 |  | April 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.7% | 1361738.38 | 3.74% | 804942.248 | 3638830.228 | 61727533.768
| 2001-04-01 |  | May 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.7% | 1361738.38 | 3.74% | 804942.248 | 3638830.228 | 65366363.996
| 2001-05-01 |  | June 22 - 01 | Progress Payment | 4% | 1472149.6 | 4% | 1472149.6 | 3.85% | 828617.02 | 3772916.22 | 69139280.216
| 2001-06-01 |  | July 22 - 01 | Gas 1 Shipment | 20% | 7360748 | 4% | 1472149.6 | 10.07% | 2167317.764 | 11000215.364 | 80139495.58
| 2001-07-01 |  | Aug 22 - 01 | Gas 2 / Steam Shipment | 5% | 1840187 | 20% | 7360748 | 15.29% | 3290793.308 | 12491728.308 | 92631223.888
| 2001-08-01 |  | Sept 22 - 01 | 30 Days After Shipment | 0% | 0 | 5% | 1840187 | 3.06% | 658589.112 | 2498776.112 | 95130000
| Total Sales |  |  |  | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
[5 empty] | 36803740 |  | 36803740 |  | 21522520 |  | 95130000 | 190260000
| IPS # 90070 |  |  | Notes:
| 2000-03-06 |  |  | Payment
The initial payment is due within 3 days of signed Letter of Credit
Progress Payments are due on the 22th of the indicated month and will be billed 30 days in advance.( Except for the February Payments)
Payments tied to shipment of equipment are due net 15 days after receipt of invoice and certification that equipment has shipped.
August reflects repayment of deferred amounts from February through July 2000.
EECC
Termination Schedules
McAdams Site
Cumulative
|  | Month |  | Termination | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$
|  | 2000-03-01 |  | Signed LOC | 10.4% | 3827588.96 | 10.4% | 3827588.96 | 5% | 1076126 | 8731303.92
|  | 2000-04-01 |  |  | 10.8% | 3974803.92 | 10.8% | 3974803.92 | 5% | 1076126 | 9025733.84
|  | 2000-05-01 |  |  | 11.1% | 4085215.14 | 11.1% | 4085215.14 | 5% | 1076126 | 9246556.28
|  | Jun 15 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 5% | 1076126 | 11970033.04
|  | Jun 16 -00 |  |  | 14.8% | 5446953.52 | 114.8% | 42250693.52 | 11% | 2367477.2 | 50065124.24
|  | 2000-07-01 |  |  | 20% | 7360748 | 20% | 7360748 | 12% | 2582702.4 | 17304198.4
|  | 2000-08-01 |  |  | 30% | 11041122 | 30% | 11041122 | 15% | 3228378 | 25310622
|  | 2000-09-01 |  |  | 32% | 11777196.8 | 32% | 11777196.8 | 25% | 5380630 | 28935023.6
|  | 2000-10-01 |  |  | 34% | 12513271.6 | 34% | 12513271.6 | 29% | 6241530.8 | 31268074
|  | 2000-11-01 |  |  | 36% | 13249346.4 | 36% | 13249346.4 | 40% | 8609008 | 35107700.8
|  | 2000-12-01 |  |  | 38% | 13985421.2 | 40% | 14721496 | 51% | 10976485.2 | 39683402.4
|  | 2001-01-01 |  |  | 40% | 14721496 | 40% | 14721496 | 59% | 12698286.8 | 42141278.8
|  | 2001-02-01 |  |  | 40% | 14721496 | 40% | 14721496 | 64% | 13774412.8 | 43217404.8
|  | 2001-03-01 |  |  | 40% | 14721496 | 40% | 14721496 | 76% | 16357115.2 | 45800107.2
|  | 2001-04-01 |  |  | 40% | 14721496 | 40% | 14721496 | 83% | 17863691.6 | 47306683.6
|  | 2001-05-01 |  |  | 40% | 14721496 | 40% | 14721496 | 86% | 18509367.2 | 47952359.2
|  | 2001-06-01 |  |  | 40% | 14721496 | 40% | 14721496 | 93% | 20015943.6 | 49458935.6
|  | 2001-07-01 |  | Gas 1 Shipment | 100% | 36803740 | 40% | 14721496 | 98% | 21092069.6 | 72617305.6
|  | 2001-08-01 |  | Gas 2 / Steam Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
|  | 2001-09-01 |  | 30 Days After Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
[5 empty] | 36803740 |  | 36803740 |  | 21522520
IPS # 90070
| 2000-03-06 |  |  | Termination
The buyer may terminate this agreement at any time upon written notification and payment of
termination charges in accordance with the schedule set forth above.
Title to any terminated combustion turbine-generator equipment or accessories remains
with the Seller.
The termination charge for any equipment for which title has transferred is 100%.
Upon Financial Closure EECC is responsible for 100% of the termination charges.

## Arcos Pmt Schedule (hidden)
IPS No. 90535 | Payment Schedule
Enron / Arcos de la Frontera
| Month |  | ($000's) | %
MOU
Non-Refundable Down Payment | 2000-04-01 |  | 25025 | 10%
| 2000-04-25 |  | 9030.4 | 2%
| 2000-05-25 |  | 7193.85 | 3%
| 2000-06-25 |  | 7193.85 | 3%
| 2000-07-25 |  | 9591.8 | 4%
| 2000-08-25 |  | 11989.75 | 5%
| 2000-09-25 |  | 14387.7 | 6%
| 2000-10-25 |  | 11989.75 | 5%
| 2000-11-25 |  | 11989.75 | 5%
| 2000-12-25 |  | 11989.75 | 5%
| 2001-01-25 |  | 11989.75 | 5%
| 2001-02-25 |  | 11989.75 | 5%
| 2001-03-25 |  | 9591.8 | 4%
| 2001-04-25 |  | 7193.85 | 3%
| 2001-05-25 |  | 7193.85 | 3%
| 2001-06-25 |  | 7193.85 | 3%
| 2001-07-25 |  | 4795.9 | 2%
| 2001-08-25 |  | 4795.9 | 2%
| 2001-09-25 |  | 4795.9 | 2%
Ship GT1, ST1 | 2001-10-25 |  | 4795.9 | 2%
Ship GT2, ST2 | 2001-11-25 |  | 14387.7 | 6%
Ship GT3, ST3 | 2001-12-25 |  | 16785.65 | 7%
| 2002-01-25 |  | 14387.7 | 6%
| 2002-02-25 |  | 2397.95 | 1%
| 2002-03-25 |  | 2397.95 | 1%
|  |  | 239795 | 100%
245075
Down payment due net 3 days from contract signing / MOU via wire transfer
Progress payments due on 25th of each month
Payments tied to shipment due Net 30 days from receipt of invoice
TDI & Training payments not included in above schedule, and will be
|  | invoiced separately (terms: 10% down, remainder as performed) |  |  | . The current value of these Services is $10,455,000.00

## Puerto Suarez (hidden)
Months from Purchase Agreement Execution
Calendar Month
7. Event
8. Milestone
Monthly % of CGT Price
Monthly Payment Total for Two (2) % of CTG Price
Cumulative Payment Total for Two (2) % of CTG Price |  |  |  | Monthly % of CTG Price
Motnhs From Date of Execution of Agreement | Calendar Month | Event | Milestone | CTG#1 | CTG#2 | Monthly Payment Total for Two (2) % of CTG Price | Cumulative Payment Total for Two (2) % of CTG Price
0 | Date of Execution of the Purchase Agreement | Monthly Progress Payment | Purchase Agreement Execution | 7.22% | 5% | 6.11% | 6.11%
1 | 2000-05-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 9.72%
2 | 2000-06-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 13.33%
3 | 2000-07-01 | Monthly Progress Payment |  | 7.22% | 5% | 6.11% | 19.44%
4 | 2000-08-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 23.05%
5 | 2000-09-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 26.66%
6 | 2000-10-01 | Monthly Progress Payment |  | 7.22% | 5% | 6.11% | 32.77%
7 | 2000-11-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 36.38%
8 | 2000-12-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 39.99%
9 | 2000-01-01 | Monthly Progress Payment |  | 7.24% | 9% | 8.12% | 48.11%
10 | 2000-02-01 | Available to Ship CTG #1 EXW | Available to Ship CTG #1 EXW | 22.22% | 7% | 14.61% | 62.72%
11 | 2000-03-01 | Final Payment CTG #1 | CTG #1 FCA Port of Export | 5.56% | 6% | 5.78% | 68.5%
12 | 2000-04-01 | Monthly Progress Payment |  |  | 9% | 4.5% | 73%
13 | 2000-05-01 | Monthly Progress Payment |  |  | 7% | 3.5% | 76.5%
14 | 2000-06-01 | Monthly Progress Payment |  |  | 6% | 3% | 79.5%
15 | 2000-07-01 | Monthly Progress Payment |  |  | 4% | 2% | 81.5%
16 | 2000-08-01 | Monthly Progress Payment |  |  | 4% | 2% | 83.5%
17 | 2000-09-01 | Monthly Progress Payment |  |  | 3% | 1.5% | 85%
18 | 2000-10-01 | Monthly Progress Payment |  |  | 2.22% | 1.11% | 86.11%
19 | 2000-11-01 | Monthly Progress Payment |  |  |  | 0% | 86.11%
20 | 2000-12-01 | Monthly Progress Payment |  |  |  | 0% | 86.11%
21 | 2000-01-02 | Monthly Progress Payment |  |  |  | 0% | 86.11%
22 | 2000-02-02 | Available to Ship CTG #2 EXW | Available to Ship CTG #2 EXW |  | 22.22% | 11.11% | 97.22%
23 | 2000-03-02 | Final Payment CTG #2 | CTG #2 FCA Port of Export |  | 5.56% | 2.78% | 100%
24 | 2000-04-02 |  |  |  |  | 0% | 100%
|  | Total |  |  |  | Total |  | 100% | 100% | 100%