## Sheet1
Nicor Compression Transaction
Risks & Mitigants
Service | Responsible Party | Risk (s) | Mitigant(s)
Wholesale Power | Enron Power Marketing (EPM) | Non-delivery during 15-Yr Term due to an | - EPM's exposure to Liquidated Damages
|  | Enron Corp. bankruptcy or merger with a | - Procure power from another company
company that plans to exit power business.
Retail Power | IL Power | - Construction delay (transmission line) | - Build in plenty of lead time (3-6 months)
- Active communication between E. & IL Power
- Signed contract between E. & IL Power
|  | - Transmission line/system interruption | - Purchase of network service vs. point-to-point
|  | and/or Substation failure | - IL Power's Contingency Plan (Back-up facility)
- Review historical outage reports
- Contractual remedies (E. & IL Power)
|  | - Regulatory change (i.e. tariff changes) | - All tariff price changes would be directly
passed through to NICOR
Compression | NICOR | Default on Annual Charge Payment during | - Corporate Guarantee from NICOR
|  | the 15-Yr Term. Annual Charge needed to | - NICOR's L-T S&P credit rating is AA
pay capital financing and power option
premium payments.
Financing | Enron | - Enron defaults if NICOR defaults | - Corporate Guarantee from NICOR
- NICOR's L-T S&P credit rating is AA
- Purchase a credit derivative
|  | - Enron Corp. goes into bankruptcy | - Power position disposition procedure (?)
Equipment | Enron | - Cost overrun | - Turnkey contract
|  | - Late delivery | - Build in plenty of lead time (3-6 months)
|  | - Equipment failure (major) | - 1 to 3 Yr Warranty + Insurance
|  | - Equipment downtime (temporary) | - Maintenance Service Contract
|  | - Equipment duration | - 25-Yr life expectancy
|  | - Faulty maintenance | - Maintenance Service Contract
Storage | NICOR | - Facility downtime or blowout | - Contractually obligated to take firm power
from Enron and pay Annual Charge to Enron.