## Project Scope
ENRON COSTS REQUIRED TO COMPLETE PROJECT
2014-09-04
|  | CUSTOMER COMPANY NAME: | TRANSWESTERN PIPELINE CO
|  | PROJECT NAME: | EOG PRONGHORN I/C
ENRON TRACKING NUMBER:
|  | PROJECT MANAGER: | LAURA J. KUNKEL
REVISION NUMBER:
ASSUMPTIONS
This estimate assumes that EOG will do all the conduit & wiring. TW will be required to help with the terminations.
This estimate further assumes that all the transmitters, tubing, piping and valving, along with the controls for the
flow control and shut-in valve will be done by EOG.
TW personnel will need to use their expertise to do the programming in the instrumentation to Enron protocol.
TW personnel will need to use their inspectors to get the information for the as-built package.
Enron personnel will need to draw the station up for As-Built purposes.
Enron personnel in Houston will need to do the programming on the Bristol RTU.
This does not include costs to spec out the equipment which had previously been done for this project.

## M&E Costs
ENRON COSTS REQUIRED TO COMPLETE PROJECT
2014-09-04
| CUSTOMER COMPANY NAME: | TRANSWESTERN PIPELINE CO.
| PROJECT NAME: | EOG PRONGHORN INTERCONNECT
TRACKING NUMBER:
| PROJECT MANAGER: | LAURA J. KUNKEL
REVISION NUMBER:
MATERIAL AND EQUIPMENT COSTS
MOST
[6 empty] | BEST CASE | WORST CASE | PROBABLE
DESCRIPTION | [5 empty] | COST | COST | COST
|  |  | Qty. | Unit | Unit cost | ESTIMATE | ESTIMATE | ESTIMATE
[6 empty] | 0 | 0 | 0
Field labor to calibrate chromatograph & other inst. |  |  | 48 | hours | 60 | 2880 | 4320 | 3168
Programming time on the Bristol |  |  | 40 | hours | 100 | 4000 | 6000 | 4400
Installing Bristol program |  |  | 10 | hours | 100 | 1000 | 1500 | 1100
Inspect & get red line info. |  |  | 10 | days | 450 | 4500 | 6750 | 4950
Set up communications - antennae & SCADA set up |  |  | 16 | hours | 100 | 1600 | 2400 | 1760
Purchase antennae & tower |  |  | 1 | each | 1800 | 1800 | 2700 | 1980
Set antennae |  |  | 1 | lot | 2500 | 2500 | 3750 | 2750
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Drawings for As-Built - Mechanical |  |  | 16 | hours | 100 | 1600 | 2400 | 1760
Drawings for As-Built -Electrical |  |  | 60 | hours | 100 | 6000 | 9000 | 6600
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
TAX (6.25% of materials) | [5 empty] | 1617.5 | 2426.25 | 1779.25
Overheads @ 20% | [5 empty] | 5499.5 | 8249.25 | 6049.45
|  | MATERIALS AND EQUIPMENT COSTS SUB-TOTAL |  |  |  | 32997 | 49495.5 | 36296.7