## Sheet1
Bank One, Texas N.A. |  |  |  | Funds Required | 10740980.8665 |  |  | Application No: | 1
Bishops Corner Apartments |  |  |  | Loan Amount | 8062278.3546 |  |  | Application Date: | 2014-09-04 10:25
Construction And Draw Schedule |  |  |  | Equity Required | 2673399.6741 |  |  | Period To: | 2001-10-31
A | B | % Total | C | D | E | F | G | J | K | L | M | N | O
Item No. | Description Of Work |  | Scheduled Value | From Previous Application (D + E) | This Period | Materials Presently Stored (Not In D or E) | Total Completed And Stored To Date (D + E + F) | % (G / C) | Balance To Finish (C - G) | Retainage (If Variable Rate) E * 10% | Net Draw ( E - L ) | Retained From Previous Applications | Cumulative Retained ( L + N )
1 | General Conditions | 3.999% | 429511 | 0 | 24571.62 |  | 24571.62 | 5.721% | 404939.38 | 2457.162 | 22114.458 | 0 | 2457.162
2 | Earthwork (Bldg. Pads & Drives) | 2.802% | 300951 | 0 | 90285.3 |  | 90285.3 | 30% | 210665.7 | 9028.53 | 81256.77 | 0 | 9028.53
3 | Utilities | 2.382% | 255885 | 0 | 25588.5 |  | 25588.5 | 10% | 230296.5 | 2558.85 | 23029.65 | 0 | 2558.85
4 | Paving, Curbs, & Approaches | 2.824% | 303323 | 0 |  |  | 0 | 0% | 303323 | 0 | 0 | 0 | 0
5 | Site Devel. (Flatwork, Fence & Gates) | 1.205% | 129430 | 0 |  |  | 0 | 0% | 129430 | 0 | 0 | 0 | 0
6 | Landscape, Irrigation, & Topsoil | 1.629% | 175000 | 0 |  |  | 0 | 0% | 175000 | 0 | 0 | 0 | 0
7 | Retaining Walls | 0.1862% | 20000 | 0 |  |  | 0 | 0% | 20000 | 0 | 0 | 0 | 0
8 | Volleyball Court | 0.04655% | 5000 | 0 |  |  | 0 | 0% | 5000 | 0 | 0 | 0 | 0
9 | Concrete | 4.994% | 536411 | 0 |  |  | 0 | 0% | 536411 | 0 | 0 | 0 | 0
10 | Masonary | 2.831% | 304046 | 0 |  |  | 0 | 0% | 304046 | 0 | 0 | 0 | 0
11 | Carpentry - Rough | 13.05% | 1401504 | 0 |  |  | 0 | 0% | 1401504 | 0 | 0 | 0 | 0
12 | Finish Carpentry | 0.7645% | 82120 | 0 |  |  | 0 | 0% | 82120 | 0 | 0 | 0 | 0
13 | Cabinets | 1.372% | 147400 | 0 |  |  | 0 | 0% | 147400 | 0 | 0 | 0 | 0
14 | Insulation & Fireproofing | 0.8353% | 89720 | 0 |  |  | 0 | 0% | 89720 | 0 | 0 | 0 | 0
15 | Roofing | 1.36% | 146097 | 0 |  |  | 0 | 0% | 146097 | 0 | 0 | 0 | 0
16 | Doors | 1.246% | 133847 | 0 |  |  | 0 | 0% | 133847 | 0 | 0 | 0 | 0
17 | Windows | 0.7237% | 77729 | 0 |  |  | 0 | 0% | 77729 | 0 | 0 | 0 | 0
18 | Hardware | 0.2121% | 22780 | 0 |  |  | 0 | 0% | 22780 | 0 | 0 | 0 | 0
19 | Drywall | 3.271% | 351360 | 0 |  |  | 0 | 0% | 351360 | 0 | 0 | 0 | 0
20 | Painting | 1.397% | 150000 | 0 |  |  | 0 | 0% | 150000 | 0 | 0 | 0 | 0
21 | Flooring | 1.764% | 189440 | 0 |  |  | 0 | 0% | 189440 | 0 | 0 | 0 | 0
22 | Specialties | 0.96% | 103110 | 0 |  |  | 0 | 0% | 103110 | 0 | 0 | 0 | 0
23 | Appliances | 1.9% | 204082 | 0 |  |  | 0 | 0% | 204082 | 0 | 0 | 0 | 0
24 | Plumbing | 5.238% | 562619 | 0 |  |  | 0 | 0% | 562619 | 0 | 0 | 0 | 0
25 | HVAC | 2.002% | 215070 | 0 |  |  | 0 | 0% | 215070 | 0 | 0 | 0 | 0
26 | Electrical | 6.75% | 725000 | 0 |  |  | 0 | 0% | 725000 | 0 | 0 | 0 | 0
27 | Swimming Pool | 0.931% | 100000 | 0 |  |  | 0 | 0% | 100000 | 0 | 0 | 0 | 0
| Contractor Hard Costs | 66.67% | 7161435 | 0 | 140445.42 |  | 140445.42 | 1.961% | 7020989.58 | 14044.542 | 126400.878 | 0 | 14044.542
28 | Builders Overhead | 6% | 435000 | 0 | 22653.78 |  | 22653.78 | 5.208% | 412346.22 |  | 22653.78
29 | Bond | 0.6275% | 67405 | 0 | 67405 |  | 67405 | 100% | 0 |  | 67405
30 | Builders Risk | 0.2184% | 23460 | 0 | 23460 |  | 23460 | 100% | 0 |  | 23460
| Contractor Soft Costs | 4.896% | 525865 | 0 | 113518.78 |  | 113518.78 | 21.59% | 412346.22 |  | 113518.78
| Total Contractor Costs | 71.57% | 7687300 | 0 | 253964.2 |  | 253964.2 | 3.304% | 7433335.8 |  | 239919.658
I certify that the work covered by this requisition has been completed in accordance with the contract documents, and that I have actually received $_________________ for work previously performed and materials purchased up to
the ________ day of __________ , 2001 (date of previous requisition).
| Date________ |  | C: Contractor Authorized Signature; 2673399.6741 E: _______________________________________; Period To: J: Owner Rep. Signature _________________________________________
31 | Permits, Impact Fees, Mort. Other Fees | 1.024% | 110000 | 0 | 55000 |  | 55000 | 50% | 55000 |  | 55000
32 | Architects Fee & Design | 1.596% | 171386 | 0 | 171386 |  | 171386 | 100% | 0 |  | 171386
33 | Architect's Fee-Supervisory | 0.5218% | C: 56050; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 56050; 2001-10-31 M: 0
34 | Taxes | 1.08% | C: 116000; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 116000; 2001-10-31 M: 0
35 | Insurance | 0.4934% | C: 53000; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 53000; 2001-10-31 M: 0
36 | Financing Fee | 0.7448% | 80000 | 0 | 80000 |  | 80000 | 100% | 0 |  | 80000
37 | Title and Recording | 0.3894% | 41822 | 0 | 41822 |  | 41822 | 100% | 0 |  | 41822
38 | Legal | 0.1862% | 20000 | 0 | 20000 |  | 20000 | 100% | 0 |  | 20000
39 | Organization | 0% | C: 0; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 0; 2001-10-31 M: 0
40 | Cost Certification Contractor | 0.1397% | C: 15000; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 15000; 2001-10-31 M: 0
41 | Pre-Lease and Operating Capital | 2.798% | C: 300513; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 300513; 2001-10-31 M: 0
42 | Developer Profit and Risk | 3.037% | 326202.57 | 0 | 326202.57 |  | 326202.57 | 100% | 0 |  | 326202.57
43 | Hard Cost Contingency | 2.793% | C: 300000; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 300000; 2001-10-31 M: 0
44 | Soft Cost Contingency | 0.3724% | C: 40000; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 40000; 2001-10-31 M: 0
| Total Soft Costs | 15.18% | 1629973.57 | 0 | 694410.57 | 0 | 694410.57 | 42.6% | 935563 |  | 694410.57
| Total Hard & Soft Costs | 86.75% | 9317273.57 | 0 | 948374.77 | 0 | 948374.77 | 10.18% | 8368898.8 |  | 934330.228
45 | Interest Carry |  | C: 303707.2965; Equity Required D: 0; 2673399.6741 G: 0; Period To: J: 0%; 2001-10-31 K: 303707.2965; 2001-10-31 M: 0
46 | Land Purchase | 10.43% | 1120000 | 0 | 1120000 |  | 1120000 | 100% | 0 |  | 1120000
| Total Project Costs | 100% | 10740980.8665 | 0 | 2068374.77 | 0 | 2068374.77 | 19.26% | 8672606.0965 |  | 2068374.77
Cash Funds Required
| Draw # 1 |  | C: 2068374.77
Less - Non-Cash Items
| - Architects Fees |  | C: -171386
| - Legal |  | C: -20000
| - Developer Profit and Risk |  | C: -326202.57
| - Land Contribution |  | C: -1120000
| Cash Funding Required To Close |  | C: 430786.2