## Key Dates (3) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
KEY DATES
| 1999 |  | 1998
| September 10 | Friday |  | Discuss revised game plan with Causey - focus on 3rd qtr and reorganization delays
Review draft of 2000 Budget straw man with Investor Relations
Receive outstanding Corporate cost centers
| September 13 | Monday |  | Receive International regional break-out
| September 15 | Wednesday |  | Review Summary of Corporate Cost Centers with Causey (3:00 p.m.)
|  |  | September 16 | Preliminary Service Group Costs Distributed to Business Units
| September 20 | Monday |  | Review Summary of Corporate Cost Centers with Skilling & Sutton
Review 2000 Budget straw man with Skilling & Sutton
| September 21 - 23 | Tues - Thurs | Last week of Sept | Meet with Corporate Cost Centers to plan presentation to Skilling & Sutton
| September 22 | Wednesday |  | Targets distributed to Business Units
| September 27 | Monday |  | Staff budget reviews with Management
| October 15 | Friday | October 16 | Operating & Strategic Plan due to Corporate Financial Planning
| November 1 - 9 | Mon - Tues | November 10, 11 & 17 | Executive Review of Business Units
| November 19 | Friday | November 13 & 19 | Plan Revisions Due to Corporate Financial Planning
| November 24 | Wednesday | November 20 | Board Book Information to Corporate Financial Planning
| November 30 | Tuesday | November 23 | Draft of Board Book Given to Causey & Skilling for Approval
| December 6 | Monday | November 30 | Complete & Mail Books to Board Members
| December 14 | Tuesday | December 8 | Presentation to the Board
2014-09-04 15:31
C:\Users\Felienne\Enron\EnronSpreadsheets\[tracy_geaccone__40303__Plan Dates.xls]Key Dates (3)

## Key Dates
ENRON CORP
2002 OPERATING & STRATEGIC PLAN
KEY DATES
2001
| June 12 | Send out request for plan headcount & gross revenues
| June 22 | Headcount due to Corporate Financial Planning
| June 28 | Headcount submitted to Benefits & Risk Mgmt (Infor. returned to Corp. - July 13)
| July 18 | Receive EPSC charges & total est. ENW charges for Corp.
| July 20 | Guidelines & files distributed to Corporate cost centers owners
| August 13 | Corporate cost centers due to Corporate Financial Planning
| August 31 | First Draft - Assessments (Corporate ONLY)
| September 4 | Executive Review of Corporate Costs
| September 7 | Distribute preliminary assessements (ALL BUSINESS UNITS)
| September 14 | Estimated targets distributed to business units
| September 14 | Distribute final assessements (ALL BUSINESS UNITS AND CORP)
| September 20 | Distributed plan format and schedule files to business units
| October 4 | Operating & Strategic Plan due to Corporate Financial Planning
| October 9 | Board of Directors' Meeting
| October 16 | Third Quarter Earnings Release
| October 18 | Third Current Estimate Due to Corp Fin Planning
| October 18 | Presentation Pages for Executive Review to Corporate Financial Planning
| October 22 - November 8 | Executive Review of Business Unit Plans
| November 12 | Plan Revisions Due to Corporate Financial Planning
| November 18 | Board Book Information to Corporate Financial Planning
| November 26 | Draft of Board Book Given to Executives for Approval
| December 4 | Complete & Mail Books to Board Members
| December 11 | Presentation to the Board

## reviews
ENRON CORP
2002 OPERATING & STRATEGIC PLAN
PROPOSED REVIEW DATES
Business Units
Enron North America |  |  | 2 hours | Pending |  | 2
Enron Europe |  |  | 2 hours | Pending |  | 2
Enron Global Markets / Enron Industrial Markets |  |  | 2 hours | Pending |  | 2
EBS / Other Wholesale |  |  | 2 hours | Pending |  | 2
EGAS |  |  | 2 hours | Pending |  | 2
Enron Energy Services |  |  | 2 hours | Pending |  | 2
Enron Transportation Services & PGG |  |  | 2 hours | Pending |  | 2
Total Time Needed for Business Units |  |  | 14 hours |  |  | 14
Schedule
Enron North America | Mon | October 22 | 1:00 - 3:00 |  |  | 2
Enron Europe | Wed | October 24 | 8:30 - 10:30 |  |  | 2
Enron Global Markets / Enron Industrial Markets | Wed | October 24 | 10:30 - 12:30 |  |  | 2
EBS / Other Wholesale | Mon | November 5 | 1:00 - 3:00 |  |  | 2
EGAS | Mon | November 5 | 3:00 - 5:00 |  |  | 2
Enron Energy Services | Thurs | November 8 | 1:00 - 3:00 |  |  | 2
ETS & PGG | Thurs | November 8 | 3:00 - 5:00 |  |  | 2
[5 empty] | Total | 14

## reviews (2) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
BUDGET REVIEWS TO BE SCHEDULED
Group | Responsible Party | Estimated Duration | Date Scheduled
Corporate Staff Groups - Oct 1
Legal | Jim Derrick | 1/2 hour | Sept. 27 | 0.5
RAC | Rick Buy | 1/2 hour | Sept. 27 | 0.5
Accounting | Rick Causey | 1/2 hour | Sept. 27 | 0.5
Investor Relations | Mark Koenig | 1/2 hour | Sept. 27 | 0.5
Other Staff Functions | Steve Kean | 1 hour | Sept. 27 | 1
Government Affairs
Public Affairs
Enron Property
Corporate Development | Mark Metts | 1/2 hour | Sept. 27 | 0.5
HR & Community Relations | Cindy Olson | 1/2 hour | Sept. 27 | 0.5
Total Time Needed |  | 4 hours |  | 4
Global Functions - To be scheduled
Risk Management | Greg Whalley | 1/2 hour | Pending | 0.5
Finance | Andy Fastow | 1/2 hour | Pending | 0.5
Asset Operations | Kurt Huneke | 1/2 hour | Pending | 0.5
Engineering & Construction | Larry Izzo | 1/2 hour | Pending | 0.5
Technology | Mike McConnell | 1/2 hour | Pending | 0.5
Global E&P | Jeff Sherrick | 1/2 hour | Pending | 0.5
Total Time Needed |  | 3 hours |  | 3
Business Units - November 1 - 12
North America | Kevin Hannon\Cliff Baxter | 2 hours | Pending | 2
Europe | Mark Frevert | 2 hours | Pending | 2
Asia/Africa | Rebecca McDonald | 1 hour | Pending | 1
Caribbean/Middle East | David Haug | 1 hour | Pending | 1
India | Sanjay Bhatnagar | 1 hour | Pending | 1
South America | Jim Bannantine | 1 hour | Pending | 1
Gas Pipeline Group | Stan Horton | 1 hour | Pending | 1
Portland General Group | Peggy Fowler | 1 hour | Pending | 1
Enron Energy Services | Lou Pai \ Tom White | 2 hours | Pending | 2
Azurix | Rebecca Mark | 1 hour | Pending | 1
Enron Communications | Ken Rice \ Joe Hirko | 2 hours | Pending | 2
Enron Economic Development | Gene Humphrey | 1/2 hour | Pending | 0.5
Total Time Needed |  | 15 1/2 hours |  | 15.5

## bullet points (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
Targets
Income Targets
Set Net Income & Pre-tax targets
Other Objectives
Return on Investment
Cash Return on Capital Deployed
Pre-Tax Earnings on Capital Deployed
After-Tax Earnings on Capital Deployed
Funds Flow - no targets
Quarter vs Full Year targets
Quarter percentage growth same as total year percentage growth
Presentations
Free form as in prior years
Standard Format
1st Page
Pre-Tax Earnings, Net Income
Capital Deployed Ratios, Total Expenses
Headcount
Prior Year Information & Quarterly Information
Global Functions - presentations
Key Dates
Summary
Budget Review Schedule - Time Allotment
Plan for 2001 and 2002
Amount of Emphasis
Targets for 2001 and 2002
Work with Corporate Group

## Key Dates (2) (hidden)
ENRON CORP
2000 - 2002 OPERATING & STRATEGIC PLAN
BUDGET REVEIWS TO BE SCHEDULED
Corporate Groups - August 13 - 25
| Corporate Group | Responsible Party | Estimated Duration | Date Scheduled
| Corporate Devlopment | Cliff Baxter | 1 hour
| Enron Capital Mgmt | Andy Fastow | 2 hours
| RAC | Rick Buy | 2 hours
| Legal | Jim Derrick | 1 1/2 hours
| Corporate Affairs | Cindy Olsen | 1 1/2 hours
| Steve Kean | Government Affairs | 2 hours
| Investor Relations | Mark Koenig | 1/2 hour
| CAIO | Rick Causey
| Corporate Accounting | Bob Butts | 1/2 hour
| Tax | Bob Hermann | 1/2 hour
| Information Services | Phillipe Bibi | 2 hours
| Enron Property Services | Bill Donavan | 2 hours
| Compensation & Benefits | Rocky Jones | 2 hours
| Total Time Needed |  | 17 1/2 hours
Business Units - November 1- 12
| ECT - North America | Ken Rice | 3 hours
| ECT - Europe | Mark Frevert | 3 hours
| Enron International | Joe Sutton | 3 hours
| Gas Pipelines Group | Stan Horton | 3 hours
| Portland General Group | Peggy Fowler | 2 hours
| Enron Oil & Gas | Mark Papa | 2 hours
| Enron Energy Services | Lou Pai | 3 hours
| Azurix | Rebecca Mark | 2 hours
| Enron Communications | Joe Hirko | 2 hours
| Enron Renewable Energy Corp | Tom White | 2 hours
| Enron Economic Development | Gene Humphrey | 1 hour
| Total Time Needed |  | 26 hours